EMERGENCY CONSTRUCTION PROJECTS

Definition of Emergency Conditions

Fiscal Rule 2-2 of the State of Colorado Fiscal Rules defines an emergency as follows:

An emergency is a situation that creates an immediate threat to public

health, welfare, or safety, the functioning of state government, or preservation or protection of property.  There is insufficient time to obtain a written waiver of the requirements for issuance of a commitment voucher pursuant to this fiscal rule before requiring goods or services to respond to the emergency.

If a situation does not pose an immediate threat to the public health, welfare, or safety, the functioning of state government, or preservation or protection of property, it is not an emergency and these procedures cannot be used.

Scope of Emergency Procedures

In an emergency, only those goods and/or services that are necessary to respond to the emergency may be acquired without the execution of a state contract, provided that such emergency procurements shall be made with such competition as is practicable under the circumstances. (Fiscal Rule 2-2)

Procedure for Emergencies

Only CDOT’s Executive Director, the Chief Engineer or their authorized delegate may declare an emergency pursuant to Fiscal Rule 2-2.  Approval must be obtained from the Executive Director, the Chief Engineer or authorized delegate prior to procuring a contractor and commencing work.

The procedures for emergency construction projects are as follows:

1.	A written request must be submitted to the Executive Director, the Chief Engineer or authorized delegate through an Area Engineer which includes the following:

a.	A justification that an emergency exists in accordance with Fiscal Rule 2-2.  The explanation must be complete enough to describe the problem and how it qualifies as an emergency.

b.	An explanation of why the normal procurement procedures will not permit procurement of a contractor quickly enough to address the emergency.  The request should state the time that will be required to obtain a contractor using the normal procurement process and why the emergency requires a quicker response; and

c.	The scope of the emergency work, the limits of the project and the estimated cost.

2.	The Area Engineer will obtain signature approval from the Executive Director, the Chief Engineer or delegate and will return a signed copy to the Region.  If warranted by the nature of the emergency, verbal approval may be requested.  However, the written request must be submitted no later than the end of the next business day after discovery of the emergency situation.

3.	A written report of the circumstances and the nature and value of the commitments shall be made to CDOT’s chief financial officer and to the Office of the State Controller no later than the end of the next business day after discovery of the emergency situation.  Such report may be made via e-mail.

Contractor Selection for Emergency Work

Emergency work which is outside the scope or beyond the termini of an existing contract cannot be added to the contract with a CMO.  If the work was not contemplated by the original solicitation for that contractor, then it is beyond the scope and the price agreed to in that contract.  Issuing a CMO in such a situation may violate CDOT’s procedures and State Statutes applicable to government contract bidding.

Commensurate with the circumstances of the emergency, the Region will use the most competitive process possible to select a contractor.  The following procedures will be used:

1.	Preliminary Investigation:	The following items must be determined:

a.	the scope and nature of the emergency work;

b.	state date and time frame for completion;

c.	pay items and quantities; and

d.	method of measurement and basis of payment

2.	Solicitation:	As circumstances allow, bids should be solicited by phone or fax from at least three qualified contractors that can respond quickly.  It is acceptable to solicit a bid from a contractor already working in the area. If unable to solicit three bids, the reason must be documented (e.g., justifiable time constraints, limited interest, lack of qualification).

3.	Force Account Work:	If a force account is necessary, the work should be paid for in accordance with subsection 109.04 of the Standard Specifications.  If doing so is not reasonable, then documentation must be provided explaining the rationale for exceeding labor and equipment rental rates.  For example, the emergency may justify non-stop work activity for a short duration, which generally warrants higher rates. Contact the Engineering Estimates and Market Analysis Unit of the Contract and Market Analysis Branch, as needed, for assistance in justifying rates.

4.	Work Authorization:	A written authorization, Form 105 – Speed Memo, to proceed with the work, must be sent to the Contractor performing the emergency work prior to the commencement of work.  The Contractor must sign and return the authorization before proceeding.  The written authorization must include the following:

a.	scope of work and project limits,

b.	the required time to start work,

c.	expected duration of the work,

d.	estimated quantities,

e.	method of measurement,

f.	basis of payment, and

g.	estimated total cost of the work.

If payment will be by force account, include either the agreed rates for labor and equipment or the provisions of subsection 109.04, whichever is applicable.

5.	Payment Prior to Contract Signing:	Disbursement may be made upon receipt of invoices, receipts or other statements describing the goods or services utilized and the amount to be paid.  However, a Contract must be executed as soon as possible in conformance with the sections below to define future performance obligations.

6.	Submittal of Contract Information:	By the end of the next business day following selection of a Contractor, the following information must be submitted to the Agreements Unit of the Contracts and Market Analysis Branch for the preparation and execution of the emergency contract:

a.	Description and Justification:	Submit a description of the nature of the emergency and justification for the emergency procurement.

b.	Procurement Documentation:	Submit all required procurement documentation and a description of the method used to select the Contractor, including any reasons for deviating from Department policy.

c.	Basis of Payment:

(1)	Agreed Unit Price or Lump Sum.  Submit the agreed prices, units and estimated quantities, including justification for using the agreed unit price or lump sum basis.

(2)	Force Account.	When force account is used, submit justification for payment in accordance with subsection 109.04 of the Standard Specifications and the agreed hourly rates for labor and equipment.  If the hourly rates exceed those that would be paid in accordance with subsection 109.04, also submit justification for exceeding those rates.

d.	Emergency Approval.  Submit the signature-approval of the Executive Director, the Chief Engineer or authorized delegate to procure a contractor to perform the emergency work.

7.	Preparation and Execution of Contract.	The Agreements Unit of the Contracts and Market Analysis Branch will prepare and execute the Contract as soon as practical after the emergency occurrence.  The Contract will be dated retroactively on the date of the written authorization to proceed, and the Agreements Unit will provide written justification of this retroactivity to the State Controller.

8.	Administration of the Emergency Contract:	The appropriate CDOT region will administer the Contract for the emergency work in accordance with CDOT policies and procedures.

9.	The Region shall also make all necessary entries into the Trns*port and ProMIS software systems for the emergency project by the end of the next business day after selection of the Contractor.