Changing Binder Grades

This bulletin addresses possible actions when a contractor submits a proposal to change the binder grade due to the current asphalt and polymer shortage.

Changing binder grades is a significant change materially in the work.  Subsection 104.02(c) of the Standard Specifications states that:

“The term “significant change” shall be construed to apply only to the following circumstances:

- When the character of the work as altered differs materially in kind or nature from that involved or included in the original proposed construction,”

Subsection 104.02(c) further states that:

“If the alterations or changes in quantities significantly change the character of the work under the Contract, whether such alterations or changes are in themselves significant changes to the character of the work, or by affecting other work cause such other work to become significantly different in character, an adjustment, excluding loss of anticipated profit, will be made to the Contract.”

If a change in binder grades is approved by the Region Materials Engineer the change in binders requires a Change Order deleting the Hot Mix Asphalt, Stone Matrix Asphalt, or Asphalt Cement item and adding a new corresponding item.  The change order shall include a negotiated price for the new item.  That price should reflect what it would cost the Contractor to perform the work today or at some point in the future.

If a region does not want or cannot afford to increase the price on a project, or a change in the binder would not work from a pavement design standpoint, then that region may consider one of the three options in Construction Bulletin 2008-6, Polymer and Asphalt Cement Shortage, July 7, 2008.   REMINDER: an extension of project time until the plan binder is available would be considered an excusable, non-compensable delay.

It is suggested that getting documentation providing proof of planned binder grade price at the time of bid from the Contractor and invoices for the new binder grade and adding or subtracting the difference from the original bid price would be an acceptable method of justifying the difference in price between the old and new pay items.

There are discussions ongoing concerning the affected projects.  Further Construction Bulletins will be released as soon as possible with supplemental information to Construction Bulletin 2008-6. Other additional information will be provided as needed.  Please forward any pertinent information you may receive from the contractors to your Area Engineer.

If you have questions, please contact your Area Engineer in Project Development.