# Post Award Project Financial Statement: Form 65

The purpose of this construction bulletin is to help Construction project personnel better understand how the Post Award Project Financial Statement: Form 65 reflects a project budget.  This specific construction bulletin focuses on the Post-Award status and Construction and Construction Engineering sections of the form.  The intent is to give users an awareness about the Project Commitment Amount, the information on how the Total Phase C (line [18]) amount is calculated, the knowledge on how Planned Contract Expenditures show how an overrun or change order affect a budget, and finally a discussion on third party force accounts.

To access the Project Financial Statement: Form 65 in SAP use transaction code ZJ20 – Project Financial Statement: Form 65.  There is a Help document that guides you through this transaction located in the SAP Training website: http://saptraining/. Select your Region then select Project Systems then select Project Systems Lifecycle then select Project Month End/Period Close then select ZJ20 – Project Financial Statement: Form 65.

Table 1, Project Financial Statement: Form 65, describes the Header Information, Column Information, and Comments portion of the Form 65.  This table is an overview of the information in the form.  There is a more detailed PDF document at the end of the table that provides more detail about the information in ZJ20 – Project Financial Statement: Form 65.

| Table 1 - Project Financial Statement: Form 65 |
| --- |
| Header Information |
| Field Description | Description and Where to find this Information |
| I | Project Definition (formerly known as Subaccount or Project Code) | 5 digit Project Definition number. It is also the first five digits in the Funded Program. |
| II | OFMB Project Number | The OFMB Project Number consists of three parts found in SAP using transaction code CJ20N - Project Builder. Below are screen shots to help find the OFMB Number. |
| III | Project Description | This is the name of the project and once assigned it should not be changed. In SAP the information is located using transaction CJ20N - Project Builder. Highlight Project Definition and Description Field display on the right in the Work Area. |
| IV | County | This is the County or Counties in which the project is located. The information is stored in CJ20N - Project Builder in the Custom Enhancement Project Manager tab. At the bottom of the tab there is a County Details section and the counties are listed in the Description. |
| V | Federal Improvement Code | To find the Federal Improvement Code go to transaction CJ20N - Project Builder in the Custom Enhancement Project Manager tab - Federal Improvement Code field. |
| VI | Project length and Units | The projects project length and units information is located in Trns*port PES. To see the Project Length, select Projects and select the BID Project/Open Project List click in Categories tab and the length is in the Category Length (Mi/K) field. The Units are found in the General tab in the Unit System field. |
| VII | Awarded to and Date | This is the name of the Contractor and award date. This information can be found in CJ20N - Project Builder in the Custom Enhancement Agreement Award tab in the Contractor Name field and Award Date field |
| VIII | Construction Start Date | This date can be found in Trns*port Site Manager. Select Contract Administration then select Contract Records then select Contracts then select the project. Click on the Critical Dates tab and the Construction Start Date is in the Work Begin Date. Note that the Notice to Proceed date in SiteManager is what triggers the time count. |
| IX | Contract Duration and Contract Completion Type | The Contract duration and Contract Completion type are found in CJ20N - Project Builder in the Custom Enhancement Agreement Award tab in the Work Days field, Type of Days field or Completion Date field. |
| X | Run Date and Time | The Run Date and Time are calculated based on the Date and Time the Form 65 was generated |
| XI | RE: | This is the Resident Engineer who oversees the construction of the project. This information is found in CJ20N - Project Builder in the Custom Enhancement Project Manager tab in the Resident Engineer/Section Head field. |
| XII | RE Orgn Code: | This is the Resident Engineer’s Organization code. This is found in CJ20N - Project Builder in the Custom Enhancement Project Manager tab in the Org Code for Resident Engineer/Section Head field. |
| XIII | PE: | This is the Project Engineer running the construction project. This is found in CJ20N - Project Builder in the Custom Enhancement Project Manager tab in the Project Engineer/Const.Eng. field. |
| XIV | Current Status | There is a watermark that displays the Current status of Pre-Ad, Ad, Award, or Post-Award. |
| Column Information |  |
|  | AWARD | This column displays the dollar amounts in the system at time of award. These will not change once a project is awarded. |
|  | CURRENT | This column displays the current dollar amounts. The line PROJECT ALLOTMENT/CURRENT amounts come from SAP. CONSTRUCTION/CURRENT/CMOs line just below line [5] comes from Trns*port Site Manager. |
|  | PROJ'D TO COMPL | This column displays the dollar amount projected to complete the project based. PROJ’D TO COMPL amounts for the CONSTRUCTION portion come from Trns*port Site Manager. Line [9] Planned Contract Expenditures comes from SAP. PROJ’D TO COMPL amounts for the CONSTRUCTION ENGINEERING (CE) portion are all calculated except for Line [17] which carries from Trns*port SiteManager. PROJ’D TO COMPL amounts for the NON CONSTRUCTION portion come from Trns*port PES. The Project Manager should make sure these numbers are correct before the project is awarded. |
|  | SURP/(DEF) | This is the surplus or deficit column and is calculated by taking the PROJ'D TO COMPL amount subtracted from AWARD amount. |
|  | EXP TO DATE | This is the Expenditures to Date column and can be found in SAP using transaction ZF70 – FM Budget to Actuals. To get the correct number, you will have to add the appropriate Functional Areas. For example, a summation of items with Functional Area 3300 - 3399 should equal the number in row [13]. |
|  | ENCUMB BAL | The encumbered balance is the dollar amount of funds set aside for the project that have not been spent. |
| Comments |  |
| To enter comments in the comments field at the bottom of the form, use SAP transaction CJ20N - Project Builder and in the Structure tree on the left select the Construction WBS (XXXXX.20.10). Then in the Work Area on the right click on the Long text tab and enter your comments starting in Line 2. DO NOT ENTER comments in the first line of the Long text field. Line 1 does not display in the Form 65 and is reserved for the WBS element description. |
| Project Financial Statement: Form 65 |  |
| This document provides all the information on the Form 65 including where to find information, how numbers are calculated, and what information is in each tab. The document also includes how the Form 65 changes in each status (Pre-Ad, Ad, Award, or Post-Award). To see all the comments once the document is open, select Comments then Show Comments List. The comments will show where information originates or how it is calculated. For example “SAP CJ20N> Cust. enhancement> Custom Fields> Project Mgr tab> 'Resident Engineer/ Section Head'> 'Org Code'” means the data comes from SAP using transaction CJ20N, open the project and select the Custom Enhancement tab then select Custom Fields button then select Project Manager tab and the data is located in the Resident Engineer/Section Head Org Code field. Currently the Form 65_All Status document has a few fields highlighted in red. The fields that are highlighted in red are not working properly so the data is not reliable. The document is provided because a majority of the information is helpful. |

Before looking at the Project Financial Statement: Form 65 you must first update the Projected Quantities in the Trns*port SiteManager Accessories Overs and Unders report.  This should be done at least monthly, as the project progresses.  See the attached document for details on how to maintain the Projected Quantity report which populates the Overs and Unders report.

# Project Commitment Amount

Once the Overs and Unders Report is accurate the information in the Form 65 can be reviewed.  The first place to look is the PROJECT COMMITMENT AMOUNT.  This is located in the box on the upper right portion of the Form 65. The Current number is the project commitment to the Contractor.  In most cases the Current number is the total ZG Highway Construction Purchase Order (PO) amount.  Line [7] Projected must be less than or equal to the Current.  This means the anticipated budget is less than or equal to the PO amount.  If the Projected amount is greater than the Current amount, funds need to be added to the PO using a funding letter or the Projected Quantities need to be adjusted to decrease the projected total.  Remember the funding letter will need to include funds to cover the construction engineering costs.

# Construction (Phase C) Total

Next, compare the Form 65 Line [18] Total Phase C to ZF70 total budget amount for Construction WBS element.

# Figure 1 – ZJ20 - Project Financial Statement: Form 65

The Total Phase C should be less than or equal to the Construction WBS total budget amount.  The total budget amount for Construction WBS element is the total for the Construction WBS in the Revised Budget Amount (Rev bud am) column.  In this example Total Phase C is equal to $32,333,498.91 (Figure 1) and the Construction budget amount is equal to $32,373,144.00 (Figure 2).

Figure 2 – ZF70 - FM Budget to Actual Report

Revised Budget Amount (Rev Bud am) = Apportionment = Project Budget = YTD Actuals + Commitments + FY Available Balance

YTD Actuals = current expenditures

Commitments = dollars committed by a Purchase Order to Contractor or Third Party (Obligation)

FY Available Balance = budget remaining after commitments and expenditures

If the Total Phase C amount is greater than the Revised Budget Amount, then funds need to be added to the PO using a funding letter or decrease the projected total.  The funding letter must include funds to cover the construction engineering costs.  If the funding letter amount is greater than the FY Available Balance, then funds will need to be added to the Funded Program (WBS element).

For example, if the new projected to complete amount was $32,573,144.00, so $200,000.00 additional funds are needed.  The projected to complete increase could be caused by item overruns or an anticipated change order.  This project has $186,548.98 available in the Construction funded program (Figure 2).  In this case two things need to be done.  First, more funds needs to be added to this Funded Program.  Discuss where the additional funds come from with the Resident Engineer and Region Business Office.  The project needs $13,451.02 (200,000.00 – 186,548.98) more funds added to the Funded Program with a budget action.  Once the funds are added, the new FY Available Balance is $200,000.00.  Next a funding letter for $200,000.00 will be needed to increase the budget amount.

# Planned Contract Expenditures

Use the Planned Contract Expenditures to estimate how a change order or cost overrun affects project financials.  There are three Help documents located in the SAP Training website: http://saptraining/.  Select your Region then select Project Systems then select Project Systems Lifecycle then select Project Month End/Period Close:  (1) CJR2 – Enter Planned Contractor Expenditure; (2) ZJ20 – Review Planned Contractor Expenditures; and (3) CJR2 – Delete Planned Contractor Expenditure.

The information can be entered under a participating or nonparticipating Cost Element.  The transaction allows you to enter the information in any period of the fiscal year.  The total estimate should only be entered under one period for two reasons; one it is only necessary in one field and it makes deleting the data easier.  When entering planned contract expenditures, remember to document the fiscal year, WBS element, cost element(s), and amount of planned expenditures for use when zeroing out the estimate.  You must delete the planned contract expenditures once the change order or cost overrun is accounted for in the CMOs and Overs/(Unders) rows, otherwise these cost will be counted twice in the project budget.

# Third Party Force Account

Third Party Force Account items are force account items paid to a third party such as a local entity, county, railroad, or other public utility company/agency and not to the prime contractor.  This is for work not in the contract bid items that are completed during the construction phase.  The funds come from the Construction funded program and are shown in the Commitment column.  When creating these force accounts in PES you must use these item numbers:

# Utility and Work by State or Local forces – 700-9XXXX.

Third Party non-utility construction – 700-733XX.  DO NOT use 700-733xx for regular force account work by the the Contractor.

# Third Party - Uniformed Traffic Control between CDOT and CSP – 700-73351

If traffic control with another non-state law enforcement agency is to be contracted by the Contractor, then a regular contractor force account item would be used. Example 700-70XXX.

Force account item numbers can be repeated.  This is sometimes necessary with the “generic” numbers such as 700-70034 and 700-70035 if there are a lot of unusual force accounts not covered by the regular numbers.  If the generic item numbers are used, the Supplemental Description column must be completed for that item on the worksheet.

When creating a force account as part of a change order with the prime contractor in SiteManager use 700-70XXX.  DO NOT use 700-9XXXX or 700-733XX for prime contractor item numbers.

# Text boxes

Project Commitment Amount

Difference > 0	No action required

Difference < 0 	Funding Letter required to increase Current commitment amount

To get the same information used in Figure 2 -  ZF70, select Get Variant…  button then enter RRH_F65/PE_TRK in the Variant field.  Make sure all other fields are blank. Click Execute.  Enter the Funded Program xxxxx.20.10, where xxxxx is the Project Definition.

Situation	Action

Total Phase C < Revised Budget Amount	No Action required

Total Phase C > Revised Budget Amount	Add funds to PO with Funding Letter

Funding Letter change < FY Available Balance	No Budget action required

Funding Letter change > FY Available Balance	Add funds to Funded Program with a Budget action

Project Development Manual

Section 8.01

“The term “force account” refers to construction work a public agency is allowed to perform on federal/state-funded projects using its own forces.  Specifically, it means the direct performance of highway construction work by the Department, local entity, county, railroad, or other public utility company/agency by use of labor, equipment, materials, and supplies furnished by them and used under their contract terms (23 CFR Part 635.203[c]).”