## Agenda
HOT MIX ASPHALT PRE-PAVE and PC/QA AGENDA
The items in the following agenda are minimum requirements that should be covered during the conference. The agenda may be used as is or as a base to develop a customized agenda. Personnel recommended to be in attendance are: Project Engineer, Paving Inspector, QA Tester, Region Materials Engineer, PC Tester, Superintendent, Paving Foreman, and Traffic Control Supervisor.
Project Number: |  | Resident Engineer:
Sub Account: |  | Project Engineer:
Location: |  | Contractor:
Date: |  | Superintendent:
Time: |  | Foreman:
I. Project Personnel
A. Colorado Department of Transportation Personnel
1. CDOT Project Engineer:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
2. Assistant CDOT Project Engineer:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
3.Owner Acceptance Tester (QA Tester):
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
4. Head Tester:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
5. Paving Inspector:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
6. Other
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
7. Other
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
B. Contractor Personnel
1. Superintendent
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
2. Personnel to Notify at Paving Site:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
3. Process Control Supervisor:
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
4. On Site Process Control Supervisor (if different from above):
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
5. Process Control Tester (PC Tester)
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
6. Other
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
7. Other
Name: |  | Fax Number:
Office Number: |  | Email Address:
Cell Number:
II. Attendance Roster
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
Name: |  | Office Number:
Representing: |  | Fax Number:
Address: |  | Cell Number:
City. State, Zip: |  | Email Address:
III. Escalation Process
A. Escalation Process ‐ Discuss the escalation process for paving items. What is the chain of command and how/when issues are elevated to the next level in an effort to improve communication and decision making
Comments:
B. Form 626 Field Laboratory Test Results‐ Who is responsible for preparing, providing, and signing a Form 626 if required on the project.
Owner Responsibility:
Contractor Responsibility:
C. Who will be the 3rd party, independent testing lab for dispute resolution? Has this been submitted in writing prior to the Pre‐Pave Conference?
Title |  |  | YES | NO
Asphalt Mix Dispute Lab:
Roadway Smoothness Profiling:
Comments:
D. Discuss dispute split sampling requirements (per CP 17) and the different levels of the dispute resolution process (levels 1, 2, and 3)
Comments:
IV. Special Provision Requirements
A. Distribution of Section 105 and Section 106 of the Standard Specifications:
A minimum of the following personnel should have a copy of Section 105 and Section 106 of the Standard Specifications
Title |  |  | YES | NO
Project Engineer:
Owner Acceptance Tester:
Head Tester:
Superintendent:
Process Control Supervisor:
Process Control Tester:
B. Distribution of QC/QA Software:
Which PC/QA Software is to be used on this project? : | Name: |  | Version:
A minimum of the following personnel should have a copy of the QC/QA Software:
Title |  |  | YES | NO
Owner Acceptance Tester:
Head Tester:
Process Control Tester:
The following Project Special Provisions for Hot Mix Asphalt Pavement are reviewed and discussed below. Review the specifications associated with the project, determine what has been revised from the Standard Special Provisions and discuss each difference with the project staff.
C. Project Special Provision
Comments:
D. Project Special Provision
Comments:
E. Project Special Provision
Comments:
F. Project Special Provision
Comments:
V. Standard Special Provisions
The following Standard Special Provisions for Hot Mix Asphalt Pavement are reviewed and discussed below. Review the specifications associated with the project, determine what has been revised and discuss each difference with the project staff.
A. Standard Special Provision
Comments:
B. Standard Special Provision
Comments:
C. Standard Special Provision
Comments:
D. Standard Special Provision
Comments:
VI. Schedule
A. Materials
1. Materials will be available for sampling on:
Comments:
B. Asphalt Plant
1. The asphalt plant will be ready to be checked on:
a. The location of the plant to be used is:
b. What is the contingency plan if the designated palnt breaks down?
Comments:
c. What type of Release Agent will be used?
Comments:
C. Scales and Certified Weigher:
1. Has a copy of the scale certification(s) been submitted? |  |  | YES: | NO:
Comments:
2. Has a copy of the weigher certification(s) been submitted? |  |  | YES: | NO:
Comments:
3. Weigh tickets shall contain information required by the owner, as listed in section 109.01 of the Standard Specifications for Road and Bridge Construction. Is the Contractor's plant set up to print the tickets with the information required? |  |  | YES: | NO:
Comments:
4. The Contractor shall provide a daily list of haul vehicles and required information per specification (CDOT subsection 109.01). Who will provide this to the Owner and who from the Owner's Agency will accept it from the Contractor?
Comments:
5. Random scale checks are required in the Standard Specifications (CDOT 109.01).
Comments:
D. Paving Schedule
1. The Contractor will commence paving on:
2. The paving equipment will be set up and ready to be checked on:
3. How many days per week does the Contractor intend to work?
4. What hours does the Contractor intend to work?
5. Where will paving start?
6. What width will be paved?
7. What paving sequence will be followed?
Comments:
8. Are there any concerns with the pahsing plan?
Comments:
9. Who should be notified if an asphalt truck is rejected?
Comments:
E. All Occupational Safety and Health Administration (OSHA) safety procedures must be followed. Discuss how the paving operation will be affected by OSHA requirements.
Comments:
F. What method will be used to determine pavement thickness?
Comments:
G. How does the Contractor and CDOT plan to address materials overruns?
Comments:
H. Other scheduling items that will affect the start of asphalt paving include:
Comments:
VII. Mix Design
A. Has the HMA Mix Deisgn and CDOT Form 429 been submitted to the Owner? |  |  | YES: | NO:
Comments:
B. Has the HMA Mix Design been reviewed by the Owner |  |  | YES: | NO:
Comments:
C. Has the HMA Mix Design (CDOT Form 43) been issued by the Owner |  |  | YES: | NO:
Comments:
D. Have the samples for CDOT acceptance testing been taken by the Contractor, and as appropriate, reduced to the size designated by the Project Engineer for compliance with CP-52? |  |  | YES: | NO:
Comments:
E. Have required Environmental Product Declarations been submitted/received for the HMA Mix Designs? |  |  | YES: | NO:
Comments:
F. The target values for Voids in Mineral Aggregates (VMA) will be established using the average of the first three volumetric field test results, or the target value specified in Table 403‐2 of the Standard Special Provisions, whichever is higher.
Comments:
G. New VMA target values will be set whenever a new or revised mix design is used and production resumes.
Comments:
H. Have incidental items been verified with the Approved Products List? |  |  | YES: | NO:
Comments:
I. No change shall be made to the ingredients comprising the approved mix design without prior written approval of the Project Engineer - this includes asphalt binder suppliers. Does the Contractor anticipate any changes needed at this time? |  |  | YES: | NO:
Comments:
VIII. Check Testing Program
A. When will check testing be performed? Note: Check testing shall be done prior to, or in conjunction with, placement of the first 500 tons of HMA. A check testing program will be conducted between acceptance testing and process control testing, per subsection 106.05 (c) of the Standard Specifications and compared to the acceptable limits shown in column 3 of Table 106‐1 of the Standard Specifications
Comments:
B. If production is suspended and then resumed, the Project Engineer may order a Check Testing Program between process control and acceptance testing personnel to assure the test results are within the permissible ranges. How with the Project Engineer notify the Contractor if this is required?
Comments:
IX. Testing Requirements
A. How will test location be determined?
Comments:
B. Which daily Rice value will be used for compaction verification? |  |  | FIELD: | REGION:
Comments:
C. What is the frequency of testing to be performed? (Refer to table 106‐1 of section 106.05 of the Standard Specifications for minimum sampling and testing for HMA)
Comments:
D. Are Quality Assurance tests to be performed in addition to Process Control tests? (All jobs including "M" projects greater than $150,000 require testing). If yes, how often and who will be responsible to schedule the QA tests? |  |  | YES: | NO:
Comments:
E. The turnaround time for test results for both QA and PC tests is immediately upon completion. Discuss any potential deviations from this requirement. What is the anticipated turnaround time?
Comments:
F. Split Samples: During production, split samples of randomly selected acceptance tests will be compared to the permissible ranges shown in Field Materials Manual, Colorado Procedure 13 (CP-13) Table 13-1. The minimum frequency will be as shown in Table 106‐1 of the Standard Special Provisions.
Comments:
G. Reference Conditions: "Condition Red" reference condition requires the Contractor to be immediately notified as per subsection 106.05(c)(3) of the Standard Special Provisions. The minimum testing frequency will be increased to 1/250 tons until the Quality Level reaches or exceeds 78. If the Quality Level for the next five process control tests is below 65, production will be suspended. Is the Contractor familiar with the steps that must be taken to resume production and the testing to be performed when production is resumed?
Comments:
F. Lottman Retesting: If one or more samples fail to meet the requirements of Table 401-2, material from the area represented by the failing sample will be evaluated per Standard Specifications 401.02 (b)(2).
Comments:
X. Production and Placement
A. Compaction Test Section
1. The Contractor must establish a roller pattern and carefully record the following information. Who will be responsible from both the Owner and the Contractor to document and verify prior to paving continuance?
a. Type, size, amplitude, frequency, and speed of roller
b. Tire pressure for rubber tire rollers
c. For vibratory rollers, is it vibratory or static?
d. Surface temperature of mixture behind the lay‐down machine and subsequent temperatures and densities after each roller pass.
e. Sequence and distance from lay‐down machine for each roller and total number of passes of each roller to obtain specified density.
Comments:
2. When a successful Compaction Test Section (CTS) has been completed, the Contractor is required to maintain the roller pattern established during the CTS for the balance of the HMA construction (i.e., the Contractor must use the same number and type of rollers and operate them at the same speed, frequency, amplitude, and in the same position, relative to the lay‐down machine, as was performed during the CTS. If the Contractor wants to perform minor changes to the roller pattern that was established during the CTS, the Contractor must perform a Roller Pass Study to demonstrate that the density is obtained with the new roller pattern before proceeding with the paving operation. The Project Team needs to agree to the definition of "minor" at the prepave meeting. Minor changes may include items such as type of roller; numbers of rollers; distance from paver; number of roller passes; and temperatures.
Comments:
3. The Contractor is responsible for testing the compaction of the pavement in the Compaction Test Section. Who will be the contact for the Contractor for the testing?
Comments:
4. Cores are required to calibrate the nuclear density gauge. The Contractor can continue to pave under the following conditions:
a. The period that the Contractor continues to pave without test results from cores shall not exceed one working day.
b. Construction proceeds at the Contractor's risk.
Comments:
5. What method will be used to bulk core samples? |  |  | Traditional Method (CP 44, Method "B") | Core Dry
Process Control (PC)
Quality Assurance (QA)
Comments:
6. A new Compaction Test Section or roller pass study will be required whenever there is a major change in the compaction process. The Project Team needs to agree to the definition of "major" at the prepave meeting. Major changes may include items such as: new mix design; change in lift thickness; or other items that could affect the nuclear density gauge correlations.
Comments:
XI. Process Control Testing
A. Has the Contractor submitted their Process Control Plan? |  |  | YES: | NO:
Comments:
B. Does the Process Control Plan, process control, project acceptance testing, and check testing frequencies meet the minimum random sampling frequency (Table 106‐1 of the Standard Specifications)? |  |  | YES: | NO:
Comments:
C. Is the Test Result Chart for each process, with tonnage and tolerance limits, posted daily at a location convenient for viewing by the Project Engineer? |  |  | YES: | NO:
Posting Location:
Comments:
D. Is the Quality Level Chart for each element in Table 106‐1 of the Standard Specifications posted daily at a location convenient for viewing by the Project Engineer? |  |  | YES: | NO:
Posting Location:
Comments:
E. Is the Process Control Supervisor for process control sampling and testing identified in the Process Control Plan (PCP)? |  |  | YES: | NO:
Comments:
F. Does the Process Control Supervisor possess one of the following qualifications? 1. Registration as a Professional Engineer in the State of Colorado 2. Level A, B, and C certifications from the Laboratory for Certification of Asphalt Technicians (LabCAT) |  |  | YES: | NO:
Comments:
G. Do technicians taking samples and performing tests possess all of the following qualifications?
1. Technicians taking samples and conducting compaction tests have Level A LabCAT certification? |  |  | YES: | NO:
2. Technicians conducting process control tests have Level B LabCAT certification? |  |  | YES: | NO:
3. Technicians determining mix volumetric and strength characteristics have Level C LabCAT certification? |  |  | YES: | NO:
Comments:
H. Does the PCP provide information to control the quality of the following:
1. Segregation |  |  | YES: | NO:
2. Longitudinal Joint Construction |  |  | YES: | NO:
3. Transverse Joint Construction |  |  | YES: | NO:
4. Smoothness |  |  | YES: | NO:
a. This project is: |  |  | Profiler (MRI):
Comments:
I. The Contractor will report the results of the process control tests to the Project Engineer in writing at least once per day. Where and when will this be performed?
Comments:
J. Has the Contractor's Processy Control Plan been accepted and approved in writing by the Project Engineer? |  |  | YES: | NO:
Comments:
K. Has the Contractor submitted the Contractor's Binder Field Quality Plan to ensure requirements of CP 11, Section 14 ‐ Certifying Suppliers Providing Performance Graded Binders? |  |  | YES: | NO:
Comments:
XII. Striping
A. Is the Subcontractor or Contractor installing the striping? |  |  | PRIME: | SUB:
Comments:
B. When will striping occur?
Comments:
C. What material will be used?
Comments:
D. Have Materials Data Sheets been submitted? If so, have they been approved? |  |  | YES: | NO:
Comments:
E. Has the striping plan been submitted? If so, has it been approved? |  |  | YES: | NO:
Comments:
XIII. Traffic Control
A. Method of Handling Traffic (MHT):
1. Has the MHT been submitted for the Hot Mix Asphalt Pavement placement operation? |  |  | YES: | NO:
If no, when will it be submitted?
Comments:
2. Has the MHT been submitted for the striping operation? |  |  | YES: | NO:
If no, when will it be submitted?
Comments:
3. Is the traffic control plan approved? |  |  | YES: | NO:
Comments:

## BP Segregation
SUGGESTED BEST PRACTICES FOR MINIMIZING SEGREGATION
1. Aggregate Stockpiles:
A. Build in Layers
B. Avoid any procedure that will allow the aggregate to be pushed or dumped over the side of a stockpile
C. Separate to prevent intermingling
D. Aggregate Handling:
i. Loader operator works full face of stockpile
ii. Install dividers on the “cold feed” bins to prevent the material from flowing into an adjacent bin
iii. DO NOT pile the aggregate so high it flows over the dividers
2. Loading the Surge Silo: (if the plant has a “batcher or “Gob Hopper” at the top of the silo)
A. Adjust the conveying devises to deposit the material in the center of the batcher or gob hopper
B. Keep the gates on the batcher or gob hopper closed unless dropping a load of mix
C. Close the gate on the batcher or gob hopper before it is empty to prevent the material from dribbling into the silo
3. Loading Trucks
A. Keep the gates on the bottom of the silo closed so the material does not dribble into the trucks
B. Take care to center the trucks (left to right) when loading
C. Load trucks in multiple drops with the first drop at the rear, second at the front and then alternate dumps
D. If the mix is prone to segregation, you should avoid loading the trucks by “slowly” driving forward while dropping the mix from the silo
4. Dumping Trucks:
A. To provide as surge of material to the paver, when using end dump type trucks, the box should be raised until the mix moves to the rear of the bed charging the tail gate prior to releasing the load
B. If any mix is spilled on the roadway, in front of the paver while dumping the truck, the spilled mix should be removed from the roadway before the paver moves forward across the mixture on the grade
5. Laydown Operations:
A. Only dump the wings on the paver hopper at the end of the paving day and utilize this material in the night taper joint or waste the material
B. To provide consistent flow of material to the screed and avoid gradual deceleration/ acceleration, the paver should be started and stopped quickly at normal operating speed
C. Keep the hopper more than half full at all times and maintain the height within 1 inch the entire paving day
D. The auger height should be adjusted so the bottom of the auger is at least two (2) inches above the finished surface of the HMA mat
E. Adjust the feed sensors to keep the material near the center of the auger at all times
F. Correctly adjust the lead and tail crown of the screed so that the surface of the HMA behind the paver is uniform in appearance and texture
G. Install or verify the material management kits are installed and functioning properly. This includes the “kick back” paddles under the gear box and outer edges of the auger
H. Adjust the flow control; gates at the rear of the hopper so that:
i. The slat conveyors run continuously
ii. The amount of material being presented to the augers allows for them to run almost continually, (minimum of 80% of the time)
6. Windrow Elevators
A. When using pickup machines they should be adjusted so that all of the HMA is removed from the surface
7. Troubleshooting
A. If segregation is observed behind the paver, check the trucks as they arrive and are dumping to see if the mix in the truck is segregated
B. The risk of causing thermal segregation is increased when paving in cooler temperatures

## BP Smoothness
SUGGESTED BEST PRACTICES FOR PAVEMENT SMOOTHNESS
Paver Operations - Best Practices and Innovations
Keep the hopper full: If you are not using a hopper insert leave as much surge as possible between truck exchanges and do not run the hopper empty. This will minimize “truck fans” by allowing hot, uniform material from the next truck to blend with mix from the previous dump. Keeping your mat as thermally uniform as possible will result in better densities.
Controlled hopper wing cycling: The wings are where the large, cooler stone tends to collect if not properly reintroduced back to the mix. Regular cycling, where allowed by spec, will reduce large buildups of this segregated material. Don’t wait until you are “out of material” to cycle the wings
Use a hopper insert: If you are using pick up machines and windrow paving use a hopper insert. It will reduce or eliminate segregation.
Keep a constant head of material at the spreading augers: A consistent flow of material to the spreading augers will prevent them from spinning too fast or too slow, which can cause longitudinal segregation. As a rule of thumb, a proper head of material is ½ up the spreading auger. Constant changes in the head of material make waves in the mat. If allowed to rotate too fast, longitudinal stripes will occur in line with the reversing augers; too low a rate and the larger stone will drop and collect at the bearing support
Time the conveying and spreading systems: Ensure the ratio pots or flow gates are set to deliver enough material to the spreading augers to keep them running continuously. Set your sonic feeds and leave them there.
Keep your paver speed steady: Drag race paving may be entertaining but stops and starts cause the head of material to rise and fall changing the mat thickness. This not only affects ride but can detrimentally affect density.
Correct lead crown setting and proper strike off adjustment: Equipment fine-tuning issues will help eliminate longitudinal segregation. String line your screed before every job and introduce the correct amount of lead crown; usually 1/8 - 1/4 inches. Make sure your strike offs are correctly aligned. Refer to your owner’s manual for the recommended procedure.
Correct spread auger length: Once you have the job planned out if you need to build up the spreading augers then DO IT. Trying to compensate for spreading augers that are too short by running them faster will only result in segregation. This only gets worse with more gap graded mixes. If you have a 20’ screed and the job calls for wide paving then BUILD UP THE SCREED; use the auger extensions, wide mat grade supports and the outboard bearing supports. The finished jobs will more than compensate for the time involved in the buildup. Then plan the layout so you can maximize the use of the built-up screed.
Use Thermal guns: Equip your paver operator and roller hands with thermal (infrared) handheld thermometers and use them to monitor changes in the mat temperature. Establishment of a thermal range during the test strip process gives you a working range to be used throughout the paving project.
Don’t broadcast material across the mat: This just gives the appearance of a segregation problem. Don’t rake material off the joint onto the new mat. Don’t walk on the fresh mat.
Train your personnel: Not only in the operation of the equipment but in the art of reading mat defects. The sooner these defects are identified the sooner remedial action can be taken. Remember when the only tool you have is a hammer every problem looks like a nail.
Pave predominately uphill: On steep grades in mountainous terrain, pave uphill when possible. Control of material and speed of equipment is easier to maintain when paving uphill. Paving downhill may be problematic with paver and roller speeds. This may cause "ripples" in the mat that are difficult to remove. The mat may shove and tear more when operations proceed downhill, requiring patching or other undesired corrective work. QC should be onsite to monitor densities when steep grades require a change in the roller pattern.
NOTE: It is not intended to change the direction of the paving operation in rolling terrain. If the roadway grade is predominately in the uphill or downhill direction on mountain passes or other significant elevation changes, paving uphill provides a better product.
Job Set Up - Best Practices
Partnering: All personnel involved in the construction planning and design need to meet before the job so we can all “be on the same page” and resolve possible problems before they arise.
Pre Paving Planning Meeting: Meet with your crew every day to review the plan for the day’s construction and expectations. Plan the truck route, plan the job layout, and assign people to required tasks.
Communication: Constant communication with all the elements of the paving process from design engineers to the lute man. This keeps all phases of the job on schedule and free of “Uh Ohs”.
Mix Selection: Ensure the mix is of an adequate design for both strength and workability. Mind your temperatures.
Machine Maintenance: Not only does well maintained iron contribute to a more pleasant work environment it shows your people that you care enough about them to give them the best tools. It provides for a safer work environment and a more productive and profitable organization.
Smoothness-Thickness-Yield: The inspectors and field personnel need to be aware of the paving fundamental that yield, minimum thickness, and smoothness cannot be obtained at the same time.
Crew Training: Not only in the operation of the equipment but in the art of reading mat defects. The sooner these defects are identified the sooner remedial action can be taken. Remember when the only tool you have is a hammer every problem looks like a nail.
Know the Consequences: Of improperly operating the machines, improper principles and techniques of paving, rolling and trucking of poor safety awareness. Designate a “job site safety man” know the way to emergency medical care.

## BP Lonigtudinal Jt
SUGGESTED BEST PRACTICES FOR LONGITUDINAL JOINT CONSTRUCTION
BE CONSISTANT: Decide on a plan and stick with it.
COMMIT TO A GOOD JOINT: Quality contractors build quality joints.
MAINTAIN A PROPER TAPER: Tapers range from near vertical to 12:1. Regardless of what taper is used, keep it consistent. Vertical edges and notches as vertical as possible. Keep edges confined as long as possible. Maintain a Proper “Head of Material”.
MAINTAIN PROPER OVERLAP: Keep overlap consistent typically from 0-1.5 inches. Place proper amount of HMA at the joint: Too little will allow water to enter the joint. Too much will cause a ridge which will carry water and interfere with compaction. DO NOT RAKE THE JOINT! If raking to correct improper amount of material, just bump the joint, DO NOT BROADCAST loose material across the mat.
USE PROPER ROLLING TECHNIQUES!

## BP Breakdown Roller
SUGGESTED BEST PRACTICES FOR BREAK DOWN ROLLER OPERATIONS
1. Communicate with paving crew and foreman for job requirements prior to the arrival of asphalt.
2. Confirm maintenance and water system checks – done on a daily basis to rollers.
3. Determine lift thickness – base or surface riding course.
4. Be aware of material temperature – at delivery to paver and behind screed.
5. Determine rolling drum mode – vibratory or static.
6. Make required amplitude adjustments both roller drums – depending on mix design, material thickness, and temperature zone.
7. Optimize water system controls – to avoid material pick-up and eliminate excessive water usage.
8. Establish proper rolling pattern – determined by paving width, roller drum width, unsupported edges, and drum overlap.
9. Determine rolling speed – to achieve proper impact spacing and meet smoothness requirements.
10. Monitor rolling temperature – and work within optimum temperature zones.
11. Make required rolling coverages – to achieve density requirements.
12. Adjust rolling operations – to satisfy density, smoothness, and production rates.
13. Maintain consistency throughout the entire shift.

## BP Finish Roller
SUGGESTED BEST PRACTICES FOR FINISH ROLLER OPERATION
1. Communicate – with paving crew, foreman and breakdown roller operator for job requirements.
2. Confirm maintenance and water system checks – done on a daily basis to rollers.
3. Be aware of material temperature – avoid “tender zone.”
4. Determine rolling drum mode – vibratory or static depending upon requirements to achieve density and smoothness.
5. Optimize water system controls – to avoid material pick-up and eliminate excessive water usage.
6. Establish proper rolling pattern, – determined by paving width, roller drum width, unsupported edges, and drum overlap.
7. Coordinate final rolling process with QA / QC personnel
8. Monitor rolling temperature – and work within optimum temperature zones.
9. Make required rolling coverage’s – to achieve density requirements and to remove drum edge marks.
10. Maintain consistency throughout the entire shift.

## BP Paver Operators
SUGGESTED BEST PRACTICES FOR PAVER OPERATORS
Safety operates the paver using "Best Practices" procedures, to produce the highest-quality pavement possible.
1. Select a paving speed that balances delivery, paver capacity and the compaction process and pave with few if any extended stops.
2. Work with screed operator in establishing and maintaining the head of material within a plus or minus one inch tolerance.
3. Steer the paver holding to a pre-determined reference.
4. Direct the truck driver to raise bed and exit when empty
5. Utilize rapid, but smooth start and stops to help prevent end-of-load roughness (if stopping is necessary.)
6. Observe HMA being discharged into paver hopper or insert for changes in characteristics of the mix.
7. Monitor paver for unusual noise or vibration (notify the proper person to take corrective actions).
8. Work with dump person to make sure truck does not bump paver, or let hopper run low.
9. Work as a team member.

## Pre-Pave Checklist
Hot Mix Asphalt Pre-Paving Conference Agenda Checklist
This checklist can be used during construction to verify compliance with CDOT standards and specifications.
| YES | NO | N/A
Prepaving Conference held?
Asphalt Plant | YES | NO | N/A
a. Asphalt Plant Operator has approved mix design?
b. Asphalt Plant Operator has current air quality certification?
c. Asphalt plant has been inspected and is in good mechanical condition?
d. Stockpiles are built to minimize segregation and built in layers?
e. The aggregates are being handled in a manor to reduce segregation? (working full face of stockpile, material in one bin doesn't flow into another?)
f. Gates on batcher closed unless dropping load of mix?
g. Trucks are loaded in multiple drops with first drop at rear, second at front, then alternating?
h. Mix not dribbling into truck to complete load?
i. Proper amount of lime added uniformly?
j. Correct amount of water added uniformly?
k. Pug mill uniformly mixing aggregate, water, lime?
l. Drum mix plant operating efficiently?
Subgade | YES | NO | N/A
a. Graded and compacted properly?
b. Soft spots corrected?
c. Proof Rolled?
d. Cross-slope, elevation & alignment correct?
e. Ground conditions suitable?
f. Approved?
Overlays | YES | NO | N/A
a. Patching complete?
b. Crack sealing complete?
c. Surface dry and swept clean including edge of pavement?
d. Manhole covers, drop inlets, and valve boxes identified and protected?
e. Ground conditions suitable?
Laydown Operations | YES | NO | N/A
a. Method of Handling Traffic (MHT) approved?
b. Weather conditions acceptable for paving? Ambient and surface temperature?
c. Stations established to allow yield checks and material placement?
d. Material placement location, thickness, yield checks, and temperature documented?
e. Temporary and permanent pavement marking plans approved?
f. Adequate control provided to place final striping?
g. Temperature of delivered plant mix meets specifications?
h. Any rejected areas of pavement (segregated or soft spots) are corrected prior to placing additional lifts?
Prime Coat, Tack Coat, Rejuvanting Agent | YES | NO | N/A
a. Proper application of tack coat on pavement before overlay?
b. Type and grade identified by Certificates of Compliance and delivery tickets?
c. Sampled properly?
d. Applied at proper rate and temperature?
e. Properly diluted with water?
f. Stored properly?
g. Allowed to "break" after application? (Dried and sticky, not wet and fluid)
h. Tack coat application rates comply with plans and specifications?
i. Tack coat application rates producing desired results?
j. Tack coat application rates verified by test section?
k. Tack coat application rates approved?
l. Placed on edges of pavement and curbs?
m. Distributor equipped with proper spread rate and temperature controls?
n. Distributor capable of positive cut-off?
o. Spray bar/nozzles delivering material uniformly without streaking?
p. Spray width properly set?
q. Tank stabbed or load readings taken on level ground?
Aphalt Paver | YES | NO | N/A
a. Screed checked for trueness with a string line?
b. Equipped with full-width augers?
c. Equipped with a full-width vibratory screed?
d. Automatic leveling ski of proper length?
e. Approved?
f. Wings on hopped dumped either every load or not at all?
g. Does paver stop as quickly as possible after truck finishes dumping?
h. Hopper kept more than half-full at all times?
i. Material kept at midpoint of augers?
j. Placing material at cross-slope or crown shown on typical section?
k. Producing an acceptable finish without segregation?
l. Placing material within required surface tolerance?
m. Placing material at specified thickness and yield?
Haul Trucks | YES | NO | N/A
a. Identification and distance between axles shown on Contractor's list?
b. Legal load limits calculated?
c. Scale ticket provided?
d. Within legal load limits?
1. Loads in excess of legal limit handled in accordance with specifications?
e. Raising bed before tailgate opens to provide surge of material?
f. Equipped with covers suitable to protect mix from weather?
g. Beds cleaned with an approved release agent?
h. All material removed from road when using pick-up machine?
Longitudinal Pavement Joints | YES | NO | N/A
a. Properly located in relation to lane lines (out of wheel track)?
b. Continuously string lined to delineate longitudinal joint?
c. Offset in multiple lifts?
d. Tapered, as required, for maintaining traffic?
e. Constructed with approximately 2" overlap on previously placed joint?
Transverse Pavement Joints | YES | NO | N/A
a. Smooth?
b. Within required tolerances?
Rollers | YES | NO | N/A
a. Compaction Test Section completed by Contractor?
b. Rollers operating in accordance with approved Compaction Section?
c. Vibratory rollers operating at high frequency?
d. Rubber tires correct tire pressure?
e. Obtaining density before mat cools to minimum specified temperature?
f. Removing roller marks?
g. Picking up material?
h. Rollers kept clean?
i. Traveling below 3 mph?
j. Producing required density with a consistent roller pattern?
k. Crushing aggregate?
l. Operating in vibratory mode on final pass?
m. Rolling stopped when pavement temperature below specified minimum?
NOTES: