Process to Set Up and Use Trns•port and SiteManager for Design-Build Projects

This bulletin identifies the steps and processes required to set up and use web Trns•port and SiteManager for Design-Build projects.  These projects will be administered in web Trns•port and SiteManager.

RFP (Request for Proposal) Development Phase

| Executed by | Step | Actions |
| --- | --- | --- |
| Project Staff | 1. Develop WBS (Work Breakdown Structure) - for inclusion in Book 2, Section 2, Project Management) |
|  | a. | Define minimum number of levels to be provided. |
|  | b. | Address how work directed by CMOs (Contract Modification Orders) will be tracked in project construction schedule. For example, include CMO work item under which all CMOs will be organized. |
|  | c. | Define project construction schedule requirements based on WBS |
| Project Staff | 2. Develop Form J (Contractor pricing of major work items). Please see attachment below. |
|  | a. | Identify work items, based on project technical requirements. Include project level standard work items – mobilization, field office, field laboratory, sanitary facility, design (highway, bridge and other structures) that will be paid by invoice after NTP 1 (Notice to Proceed). Determine mobilization amount and number/schedule of payments. |
|  | b. | Define units for work items – DOLLAR preferred over LUMP SUM. Best practice would be for the work items to be defined with the appropriate unit of measure. |
| Project Staff | 3. Get project funding sources. |
|  | a. | Get funding sources and categories from SAP – ZF20, ZF70. Region Business Office and HQ can assist. |
|  | b. | Adjust Form J and WBS to address reporting, proper use of funds required by different funding sources, i.e. Bridge Enterprise. |

Proposal Phase

| Executed by | Step | Actions |
| --- | --- | --- |
| Project Staff | 4. Review selected contractor’s Form J for conformance to project requirements. |
| Project Staff | 5. Create preliminary detailed cost estimate in web Trns•port. Construction work items, quantities, and unit costs will be defined in the contractor’s construction schedule in the Design phase. |
|  | a. | Use Proposal Form J and project funding sources as inputs to webTrns•port to create preliminary detailed estimate. |
|  | b. | Compare cost estimate to project budget to identify any problems and address as needed. |
|  | c. | Create proposal schedule and Notice to Contractors. |
|  | d. | Provide preliminary detailed cost estimate to HQ Cost Estimates. |
| CDOT HQ | 6. Create bid tabulation. |
|  | a. | Set up pseudo bid letting using proposal schedule and Notice to Contractors. |
|  | b. | Cost Estimates will create a bid tabulation using the preliminary detailed cost estimate as the Engineer’s estimate. |
| CDOT HQ | 7. Issue financial statement. |
| CDOT HQ | 8. Create and execute contract. |

Design Phase (after Contract Execution)

| Executed by | Step | Actions |
| --- | --- | --- |
| Project Staff | 9. CDOT issues NTP 1. |
| CDOT HQ | 10. Create SiteManager input file. |
|  | a. | Trns•port staff will transfer the project from web Trns•port. |
| Region Final Unit Staff | 11. Activate project in SiteManager. |
|  | a. | Input construction project staff that will input project data into SiteManager. |
|  | b. | Project staff can begin entering data into SiteManager. |
| Project Staff | 12. Process invoices for mobilization, field office, field laboratory, sanitary facility, and design (highway, bridge and other structures). |
| Contractor | 13. Define cost loaded work activities and quantities as design progresses. |
| Contractor | 14. Develop construction schedule. |
|  | a. | Use prices from Form J as upper level schedule activities. |
|  | b. | Define more detailed, cost loaded work activities and quantities based on Design-Build work item list which aggregate to upper level schedule activities. |
|  | c. | Submit construction schedule to CDOT for review and approval or acceptance. |

Construction Phase

| Executed by | Step | Actions |
| --- | --- | --- |
| Project Staff | 15. CDOT issues NTP 2. |

In addition, the following workflow is attached to assist project managers during the Design-Build Procurement process.

All these changes will be reflected in the CDOT Design-Build Manual.

Innovative Contracting Bulletins can be found on the Design and Construction Project Support web page at:  http://www.coloradodot.info/business/designsupport/bulletins_manuals