Timely Submittal of Final Documentation and Final LA Invoices

The purpose of this Local Agency Bulletin is to serve as a reminder that the Local Agencies must assemble and submit all supporting project documentation and the final invoice to CDOT, no later than six months of project acceptance, so that reimbursement can be completed and the project closed out in a timely manner.  Subsection 11.11, Process Final Payment, in the 2006 Local Agency Manual states:

“The Local Agency shall submit the final bill within six months after project acceptance.  If a time extension is needed, the Local Agency shall submit a letter of explanation to the Resident Engineer (or CDOT project manager).  The letter must be submitted to the Resident Engineer (or CDOT project manager) prior to the expiration of the six-month period.”

Appendix F of the Local Agency Manual, Finals Documentation, has been updated and is attached below.  The attachment includes finals documentation checklists, certification letters and example CDOT forms.  Detailed project documentation requirements are covered in Chapters 8 through 11 of the 2006 Local Agency Manual.

To aid Local Agencies in preparing their invoices to CDOT and CDOT in reviewing the billings, the attached documents have been developed by the Regional Business Offices and OFMB:

Recent FHWA National Review Team (NRT) and CDOT Internal Audits have raised concerns about project documentation and timely closure as identified below:

- A number of Local Agency projects do not have project records to support payments made to contractors.

- Cases where CDOT has completed reimbursement to the Local Agencies before required documentation was submitted by the Local Agencies.

- A project accepted in 2004 that had not been closed pending the submittal of final documentation by the Local Agency.

In these situations, incomplete documentation could jeopardize Federal-aid funding and require that the Local Agencies involved fund the entire cost of these projects. Note that the loss of funding is NOT only what is remaining in the budget, but could be the TOTAL AWARD AMOUNT, so that funds already paid to the Local Agency would be paid back to FHWA.

When the Local Agency notifies CDOT that the project acceptance letter has been issued to the contractor, the Local Agency should also identify the anticipated date of submittal of the supporting documentation and final invoice to CDOT. This date shall allow adequate time for documentation review by CDOT in order to complete project closure within six months of the acceptance date of the project.  If the CDOT project administrator has not received the documentation and final invoice by this date, the CDOT project administrator will notify the Local Agency in writing that they are delinquent. CDOT cannot process the reimbursement to the Local Agency until all documentation and a complete final invoice has been received and reviewed for compliance with state and Federal requirements.  Failure of the Local Agency to comply with documentation requirements and close projects out in a timely manner could result in loss of Federal-aid funding for the project and could potentially impact selection of future projects.

Local Agencies must ensure final documentation and final invoices are submitted in a timely manner and are in compliance with the above requirements to maintain eligibility for Federal-aid funds.  Contact the CDOT Region Local Agency Coordinator or CDOT project manager if there are any questions about these or other issues related to the administration of Federal-aid funded Local Agency projects.