109m&p

REVISION OF SECTION 109

MEASUREMENT AND PAYMENT

Section 109 of the Standard Specifications is hereby revised for this project as follows:

Subsection 109.01 shall include the following:

All work completed under the Contract will not be measured but will be paid for on a lump sum basis.  Only the lump sum price will be used to determine final payment to the Contractor, except as adjusted for incentive and disincentive payments.  All work and materials required to design and construct the project shall be solely the responsibility of the Contractor.  The work includes, but is not limited to the design, supplemental survey, geotechnical investigations and quality control testing and inspections required to complete the Contract.

Subsection 109.02 shall include the following:

The accepted quantities for the construction of the project will be paid for at the contract lump sum bid.  The lump sum bid shall be full compensation for all work, materials, labor, tools, equipment and incidentals required to complete the Contract.

In Subsection 109.06, first paragraph, delete the second sentence, and replace with the following:

Payments will be based upon an invoice submitted by the Contractor to the Engineer. The amount of each invoice shall be determined based upon the actual progress of the work performed in accordance with the Contract and associated payment schedule for activities shown on the CPM progress schedule monthly updates, as well as the value of materials on hand in accordance with subsection 109.07.

Subsection 109.06 shall include the following:

(h)	With each monthly invoice, the Contractor shall submit a letter certifying that the invoiced work was performed in compliance with the requirements of this Contract and that all necessary materials to perform such work have been provided by the Contractor or its subcontractors or vendors in accordance with the provisions of the Contract. The letter shall be signed by the Contractor’s Engineer in responsible charge of construction observation.