## April 29, 2010

### REVISION OF SECTION 108

PAYMENT SCHEDULE

NOTICE

This is a standard special provision that revises or modifies CDOT's Standard Specifications for Road and Bridge Construction.  It has gone through a formal review and approval process and has been issued by CDOT's Project Development Branch with formal instructions for its use on CDOT construction projects.  It is to be used as written without change.  Do not use modified versions of this special provision on CDOT construction projects, and do not use this special provision on CDOT projects in a manner other than that specified in the instructions unless such use is first approved by the Standards and Specifications Unit of the Project Development Branch.  The instructions for use on CDOT construction projects appear below.

Other agencies which use the Standard Specifications for Road and Bridge Construction to administer construction projects may use this special provision as appropriate and at their own risk.

Instructions for use on CDOT construction projects:

Use this standard special provision on all projects.

# April 29, 2010

# REVISION OF SECTION 108

# PAYMENT SCHEDULE

Section 108 of the Standard Specifications is hereby revised for this project as follows:

Add subsection 108.031, immediately following subsection 108.03, which shall include the following:

108.031  Payment Schedule.  The Contractor shall prepare a payment schedule which shall show the dollar amount of work the Contractor expects to complete by the progress estimate date each month for the duration of construction.  The schedule shall cover the period from the commencement of work to the expected completion date as shown on the Contractor’s progress schedule.  The payment schedule may be prepared using standard spreadsheet software such as MS Excel and submitted in electronic format.

(a)	Initial Payment Schedule.  The Contractor shall submit the initial payment schedule at the preconstruction conference.  The payment schedule shall show the total dollar amount of work expected to be completed by each month’s progress estimate date.

The amounts shown shall include planned force account work and expected incentive payments.

(b)	Payment Schedule Updates.  Once each month the Contractor shall submit a payment schedule update to the Engineer.  The schedule update shall be in the same two part format as the initial schedule and shall be submitted to the Engineer by the first day of each month.  In each payment schedule update, estimated monthly dollar amounts shall be revised to match actual progress payments made to the Contractor to date.  Each payment schedule update shall show corrected dollar amounts of work to be completed each month through the expected completion date as shown on the Contractor’s progress schedule.

(c)	Failure to Submit Payment Schedule.  If the Contractor fails to submit the initial payment schedule or a payment schedule update by the required date, the Engineer will withhold further progress payments until such time as the Contractor has submitted a current payment schedule.