February 18, 2016

REVISION OF SECTION 108

HOLIDAY WEEKEND

**NOTICE**

This is a standard special provision that revises or modifies CDOT’s *Standard Specifications for Road and Bridge Construction*. It has gone through a formal review and approval process and has been issued by CDOT’s Project Development Branch with formal instructions for its use on CDOT construction projects. It is to be used as written without change. Do not use modified versions of this special provision on CDOT construction projects, and do not use this special provision on CDOT projects in a manner other than that specified in the instructions unless such use is first approved by CDOT’s Standards and Specifications Unit. The instructions for use on CDOT construction projects appear below.

Other agencies which use the *Standard Specifications for Road and Bridge Construction* to administer construction projects may use this special provision as appropriate and at their own risk.

**Instructions for use on CDOT construction projects:**

Use in all projects.

February 18, 2016

REVISION OF SECTION 108

HOLIDAY WEEKEND

Section 108 of the Standard Specifications is hereby revised for this project as follows:

In subsection 108.08, delete the second paragraph and replace with the following:

The Contractor shall not carry on construction operations on Saturdays, Sundays or holidays unless previously arranged and approved. The Contractor shall not perform work on any day of a three or four day holiday weekend when the holiday is New Year’s Day, Memorial Day, Independence Day, Labor Day, Thanksgiving Day, or Christmas Day. Construction operations shall stop at 12:00 Noon the day before the start of the holiday weekend and shall commence the day after the three or four days have passed. The Contractor shall only make emergency repairs, and provide proper protection of the work and traveling public on these days.