104lrf2

08-01-05

REVISION OF SECTION 104

LANE RENTAL FEE

Section 104 of the Standard Specifications is hereby revised for this project as follows:

Subsection 104.04 shall include the following:

- Lane Rental Fee.  The Contractor shall pay a daily lane rental fee for lane closures on ♦ during construction as depicted in Phase B, Stages 1 and 2 of the Construction Traffic Control Plan.  This fee will be assessed for each calendar day or portion thereof that traffic on ♦ is using Phase B of the Construction Traffic Control Plan.  Different fees will be charged for Stage 1 and Stage 2 of the plan.  The Engineer may determine that the fee will not be charged for lane closures for additional work not covered in the scope of the project or for any work stoppage or extenuating circumstances, excluding weather.  The lane rental fee will not be charged for each weather day after the second consecutive weather day.

The lane rental fee will be deducted from any monies due the Contractor for work performed.  The deduction will be based on the applicable rate for any and all closures, whether work is performed or not.  This deduction will be reflected in each progress payment.  This deduction is not a penalty, but is a rental fee based upon road user costs to occupy ♦.

The lane rental fee for closures on ♦ shall be $▲ per day For Stage 1 and $▲ per day for Stage 2.

*******************************************************************************************

Instructions to designer (delete instructions and footnote marks from final draft):

♦	Insert location.

▲	Insert lane rental fee.  Lane rental fee is usually calculated based on road user costs and should be documented in the project file.