DISPUTE REVIEW BOARD REPORTAND RECOMMENDATION

SH 7 Cherryvale Road to 75th Street

BOULDER COUNTY, CO

CDOT PROJECT NO. STA 0072-010

DISPUTE #2 CONCERNING DELAY AT BNSF RAILROAD ABUTMENT 1 CAISSONS   				    XCEL ENERGY CURFEW

Hearing Dates: February 26-27, 2013

Hearing Location:   CDOT Region 4 Office									          1050 Lee Hill Road										          Boulder, CO

Hearing Attendees:	Joe O’Dea – CEI – Vice President									Matt Brinkle – CEI – Project Manager								Derek Rowland – CEI – Assistant Project Manager							Michelle Berger – CEI - General Counsel								Jeff Jackson – CEI Expert – Demand Construction Services						Keith G. Sheaffer – CDOT – Region 4 South Program Engineer					Dan Marcucci – CDOT – Resident Engineer								Chris Boespflug – CDOT Resident Engineer								Ryan Sorensen – CDOT – Project Engineer								Michael Wells – CDOT/URS – Inspector (2/26 only)						Laura Zamora – CDOT – Area Engineer								Roselle Drahushak-Crow`- Assistant Area Engineer							Leo F. Milan, Jr. – CDOT – Attorney for State							John Umbewust – CDOT Expert - Trauner								Lauren Ramirez – CDOT – Colorado AG Intern							Melissa Mullan – CDOT – Colorado AG Intern

Background:																									On November 11, 2011 Concrete Express, Inc. (CEI) (Contractor) was awarded a Contract by CDOT for $18,094,575.69 for the full reconstruction and widening, major railroad structures, MSE walls, caisson walls, drainage structures, HMA pavement, and concrete curb, gutter and sidewalk on SH 7 from Cherryvale Road to 75th Street in Boulder, CO.  A Notice to Proceed was issued on December 1, 2011.

Section 7 of the Contract incorporates the Plans, the Standard Specifications for Road and Bridge Construction dated 2011 and any Special Provisions for this Project and Revised Standard Specifications.

Due to delays associated with CMO #2 and Dispute #3, the start of the caisson drilling at Abutment 1 was delayed until June 26, 2012.  The equipment used for the caisson work required the overhead lines that Xcel had relocated to be shut down during the caisson work for safety reasons.  Due to electricity requirements during the summer, the lines had to be put back in service by 12:00 p.m., which required the Contractor to have all of its aerial equipment for caisson operations out of the air by 11:00 a.m.  In addition, there was a delay in the caisson work itself which was the subject of Dispute #1.

On July 2, 2012, the Contractor sent CDOT a letter giving notice that there was a Significant Change in the Character of the Work (SCICOW) due to the Xcel curfew which restricted the time each day that the Contractor could perform caisson work.  At a meeting on July 9, the Contractor said CDOT recognized there was a SCICOW but said it only asked the Contractor to submit related documents verifying all costs and time requests.

The Contractor submitted a Request for Equitable Adjustment and time extension on July 23, 2012.  On September 10, 2012, the Project Engineer sent a letter in which CDOT disputed the length of the delay.  After meetings and additional correspondence, the Project Engineer denied the merit of the dispute on November 8, 2012.  The Contractor rejected the denial and per Spec 105.22(c), elevated the dispute to the Resident Engineer on November 9, 2012.  After two meetings with the Resident Engineer and no agreement, the decision was made to elevate the dispute to the Dispute Review Board per Spec 105.22.

Joint Statement of Dispute:

Completion of the drilling operations for the bridge caissons for the BNSF Shoofly Bridge Structure, D-16-EB, were delayed.  Concrete Express, Inc. (CEI) believes the delay to be due to a significant change in the character of the work which required resequencing of the caissons which affected and altered CEI’s ability to complete the work in the manner and time originally scheduled.   CDOT believes this is not a significant change in the character of work because accommodations were made with working hours in an attempt to mitigate any delay. CEI and CDOT ask the DRB to determine merit and the number of working days impacted, if any. CDOT has requested an audit so dollar amounts of quantum cannot be determined at this time.

Pre-hearing Submittal:

In addition to the Plans and Specifications for the Project, both parties provided the DRB with Pre-hearing Submittals per Spec 105.23(e) which included, but were not limited to, documentary evidence relevant to the issues, serial letters, e-mails, speed memos, daily logs and handwritten notes.  Both parties essentially submitted the same documents in organized three ring binders.  Both parties provided the DRB with their lists of attendees.  The Contractor also provided an addendum to its submittal at the hearing to add its Method Statement for the caisson drilling.

Contractor Presentation on the SCICOW Due to the Xcel Curfew:

The Contactor’s position is that there was a Significant Change in the Character of the Work (SCICOW) due to the reduced work hours for work on the caissons at Abutment 1.  The delays associated with the caisson work at Abutment 1 are included in the 40 days requested in Dispute #3 and four days recommended by the DRB in Dispute #1.  The Contractor is only requesting direct costs for the reduced work hours.

The Contractor then went through the timeline which started with a letter to CDOT   dated February 10, 2012 requesting relocation of the overhead lines.  On April 26, 2012, the Contractor began drilling caissons on Abutment 3 and the Center Pier, completing this work on May 2, but could not continue to Abutment 1 due to overhead utilities being in the way.  After the lines were relocated, the Contractor could not start caisson work on June 25 because Xcel could not deenergize the lines for reasons beyond the Project.  The contractor began caisson work on June 26 under the Xcel curfew.  Due to the delay associated with Dispute #1 the caissons were not completed until July 18.

On June 27, the Contractor gave notice of Time and Cost impacts to CDOT and requested compensation per Spec 108.08(d).  A meeting was held on July 9 and recapped in CDOT’s letter of July 13 which confirmed CDOT’s direction to formally submit all impacts, costs and delays relevant to the SCICOW.  On July 23, the Contractor submitted its Request for Contract Extension and Compensation Part 1.  On August 22, the Contractor submitted its Request for Contract Extension and Compensation Part 2.  Meetings and correspondence then followed resulting in the request for the DRB.

In supporting the merit of the dispute, the Contractor referred to Spec 104.02(c) concerning the SCICOW.   Cooperation with Utilities is covered in Spec 105.11 and Compensation for Delay in Spec 108.08.  In Dispute #3, the Contractor pointed out CDOT’s responsibilities concerning utilities under the FHWA provisions which CDOT did not do.  Spec 105.11 says CDOT is to coordinate with utilities for relocation.  The Contractor did the work under the curfew and is in entitled to the cost of Extra Work per Spec 104.03.

The Contractor had to change its “As Planned” schedule due to the SCICOW which is a material difference since it could not do the caisson work at Abutment 1, the Center Pier and Abutment 3 in a continuous operation as originally planned.  The change should be compensated per Spec 104.02(c) and Spec 108.08(c).  The Contractor is not asking for delay time which was covered in Dispute #3 but is asking for the added costs caused by the Xcel curfew.

On the approved Baseline Schedule dated December 11, 2011, the duration for Activity A1170, Drill/Pour Shoofly Caissons, was six days working 12 hours as was allowed by the specs.  This is shown on Exhibit 3Q with three caissons per day, except on one day where it was four caissons.  Since the abutment caissons were only six inches apart, to meet the spec requirements, the schedule was based on “drill one and skip two”.

The contractor was concerned with drilling caissons a day apart due to the Cross Sonic Logging (CSL) requirement.  If a bulge in the concrete in an adjoining caisson was hit during the drilling, it could affect the CSL if the adjoining caisson was drilled the next day.  There was only one case where the adjoining caisson was drilled the next day.  There was also concern that the protruding rebar above the ground could trap the drill rig.  In addition, there was a fence on the east side of the wingwall which allowed access to the caissons from only one side.  The delay due to Dispute #3 did not allow the Contractor to drill at all three caisson locations in the same operation and resulted in the Abutment and Center Pier caisson using four of the six planned schedule days.

The Xcel curfew required all the vertical equipment to be moved or out of the air by 11:00 a.m. so that Xcel could energize the lines by noon.  The delay was beyond the control of the Contractor since it had requested the overhead lines to be moved and Xcel imposed the curfew.  By starting at 5:30 a.m. and completing work by 11:00 a.m., only allowed the Contractor 5.5 hours per day compared to the 12 it had planned.  Due to earlier delays, the work was also pushed into the summer when the Contractor had planned to do the work much earlier when heat would not have been a problem.

Due to drilling the Abutment 1 caissons by themselves, required the same work in a shorter time frame.  This reduced production and is compensable and should be paid for per Spec 109.10.  The SCICOW was not the Contractor’s fault and the curfew increased the duration of the work.  The additional work should be compensated.

CDOT Presentation on the SCICOW Due to the Xcel Curfew:

Due to the Xcel curfew, CDOT offered different work hours but the Contractor chose to work from 5:30 to 11:00 a.m.  The Abutment 1 caisson work was done in seven days for a total duration for all caissons of 11 days, one day of which for exploratory work.  This should be compared to the 10 day duration the Contractor showed in the May 1 revised Baseline Schedule.  The drilling on Abutment 3 and the Center Pier began on April 26 and was completed on May 2.  Abutment 1 drilling started on June 26 and was stopped on June 27 due to Dispute #1.  July 11 was an exploratory drilling day for Dispute #1 with drilling resuming on July 12 and completing on July 18.

On the May 1 schedule, Activity A1170, Drill/Pour Shoofly Caissons, showed a 10 day duration.  This activity had 50 days of float so any delay ate into the float.  The April schedule that was submitted August 22 with Part 2 of the Contractor’s request for delay showed Activity A1170 with a six day duration and 48 days of float so completion was not impacted.

You must go back to Dispute #3.  The Contractor was responsible for the delay and utility delay by the Contractor is nonexcusable per Spec 105.11.  Had the Contractor pushed to relocate the overhead lines, the hot weather would not have been a factor.

CDOT tried to help mitigate the Xcel curfew by suggesting the use of Aggregate Industries’ Del Camino concrete plant since the Broomfield plant the Contractor was using was limited in hours of operation by noise requirements.  The Contractor’s email of July 2 stated, …we would want to start as early as possible.   The Contractor’s email of July 3 stated, We would to have concrete on site as early as 5am, which means we would start drilling as early as 3am and the concrete plant would have to fire between 3 and 4 I believe.  CDOT tried to work with the City of Broomfield on the noise problem but was not successful.  The Contractor chose not to use the Del Camino plant but has since used it for other night pours on the Project.

CDOT’s email of July 19 corrected the Contractor’s July 9 meeting notes concerning the  SCICOW but did ask the Contractor to provide information on production and delay.  The caisson duration of 11 days was near the schedule duration of 10 days.  CDOT was confused by the Contractor’s request for 15 delay days in its August 22 Part 2 request versus the six days in the Part 1 request dated July 23.  There was nothing during the negotiations to reduce the days and now the Contractor says there was no delay.  Accordingly, why are we here?

Contractor Rebuttal on CDOT Presentation on the SCICOW Due to the Xcel Curfew:

In CDOT’s pre-hearing Position Paper, they said the Contractor said the lines must be deenergized if the Contractor was within 10 to 20 feet of the lines.  CDOT said the Contractor could work at night.  The responsibility for the delay was CDOT’s but the Contractor helped mitigate the delay.  The Contractor was concerned about safety for night work given the tight working conditions as shown in the pictures in Exhibit 3H.  Quality was also a concern due to the CSL testing.  Night work was a risk for the Contractor and it could lose the side of a caisson.  CDOT did work with the City of Broomfield to get concrete but was not successful.  The Contractor had past quality problems with the concrete due to air and plasticizer and was concerned with concrete quality since the Del Camino plant had not used the mix before.  The Contractor tried to mitigate impact but would not assume the risk for the CSL and quality.

Work started at 5:30 a.m. because that is when it got daylight and concrete could be delivered.  Total drilling time was 11 days.  The May 1 schedule showed 10 days and was prepared during the earlier delay.  The Contractor’s plan was for six days.  The relocation delayed the job into the hot time.  The August 22 request for 15 days was made up of nine days for Dispute #1 and six days for Dispute #2.  When Matt took over the job, he broke the delays down by dispute and the REA was clear on days.  Today the Contractor is not asking for any delay for Dispute #2

CDOT Rebuttal on Contractor Presentation on the SCICOW Due to the Xcel Curfew:

CDOT’s July 13 letter concerning the July 9 meeting did not state that CDOT agreed with the SCICOW but directed the Contractor …to submit documents, schedules, and related documents verifying all costs and time requests.  The Contractor said it planned to drill four caissons per day but the most it ever got was three per day.  The Contractor’s original duration was six days and the revised Baseline Schedule duration was 10 days; however, the change was never listed in the monthly Project Narrative.

The Contractor said it did not want to do night work due to safety and quality but has done night work later on when the girders were set and the bridge deck was poured.  CDOT expects the same quality no matter when the work is done.

The Contractor requested time for delay and now says there in none.  CDOT’s interpretation of the caisson duration is that there is a maximum of one day.  As part of its August 22 Part 2 submission, the Contractor attached a handwritten caisson plan showing the drilling pattern and dates.  This showed seven days for caissons.  A list of actual days for Abutment 1 caissons was also attached and showed 6six days for the Abutment 1 caissons.

The Contractor gave “soft” notice on February and sent a notice letter on February 10, and then went for two months discussing deenergizing or dropping the overhead line.  It then changed its means and methods requesting that the lines be moved.  Spec 105.11 states, Utility delays due to changes which are the responsibility of the Contractor will be considered nonexcusable delays.

Questions by DRB on the SCICOW Due to the Xcel Curfew:

1.  To both parties:  If the Contractor is not asking for any delay days, then what are   	we going to see tomorrow on impact?

The Contractor said it would show the cost impacts after June 27 due to the Xcel 	curfew productivity problems using the REA -Price Justification in Exhibit 2S.

The Contractor would also go over the Critical Path analysis for Dispute #3 using 	the May and June schedules to show the 40 days of delay.

Note:  After the parties presented their positions on Dispute #2, there was some confusion on what comprised the 40 days that the Contractor said it was delayed in Dispute #3 and then the Contractor dropping the delay request for Dispute #2.  The parties were requested to review what had been discussed so far in the hearing and the hearing would then continue with each party presenting it positions on the cost impact of the Xcel Curfew.

Contractor Presentation on Cost Impact Due to the Xcel Curfew:

At the hearing, the Contractor submitted a revised REA – Price Justification showing its direct costs due to the Xcel Curfew.  The revised amount was $19,694.57 without any additional railroad flagging.

If there is merit in Dispute #3 that the delay pushed the job into the summer, then the Contractor should be compensated for the additional cost impacts due to the shorter work day from the Xcel curfew per Spec 104.03, Extra Work.  The caisson work took longer because the work had to be resequenced which took more time.  The original duration of six days now became an actual duration of 11 days for all the bridge caissons.

The job was delayed and the Contractor should be compensated for extra work per Spec 109.10.  The actual caisson work took 11 days and the Contractor had planned for six days.  This amounts to five additional days.  The request is based on five days of eight hour shifts for a total of 40 hours additional costs plus any added railroad flagging costs.  The Contractor is not requesting days but direct costs due to the delay.  The Contractor then went over the revised Price Justification.

CDOT Presentation on Cost Impact Due to the Xcel Curfew:

CDOT’s position is that if there are no delay days for Dispute #2, there should be no added costs.  The costs for the added 40 hours could be included in other pay items.  The original railroad flagging had an incentive/disincentive clause based on a total number of flagging hours.  CMO #2 changed this by eliminating the disincentive so the flagging hours are not a consideration.

CDOT said it had three points on the Contractor’s inefficiency comments:					The Contractor’s production rates are flawed.  It said it was planning to work 12 			hours per day.  The Contract allows work from 7 to 7 but no night time work.

In January, the most hours that could be worked is10.

In its REA for 	Dispute #2, the Contractor based his cost submittal on 8 hours per 			day.

The Contractor’s REA letter dated October 9 attached an April 17 schedule that had a caisson duration of six days but also had 48 days of float.  The actual drilling took 10 days and there was an additional day for exploratory work for a total of 11 days but there were still 48 days of float to use up.  After the May schedule, the Contractor changed activity relationships which put the affected activities on the Critical Path.  The May 1 schedule shows a 10 day duration for Activity A1170 and 50 days of float.  The attachments to the August 22 REA showed a planned duration for Abutment 1 caissons of four days and an actual duration of six days.  At most, the delay would have been 2 days while the Project Engineer had earlier said one day.  The added time for the change in work time from 8 hours to 5.5 hours per day would have been covered by the float.  If there is no delay, there can be no costs.

Contractor Rebuttal to CDOT Presentation on Cost Impact Due to the Xcel Curfew:

The Contractor said the schedule program is based on eight hours per day but the REA was based on 12 hours per day and the curfew reduced the work day for caissons to 5.5 hours which is almost a 50% reduction in hours.  The Contractor also questioned CDOT’s two day number.  (CDOT explained the curfew only affected Abutment 1.  The reduction from eight hours to 5.5 hours in approximately a 30% reduction and 30% of the seven days it took for the caissons is approximately two days.)

The Contractor said that if CDOT had mentioned doubling up in costs because the time could be in other work items.  This would be cleared up in the audit.  The time is not in other work items and most items are Unit Price.

The schedule software uses eight hours per day but the schedule is based on days not hours.  The Contractor is not asking for delay days but rather the costs associated with the curfew.  The railroad flagging is now covered in CMO #2.

With 12 hour days, the Contractor could have chosen to work overtime to meet the caisson production rate.  This was not the case when it was limited to 5.5 hours.  The bid was based on three caissons per day but only 2 caissons per day were achieved.  If not for the curfew, they would have hit the bid production.  The lost production was due to the lack of available caissons to drill.  The actual duration of 11 days versus the planned six days is an overrun of five days.  The Contractor wants the cost of disruption associated with these five days.

As to the Critical Path and the 50 days of float, the Contractor is not asking for days.  If there is an error in the schedule logic, the Contractor has a right to correct the error.

The Contractor’s Method Statement gave a production rate of four to six caissons per day.  With the reduced work hours the Contractor decided not to start a hole if it could not be finished.

CDOT Rebuttal to Contractor Presentation on Cost Impact Due to the Xcel Curfew:

The original Baseline Schedule showed the caisson work for the Shoofly starting in January.  The maximum daylight hours for working would have been 10 hours.

The caisson activity had 50 days of float.

The caisson layout that was attached to the Contractor’s August 22 REA showed only one caisson (#8) at Abutment 1 that was planned on the same day as the caissons at Abutment 3 and the Center Pier.  This made any resequencing impact minimal.

Contractor Summary on Cost Impact Due to the Xcel Curfew:

There is a lot of information in the binders for the DRB.

The Contractor met its responsibilities.

The Contractor is not asking for additional days but only for the added costs for reduced 	production due to the curfew.

CDOT Summary on Cost Impact Due to the Xcel Curfew:

If there was no delay, then there can be no costs  per Spec 108.08(c).

If there was inefficiency, based on 11 days actual versus 10 days planned, the added time 	is only 1 day.  The most days would be two days based on the time analysis that has been 	discussed.

In Dispute #3, the Contractor caused the delay by changing from dropping the overhead 	lines to relocating them.  Therefore, the Contractor is the one responsible for the work 	being done in the summer.

The hearing was adjourned to allow for monetary considerations pending the audit.  The DRB will consider merit and quantum concerning cost impact due to the Xcel curfew, if any, and make its Recommendation.

Findings:

- The May 1, 2012 revised Baseline Schedule, which was agreed to by both parties, shows Activity A1170, Drill/Pour Shoofly Caissons, with a duration of 10 days.

- The Contractor’s Initial REA dated August 22, 2012 requested a 15 day delay and the costs associated with a 15 day delay; however, the caisson layout and daily schedule for all of the caissons on the Shoofly Bridge attached to the REA indicated the Contractor planned two to three caissons per day with a total duration of seven days.  In its revised REA dated October 10, 2012, the Contractor requested a six day delay and the costs associated with a six day delay.

- The Contractor said it planned to work 12 hours per day.  Since the original Baseline Schedule planned the caisson work to be done in January, it would not have been possible to work 12 hours as the Project Special Provision, Revision of Section 108 – Prosecution and Progress states, The Contractor shall establish daily working hours, Monday through Friday during daylight hours…  It should also be noted in the Contractor’s REA cost requests, it converted delay days into hours using eight hours per day.

- In the Contractor’s REA letter dated October 10, 2012 under REA (2), the Contractor stated, CEI was able to move its work crews working on the caissons to other work in order to complete a full work day and mitigate CDOT’s damages.  However, in is revised compensation request presented at the hearing, the Contractor requested compensation for all of the hours to complete the caisson work using eight hours per day.  This seems to conflict with the statement in the Contractor’s REA on mitigating CDOT damages.

- The actual duration for all the caisson work on the Shoofly Bridge was 11 days.  If the one day is excluded for the exploratory caisson work related to Dispute #1, the actual duration for completing all of the caisson work is 10 days.  Since the actual duration is the same as the duration in the revised Baseline Schedule, there is no increase in duration for the Shoofly Bridge caisson work and hence no loss in productivity.

Recommendation:

1.   The Contractor withdrew its request for any delay time at the hearing.  Accordingly, the 	DRB  accepts the Contractor’s position of no time for delay due to Dispute #2.

2.    The Contractor’s request for compensation for reduced working time is found to be 	 	 without merit.

Respectfully submitted, this 8th day of March 2013.

W. H. Hinton II