DISPUTE REVIEW BOARD REPORTAND RECOMMENDATION

SH 7 Cherryvale Road to 75th Street

BOULDER COUNTY, CO

CDOT PROJECT NO. STA 0072-010

DISPUTE #3 CONCERNING OVERHEAD UTILITY DELAY AT BNSF RAILROAD                     					ABUTMENT 1

Hearing Dates: February 26-27, 2013

Hearing Location:   CDOT Region 4 Office									          1050 Lee Hill Road										          Boulder, CO

Hearing Attendees:	Joe O’Dea – CEI – Vice President									Matt Brenkle – CEI – Project Manager								Derek Rowland – CEI – Assistant Project Manager							Michelle Berger – CEI - General Counsel								Jeff Jackmond – CEI Expert – Demand Construction Services					Keith G. Sheaffer – CDOT – Region 4 South Program Engineer					Dan Marcucci – CDOT – Resident Engineer								Chris Boespflug – CDOT Resident Engineer								Ryan Sorensen – CDOT – Project Engineer								Michael Wells – CDOT/URS – Inspector (2/26 only)						Laura Zamora – CDOT – Area Engineer								Roselle Drahushak-Crow`- Assistant Area Engineer							Leo F. Milan, Jr. – CDOT – Attorney for State							John Umbewust – CDOT Expert - Trauner								Luke Mattenwodt– CDOT – Intern Observer

Background:																									On November 11, 2011 Concrete Express, Inc. (CEI) (Contractor) was awarded a Contract by CDOT for $18,094,575.69 for the full reconstruction and widening, major railroad structures, MSE walls, caisson walls, drainage structures, HMA pavement, and concrete curb, gutter and sidewalk on SH 7 from Cherryvale Road to 75th Street in Boulder, CO.  A Notice to Proceed was issued on December 1, 2011.

Section 7 of the Contract incorporates the Plans, the Standard Specifications for Road and Bridge Construction dated 2011 and any Special Provisions for this Project and Revised Standard Specifications.

On February 10, 2012, the Contractor sent CDOT a letter requesting the relocation of the overhead utility lines at Abutment 1 that interfered with the drilling of the caissons.  The issue was a discussion topic at the weekly Utility Coordination meetings.  In April 2012 another letter on the issue was sent to CDOT and the utilities.  On April 26, 2012, caisson drilling commenced at Abutment 3 and the Center Pier and that work was completed on May 2.  The lines were ultimately relocated so that caisson drilling at Abutment 1 began on June 26, 2012.

The Contractor submitted a Request for Equitable Adjustment and time extension on October 10, 2012.  After two meetings with the Project Engineer, the  Project Engineer sent a letter dated November 8, 2012 in which CDOT agreed there was a delay caused by the overhead line relocation but felt it was impossible to determine if the delay would delay the completion of the project.

Per Spec 105.22(c), the Contractor elevated the dispute to the Resident Engineer on November 9, 2012.  After two meetings with the Resident Engineer and no agreement, the decision was made to elevate the dispute to the Dispute Review Board per Spec 105.22.

Joint Statement of Dispute:

Drilling operations of the bridge caissons for the BNSF Shoofly Bridge Structure, D-16-EB, were delayed due to utility lines in conflict with the caisson drilling equipment.  CEI believes it is due additional time and compensation now for this delay.  CDOT believes the project has not yet realized this delay and has agreed to reevaluate the time and compensation issue if the project extends past its original 431 working day contract.  CEI and CDOT ask the DRB to determine merit and the number of working days impacted, if any.  Because of the dollar amount of this dispute, an audit was automatically triggered so dollar amounts of quantum cannot be determined at this time.

Pre-hearing Submittal:

In addition to the Plans and Specifications for the Project, both parties provided the DRB with Pre-hearing Submittals per Spec 105.23(e) which included, but were not limited to, documentary evidence relevant to the issues, serial letters, e-mails, speed memos, daily logs and handwritten notes.  Both parties essentially submitted the same documents in organized three ring binders.  Both parties provided the DRB with their lists of attendees.  The Contractor also provided an addendum to its submittal at the hearing to add its Method Statement for the caisson drilling.

Contractor Presentation on the Overhead Utility Delay:

The Contractor stated that the delay caused by the relocation of the utility overhead lines was an excusable and compensable delay for which it should be granted an extension of the Contract time and associated costs.  The Delay impacted the caisson drilling which was on the critical path and costs have been incurred by the Contractor.

The Contractor then went through the timeline which started with an email dated February 8, 2012 and letters to CDOT and Xcel dated February 10, 2012 requesting relocation of the overhead lines.  On April 19, 2012, the Contractor gave a second notice to CDOT and Xcel and on April 20 the first notice to CenturyLink concerning relocation of the overhead lines.  Due to problems with the railroad agreement which was finally resolved in a CMO #2, the Contractor did not have access to the railroad right-of-way until April 17 at which time it laid out the caissons on Abutment 1 and found conflicts on two of the wingwall caissons. A meeting was held with CDOT on April 18 to discuss the problem.  On April 26 the Contractor began drilling the caissons on Abutment 3 and the Center Pier and completed this work on May 2.

In supporting the merit of the dispute, the Contractor referred to 23 CFR 635.309 which required CDOT to submit a statement that “...either all right-of-way clearance, utility and railroad work has been completed or that necessary arrangements have been made for it to be undertaken and completed as required for proper coordination with physical construction schedules”.  The Contractor stated that it had complied with the notice and timelines specified in the Utilities Special Provision.  The overhead lines were not shown on the Plans to be relocated and the Utilities Special Provision did not list the lines in the section covering lines to be relocated.

The Contractor said Spec Section 105.11 states, work shall not commence until arrangements for the protection of the utilities have been made and it considers relocation as protection.  This section also requires CDOT to notify the utilities but the Contractor does not know what CDOT did.  The lines were finally relocated by June 21as the Contractor had requested on February 10, 2012 and if CDOT had followed what they were to do per the specs there would not have been a delay.

The Contractor said it gave notice, followed the Contract and nowhere were the lines shown to be relocated.  The Contractor also did everything it could to mitigate the impacts and resequenced the work on Abutment 3 and the Center Pier.  The delay was not due to any fault or negligence of the Contractor and what direction CDOT did give was not possible to follow.

CDOT Presentation on the Overhead Utility Delay:

The Project was designed for construction to be performed with the overhead lines left in place.  There was only one wingwall caisson that was in conflict with the lines.  The line could have been deenergized.  Based on several utility meetings with the Contractor, the Contractor planned to work around the lines rather than relocate them.  On April 19, 2012, the Contractor changed its approach requiring the lines to be relocated.  The relocation was completed on June 21.

In the REA and the Addendum, the Contractor asked for delay for an activity that had 50 days of float.  The Contractor has not shown overall Project delay as required in Spec 108.08. The Contractor changed it means and methods by requesting that the lines be relocated after earlier indications that it planned to work around the lines.  Spec 105.11 states, Utility delays due to changes are the responsibility of the Contractor and will be considered nonexcusable delays.

CDOT went through a timeline of events and emphasized the weekly utility meeting notes which indicated the Contractor was going to work around the lines or later have the lines dropped.  It was not until April 19 that the Contractor indicated the lines had to be relocated.

CDOT acknowledged that the relocation of the lines took 37 days but does not acknowledge that the relocation delayed the Project.  The Contractor must prove the schedule impact on the completion date and has changed the delay from 37 days in its REA to 34 days in its pre-hearing submittal.  The Plans and Specs do not indicate the lines were to be relocated but rather that they were to be left in place.  During the bidding period one contractor had asked about Xcel reenergizing the lines and this was indicated in the note that the Contractor had before bid.  Spec 105.11 states, The Contractor shall consider in the bid proposal all of the permanent and temporary utility facilities in their present or relocated positions as shown in the Contract and as revealed by site investigation.

CDOT questioned why the Contractor waited until April 19 to request that the lines be relocated.  This was not timely since the Contractor was told that there was a six week permitting process by the railroad.  The Contractor changed its means and methods and any delay is nonexcusable.

Contractor Rebuttal on the Overhead Utility Delay:

The Contractor submitted a new exhibit (3U), which contained the Methods Statement – Caisson Drilling and two court cases, be added to its prehearing submittal.  CDOT objected that the submissions were new material that had not previously been a part of dispute discussions.  The DRB allowed the Methods Statement since it had previously been submitted to CDOT but said the court cases would be withheld.

The Contractor questioned why CDOT waited from February 10, 2012 until April to do anything about the problem.  Since the lines were not identified to be relocated anywhere in the documents, the interference was unforeseen and per Spec 105.11 The Engineer will make arrangements with either the utility owner or the Contractor to accomplish the necessary adjustments or relocations when not otherwise provided for in the Contract.  CDOT did not do what was required of CDOT under Spec 105.11to have the lines moved, dropped or deenergized.

Under the Spearin Doctrine, the Contractor has a right to rely on the correctness of the Plans and the lines were not identified to be relocated on the Plans.  The Contractor had to wait to enter the railroad ROW to layout the caissons until there was an agreement with the railroad.

In its February 10, 2012 letter, the Contractor listed in the Details of the Conflict – Required Relocation Completion Date: February 22, 2012.  The Contractor always required relocation.  The relocation could have been done by any method to get the lines out of the way, including dropping the lines or deenergizing them.  Until April 17 when the Contractor constructed the temporary shoring wall and then laid out the caissons, the Contractor did not know what the actual overhead line interference was.

The “unofficial” notice referred to by CDOT was given in the April 8 email from the Contractor.  The delay of two days in the “official” notice in the Contractor’s April 10 letter did not prejudice CDOT.

The Contractor tried many equipment configurations to work around the lines being left in place but the tight area did not allow it.  The change to relocate the lines was because the work could not be done per CDOT’s direction.  CDOT was responsible for the utility relocations and CDOT proposed moving the lines.  This was an unforeseen condition since the lines could not be dropped or deenergized.  CDOT also said that the relocation was not included in the Contractor’s schedule.  Until the layout work was done, the Contractor did not know there was a problem but did reflect the relocation in a schedule update.

CDOT said the Contractor did not give enough notice for the work in the railroad ROW.  The Special Provision says 14 days and the line relocation is not listed in the Special Provision.

CenturyLink completed its line relocation at 3:00 p.m. on April 21, 2012.  Work could not begin immediately as the caisson subcontractor had to remobilize.  Then on April 25, Xcel could not deenergize the lines due to other problems.

The 69 day delay covered under CMO #2 did not benefit the Contractor and prevented it from entering the railroad right-of-way.  In addition, in conversations with Xcel the week of February 17, 2012, Matt Brenkle reported that it was never Xcel’s intention to drop the lines at the railroad.  It was at another location that Xcel discussed dropping lines.

CDOT Rebuttal on the Overhead Utility Delay:

CDOT did discuss dropping or deenergizing the lines with the Contractor.  CDOT never directed the Contractor to leave the lines in place.  Like in Dispute #1, it was the Contractor who said they would not work until the lines were moved.

The lines were not shown to be relocated and there was no omission on the Plans.  The six Abutment 1 caissons were 20 feet from the lines and could have been drilled.  There was only one wingwall caisson where there was possible interference and the lines could have been deenergized for that caisson.  CDOT believes the caissons could have been completed with the lines in place.  CDOT confirmed with Xcel that the lines could have been deenergized.

If the Contractor felt there was a problem after its site investigation it could have brought the problem up which they did not.  In many weekly Utility Coordination meetings, the Contractor’s notes indicated leaving the lines in place or dropping them.  The Contractor never objected to the item in CDOT’s February 10, 2013 email which stated, …the lines on the south side will be dropped and placed in protective conduit run along the ground on the south side of the access within our ROW up to the RR.

CDOT’s position is that the Contractor could have begun work on June 22 as it was apparent that CenturyLink was nearing the completion of its relocation and mobilization could have been planned for.  The inability to drill on June 25 is part of another Dispute.  Also, CDOT has not seen any documentation on the recent conversation with Xcel and the Contractor has made a point throughout the Dispute to document everything.

CDOT admitted the 69 day delay did push the work.  Although CMO #2 has not been implemented, it is in the works and discussions are being held with the Contractor.

Questions by the DRB on the Overhead Utility Delay:

1.  To the Contractor:  Were the lines that the Contractor shaded in blue on Plan Sheet 		     157 shown on the Plans?

The Contractor said “yes”.

2.  To the Contractor:  Are the lines in question included in Part 1 or Part 2 of the work 		     to be performed under the Utilities Special Provision?

The Contractor could not find the lines in question listed in Part 2.  The DRB said then they must be in Part 1 on Page 160 under OTHER UTILITIES (ALL COMPANIES).

The Contractor pointed out that the lines could not be left in place because the clearance from the ground to the lines was 42 feet and the rebar cages were 46 feet.  If the lines would have been dropped, the work could have been done.   The Contractor did not know what Xcel’s requirements were but the lines were never dropped.

3.  To the Contractor:  Could the rebar cages have been spliced?

The Contractor was concerned that a mechanical splice could have affected the Cross 		     Sonic Logging and was not sure how a splice in the CSL tube could affect the CSL.

4.  To CDOT:  If the lines were dropped by the utilities, would the utilities have been 	  	     required to get the same permits that were required for the relocation?

CDOT did not know and thought the dropping would have been in the temporary 	   	     easement that they had gotten for construction from the railroad.  The new permits  	  	     were required because of the crossing location was outside of the temporary easement.

4.  To CDOT:  Could the lines have been deenergized and the work done?  Refer to Plan 	  	     Sheet 161 where the Contractor indicated the work limits.

CDOT said that dropping the lines was an Xcel idea.

5.  To the Contractor:  Based on the Contractor’s added details on Plan Sheet 161,			a.   Could the lines have been left in place and deenergized?

The Contractor said it was its risk if the lines were hit.  Also the CenturyLink 			     line was lower that Xcel’s lines.  The Contractor then referred to the pictures in 		     Exhibit 3H.

b. Would there have been a problem if the lines were dropped?

The Contractor said “no”.

c. Did Matt recall discussions at the weekly utility meetings where “shutting 			     down the lines” was discussed?

Matt only recalled CDOT discussing dropping the lines.  Dropping is a form of 			    relocation.  On other areas of the job, when the Contractor identified a utility 			    problem, then CDOT was responsible to have the utility correct the problem.  		   	    This has happened in over 150 locations.

6.  To both parties:  Who decided the location of the final relocation?

The Contractor said it could have worked with the lines dropped in their original  	 	     location.

CDOT said there were several meetings held on the relocation location and the final 	 	     location was based on giving the Contractor the room they said they needed and Xcel 	 	     wanting the lines energized for summer electrical requirements.  CDOT is arguing 	 	     with Xcel on who should bear the relocation costs.

Contractor Presentation on Schedule and Delay:

The relocation of the overhead lines delayed the Project.   Per Spec 105.11, CDOT was responsible for relocation and …work shall not commence until arrangements for the protection of the utilities have been made.  Since the delay was beyond the Contractor’s control, the delay is excusable and compensable per Spec 108.08 (c).

CDOT has focused on the delay to activities rather than the Project completion and the Critical Path.  The Contractor’s Exhibit 3M is a Critical Path analysis based on the revised Baseline Schedule and the June, July and August 2012 schedule updates.  The 50 day float for Activity A1170, Drill/Pour Shoofly Caissons, shown on the May 1 revised Baseline Schedule was wrong due to incorrect logic and was corrected in the June 19 update.  No schedule can accurately show delay from only one delay when there are also delays due to other disputes.

The Critical Path analysis, Exhibit 3M, shows there were 44 days in delays.  Taking into account the 4 days of delay awarded by the DRB for Dispute #1, if there is merit to the Contractor’s delay claim, then the Contractor maintains there is a 40 day delay due to Dispute #3.

Per Spec 108.08(c), the delay is excusable and compensable and monetary compensation for the delay should be made in accordance with Spec 109.10.  Since CDOT has requested an audit, the DRB is requested to rule on the delay days but wants the DRB to understand costs were incurred for the delay.  Per Spec 105.24(c),  All audits will be complete within 60 days of receipt of the complete package.  If the monetary compensation issue is not resolved, the Contractor requests another hearing on costs.

CDOT Presentation on Schedule and Delay:

The Contractor’s submission of the revised Baseline Schedule and updates does not comply with the Contract requirements per Spec 108.08(d) which requires the schedule to show the delay to the completion date.  The actual delay was from May 3 to June 21.  This results in a 32 work day delay and not the 37 work day delay requested by the Contractor.

The Form and Pour Abutment and Pier Cap work was performed out of sequence with Abutment 3 and the Center Pier taking 10 days and this work was completed by May 30.  Pier columns were not shown on the schedule and the work was performed May 14-16.  The 10 days of work should reduce the delay to 22 days (32 – 10).  On the December 2012 schedule update, Activity A1730, Abutment and Center Pier Cure, the work was done 10 days early and out of sequence which would then reduce the delay to 12 days.

CDOT maintains that Activity A1170 had 50 days of float so all the delay was absorbed by the float.  On the July 12 schedule update the tie to A1490 was changed which caused the float to disappear.  In Part 2 of the REA that was submitted on October 10, the Contractor only attached the schedule updates dated May 1 and July 12.

CDOT feels a more accurate analysis is to look at Activity A2460, Shift Rail Traffic to Temp Configuration.  On the July 18 schedule update, Activity A2460 showed a finish date of January 11, 2013 but the actual completion was November 28, 2012.  This is eight weeks ahead of schedule and does not include seven weeks of delay caused by the Contractor.  If the seven weeks of delayed is added to the eight weeks mentioned earlier, the Activity was complete 15 weeks ahead of the July Schedule.  This is another reason CDOT says the utility line relocation did not delay the Project.   On the May 1 Schedule, Activity A2460 showed a completion date of October 19 while the actual completion date was November 28.  This difference is less than the seven weeks of other delay caused by the Contractor.

Contractor Rebuttal on Schedule and Delay:

The May 1 Schedule shows Activity A1170 with a start date of April 26 and a finish date of May 15 and Activity A2460 with two days of negative float.  The July schedule shows A2460 with a negative 72 days of float which is based on forecasted delays of 70 days.  You have to compare actual delays in the schedule and there is no correct way to review this delay since there are other delays in the schedule.

CDOT said the work was done out of sequence as shown on the schedule.  By doing work out of sequence, the delay was shortened.  If the work would have been done per the initial baseline schedule of December 20, 2011, the delay would have been greater as A1490 showed starting after A1170. The delay per the Contractor’s Critical Path analysis is 44 Days.

The Contractor did not show the delay effect on the completion date.  The revised baseline Schedule showed a completion date of September 4, 2013 while the August 13 schedule update shows a completion date of November 20 and a negative float of 57 days.  Therefore, the schedule updates do show the delay.

CDOT  Rebuttal on Schedule and Delay:

The Contractor’s Critical Path analysis, Exhibit 3M, and their Position Paper show overall delays.  The reduction for the Dispute #1 delays from nine days to four days is not reflected in the analysis.  CDOT asked whether the Dispute #3 delay was 40 or 44 days and pointed out that the Contractor’s Position Paper said there were 34 days of delay.

CDOT said the audit is underway or soon will be.

Activity A2460,  Shift Rail Traffic to Temp Configuration, is a significant milestone.  The permanent bridge activities were resequenced and the Contractor’s projections do not show what actually happened in the field.  The June 19 schedule update shows A1490 starting after A1170 is finished.  The Contractor never tied the delay to the Project finish.  The reason CDOT looked at the May and July schedule updates is that these are the schedules the Contractor provided in their REA.

Questions by the DRB on Schedule and Delay:

1.  To the Contractor:  Was May 23, 2012 charged as a work day based on the rain?

There was no Critical Path work but CDOT charged a work day.

Summation Statement by Contractor:

There was excusable and compensable delay per Spec 108.08(c) because the delay was not caused by the Contractor.  CDOT was notified of the problem and requested the lines be relocated which meant getting the lines out of the way.  It was CDOT and Xcel’s responsibility to decide what to do.  The overhead lines were not shown to be relocated on the Plans.

The Contractor was proactive with CDOT and followed Spec 105.11.  They followed CDOT’s direction and then CDOT relocated the lines.  There was no way to know about the heat impact on power requirements and what would happen if the lines were dropped with 20 trains per day on the tracks.  CDOT caused the delay and per Spec 108.08(c) the delay is compensable.  Per FHWA requirements, CDOT had the duty to take care of utility problems.  Spec 105.11 says the Engineer is to do the utility coordination.

The Contractor did provide a schedule analysis and followed the Green Book.  The analysis shows 40 days of delay for Dispute #3.

Concerning the audit, as of 15 minutes ago, there had been no contact with the Contractor concerning the audit.  The audit should be done not later than 60 days after the receipt of the DRB Recommendation and not delayed until the Project has been complete as CDOT said was the auditor’s position.

Summation Statement by CDOT:

It is clear on the Plans that the overhead lines were not to be relocated.  Spec 105.11 states The Contractor shall consider in the bid proposal all of the permanent and temporary utility facilities in their present or relocated positions as shown in the Contract and as revealed by site investigation.

Although the Contractor notified CDOT on February 10 that the lines needed to be moved, for two months the discussions centered on dropping or working around the overhead lines.  On April 19, the Contractor decided to change its means and methods and wanted the lines moved.  Relocate means moved not dropped. This is not the procedures call out on Page 160 of the Utilities Special Provision.  The Contractor did not give reasonable time for relocation by waiting so long to change its means and methods.

The tight working conditions were known at bid time and the Contractor could have put the rebar splicing in the bid.

The Contractor changed the means and methods for the overhead line problem and thus caused the delay.  Per Spec 105.11, Utility delays due to changes which are the responsibility of the Contractor will be considered nonexcusable delays.

The lines were relocated by June 21 but the Contractor did not start work it said was on the Critical Path until June 26.  The schedule showed the delayed activity had 50 days of float.  The Contractor has not shown how the delay affected the completion date.  In its Position Paper, the Contractor asked for 34 days not 40.  CDOT maintains the delay was nonexcusable.

The hearing was adjourned to allow for monetary considerations pending the audit.  The DB will consider merit and quantum as to the number of delay days, if any, and make its Recommendation.

Note:  After the parties presented their positions on Dispute #2, there was some confusion on what comprised the 40 days that the Contractor said it was delayed in Dispute #3.  The parties were requested to review what had been discussed so far in the hearing and the hearing would then continue with each party presenting it positions on the delay days.

Contractor Additional Presentation on Schedule and Delay:

The information that the Contractor submitted in the REA was not in violation of Spec 105.08(d).  The Critical Path analysis that was provided in Exhibit 3M was not new information but was a different presentation of the analysis.  CDOT is the one who made the changes and now wants to wait until the end of the job to see if the delay affected the Project completion.  The Contractor adhered to the requirements.

If more time is needed to resolve the delay, then the hearing should be delayed.  Three disputes are interconnected.  The delay for Dispute #2 and #3 are concurrent.  The length of delay does not have impact on the Critical Path.  This was shown in Dispute #1 where the Activity impact was from July 23 to July 27, a total of four days.  The Critical Path analysis should lend support that there was delay to the Critical Path impact.

The Contractor’s schedule expert explained that the request in its Position Paper for 34 days of delay for Dispute #3 plus the six days of delay for Dispute #2 has no connection to the 40 days previously requested during the hearing for Dispute #3.  Contractor Exhibit 3M compares the May 1 schedule to the June 19 schedule showing the delay of 40 days on the Critical Path.  The July 12 schedule update shows there were two delay impacts to two activities, A1170 and A1490, resulting in a projected finish for Activity A1490 of August 28, 2012.  The six day delay for Dispute #2 is concurrent with the delay for Dispute #3.

The Contractor said it had not heard from CDOT on whether CDOT accepted the four day delay in the DRB Recommendation for Dispute #1.  There is still a total delay of 44 days and the Contractor reserved its rights to also request an additional four days for Dispute #3 if CDOT rejects the DRB Recommendation for Dispute #1.

CDOT Additional Presentation on Schedule and Delay:

Disputes #1, #2 and #3 are three distinct disputes and they were never submitted as a whole by the Contractor.  There is some overlap in the dispute delays.  The Contractor originally requested 37 days of delay for Dispute #3 and then in its pre-hearing submittal changed to 34 days of delay.  CDOT says there are 32 days of delay at the maximum.  For Dispute #2 the Contractor requested 6 days of delay.  Dispute #1 was within the time for Dispute #2 and the delay was coincidental but still distinct issues.  CDOT said that it was accepting the DRB Recommendation for Dispute #1.

The Contractor’s change to 34 days in its pre-hearing submittal was submitted before the Recommendation for Dispute #1 was received.  By changing to 40 days of delay for Dispute #3 at the hearing, the Contractor is trying to recoup some of the nine days requested in its pre-hearing submittal for Dispute #1.

The two schedules that the Contractor submitted with its REA dated October 10, 2012 were the May 1 revised Baseline Schedule and the July 17 schedule update.  If the Contractor now wants to change the delays to 40 days for Dispute #3 and zero days for Dispute #2, then CDOT needs to reopen both disputes and introduce the inefficiency of the Contractor.

The production losses in Dispute #2 are separate from the delay in Dispute #3.  The schedules that the Contractor submitted with its REA are not the schedules it is now using for its analysis to request 40 days of delay for Dispute #3.

Contractor Rebuttal on CDOT Additional Presentation on Schedule and Delay:

There were three separate issues under provisions in the Green Book and the issues were handled separately because of the causes.  In the discussions with CDOT, they were never introduced as one.  As more schedules are submitted, they should be able to be used for analysis as they are available.  The previous delay analysis was not correct but the latest Critical Path analysis used the Critical Path to show the delay for Disputes #1 and #3.

It is just coincidental that the 34 day plus 6 day delay total the same as the 40 days of delay that the Contractor is now requesting for Dispute #3.  The Contractor did not want it to seem that new information was being submitted.  They had a software problem which was corrected but everything else is the same.

CDOT said that it was also accepting the DRB Recommendation for Dispute #1.

CDOT Rebuttal on Contractor Additional Presentation on Schedule and Delay:

During discussions with the Contractor, the Contractor requested looking at the disputes one at a time.  Dispute #1 is separate but Disputes #2 and #3 are tied.

Questions by DRB on Additional Presentations on Schedule and Delay:

1.  To the Contractor:  On the Contractor’s Exhibit 3M, is it the May 1 and June 19 	  	     schedule comparison that reflect  the 40 day delay?  Why does the five day duration to 	     complete the abutment after the completion of the caissons as shown on the May 1 	  	     schedule change to 12 days duration on the June 19 schedule?  Is the error in the 50 	 	      days of float?

The Contractor answered “yes to the first question.  There was considerable discussion between the DRB and the Contractor on the last two questions with no clear outcome.

2.  To the Contractor:  Was a schedule as required by Spec 108.08(d)4 ever submitted to CDOT?  Was the requirement ever discussed in the dispute meetings with CDOT?

The Contractor’s answer to both questions was “no”.

3. To CDOT:  Did CDOT ever run its own schedule analysis?

CDOT said “no” because it was not possible to determine the delay.

There was considerable discussion between the DRB and the parties on the two questions with no clear outcome.

4.  To CDOT:  If CDOT waits until the end of the Project to determine the delay, how can the Contractor plan its work or know what completion date it needs to meet.

There was some discussion but CDOT did not answer the question.

The hearing was adjourned to allow for monetary considerations pending the audit.  The DB will consider merit and quantum as to the number of delay days, if any, and make its Recommendation.

Findings:

- Project Special Provision, Revision of Section 105.09, Order of Precedence, shows the Project Special Provisions take precedence over the Standard Specifications.  Accordingly the Project Special Provision, Utilities take precedence over Spec 105.10 Cooperation by Contractor.  The Special Provision contains the following language: The work described in these plans and specifications requires full cooperation between the Contractor and the utility owners in accordance with Subsection 105.10 (emphasis added) in coordinating their respective operations, to complete the utility work with a minimum delay to the project.

Utilities Special Provision, Part 1, contains the following language:

CONTRACTOR SHALL PERFORM THE WORK LISTED BELOW

…Provide an accurate construction schedule that includes all utility work elements to the owner of each impacted utility.  Provide each utility owner with periodic updates to the schedule.

OTHER UTILITIES (ALL COMPANIES)

Contractor shall support/protect all buried and/or overhead utilities noted on the plans or otherwise encountered on-site.  This work is expected to be coordinated with construction(emphasis added).

Although the Contractor gave notice to CDOT and Xcel in February 2012, it did not take the proactive position as required by the Utilities Special Provision.  In the case of notice to CenturyLink, the notice was not timely.  Had the Contractor taken the required proactive position,  there was more than adequate time (75 days) from February 10 to April 26, start of caisson work, to have the overhead lines relocated.  The delay for relocating the overhead lines requested in the Contractor’s pre-hearing submittal was 37 days.

Similarly, Spec 105.11 requires the Department and the Engineer to take various actions, one of which states, The Engineer will make arrangements with either the utility owner or the Contractor to accomplish necessary adjustments or relocations when not otherwise provided for in the Contract.  In the hearing it was not made known what actions, if any, CDOT took to fulfill its requirements.  Accordingly, CDOT is also responsible for the delay.

- It appears there is an error in the Utilities Special Provision.  Paragraph 1 on Page 158 refers to Subsection 105.10, Cooperation by Contractor.  It should have referred to Subsection 105.11, Cooperation with Utilities.  In the 2005 Spec Book, Cooperation with Utilities was Subsection 105.10.  In reviewing other CDOT contracts since the 2011 Spec Book went into effect, The Utilities Special Provision refers to Subsection 105.11.  (Refer to Finding 1 above.)

- Form 105 #117 dated June 19, 2013 and titled Acceptance of Schedule, states, This hereby serves as official notice that the enclosed “re-phasing” schedule is accepted.  The schedule shall now become the official project baseline schedule from the printed date of the schedule, May 1, 2012 forward.

Although the Completion date on the May 1 schedule shows a negative 2 days of float, this is the schedule that should be the basis for the delay analysis.

- Plan Sheet No. 157 shows the power lines running overhead above the wingwall caissons at the southeast corner of Abutment 1.

The presence of these lines should also have been obvious in a site inspection and was even questioned by another contractor and recorded in notes that the Contractor had access to.

- The Xcel and CenturyLink overhead lines are not on the identified utilities to be relocated in Part 2 of the Utilities Special Provision.  In addition, the Utilities Special Provision on Page 164 under XCEL ENERGY – ELECTRIC DISTRIBUTION states what is to be done if the Contractor is working near Xcel’s overhead lines.

Other than for the two notices sent to Xcel and one to CenturyLink and discussions at the weekly coordination meetings, nothing was presented in the pre-hearing submission or at the hearing that indicated the Contractor was proactive in getting any problems resolved with the utilities.

- Spec 105.11 states, Utility delays due to changes which are the responsibility of the Contractor will be considered nonexcusable delays.

After several weekly utility coordination meetings beginning March 21, the notes which were prepared by the Contractor, the Contractor consistently referred to shutting down the overhead lines.  Then in its letter to CDOT dated April 19, 2012, the Contractor stated, …these lines must be taken down in order to drill and set the proposed caissons.  Based on Spec 105.11, the change in the method to handle the overhead line problem was the Contractor’s change and the delay should be considered nonexcusable under this spec section.

However, as was stated in Finding 1 above, CDOT was also responsible for the delay and per Spec 108.08 (c), since CDOT’s actions or lack thereof were beyond the control of the Contractor, the delay should be considered excusable.  CDOT said the maximum delay would have been From May 3 to June 21 which equates to 32 work days.

- At the Contractor’s request, CDOT had the overhead lines temporarily relocated.  This relocation was for the Contractor’s convenience.  Any delay or extended duration due to the relocation is the responsibility of the Contractor as it is the result of a relocation done at the Contractor’s request for the Contractor’s convenience.

- Spec 108.08(d) defines the schedule submission requirements to be included in Part 2 of the REA.  Although the Contractor submitted schedules with it REA and provided a Critical Path analysis, Exhibit 3M, in its pre-hearing submittal, it has not provided a schedule reflecting how Dispute #3 directly delayed the Contract Completion Date.

Recommendation:

- The Contractor’s request for a 40 day delay and time extension is found to be without merit.  However, since CDOT was also responsible for the delay, the delay should be considered excusable.  Based on CDOT’s position that the maximum delay was 32 work days, THE Contractor should be granted 32 days of excusable but noncompensable delay.

- CDOT should ensure that their bid documents are correct before advertising the Project.

Respectfully submitted, this 7th day of March 2013.

W. H. Hinton II