DISPUTE REVIEW BOARD REPORTAND RECOMMENDATION

SH 7 Cherryvale Road to 75th Street

BOULDER COUNTY, CO

CDOT PROJECT NO. STA 0072-010

DISPUTE #1 CONCERNING DIFFERING SITE CONDITIONS AT BNSF RAILROAD                     					ABUTMENT 1

Hearing Date: January 31, 2013

Hearing Location:   CDOT Region 4 Office									          1050 Lee Hill Road										          Boulder, CO

Hearing Attendees:	Joe O’Dea – CEI – Vice President									Matt Brenkel – CEI – Project Manager								Derek Rowland – CEI – Assistant Project Manager							Michelle Berger – CEI - General Counsel								Keith G. Sheaffer – CDOT – Region 4 South Program Engineer					Dan Marcucci – CDOT – Resident Engineer								Chris Boespflug – CDOT Resident Engineer								Daryl Miller – CDOT/AECOM – Consultant Project Engineer					Joseph Burrows – CDOT – Assistant Project Engineer						Michael Wells – CDOT/URS – Inspector								Laura Zamora – CDOT – Area Engineer								Roselle Drahushak-Crow`- Assistant Area Engineer							Leo F. Milan, Jr. – CDOT – Attorney for State							Richard M. Wenzel III – CDOT – Observer								Stacy DeWitt – CDOT – CDOT Observer

Background:																									On November 11, 2011 Concrete Express, Inc. (CEI) (Contractor) was awarded a Contract by CDOT for $18,094,575.69 for the full reconstruction and widening, major railroad structures, MSE walls, caisson walls, drainage structures, HMA pavement, and concrete curb, gutter and sidewalk on SH 7 from Cherryvale Road to 75th Street in Boulder, CO.  A Notice to Proceed was issued on December 1, 2011.

Section 7 of the Contract incorporates the Plans, the Standard Specifications for Road and Bridge Construction dated 2011 and any Special Provisions for this Project and Revised Standard Specifications.

While drilling a 48 inch diameter caisson on Abutment 1, the Contractor encountered a concrete obstruction and gave written notice to CDOT and stopped work on the caisson work.  After numerous letters and meetings, the Contractor removed a portion of the obstruction and drilled the caisson.  Obstructions were also encountered on the two adjoining caissons.

The Contractor submitted a Request for Equitable Adjustment on September 12, 2012 which was denied by the CDOT Project Engineer on October 2, 2012 as being without merit and incomplete.  Per Spec Section 105.22(c), the Contractor elevated the dispute to the Resident Engineer on October 9, 2012 and submitted a revised REA. An addendum to the REA was submitted on October 30, 2012.  After three meetings with an alternate Resident Engineer and no agreement, the decision was made to elevate the dispute to the Dispute Review Board per Spec Section 105.22.

Joint Statement of Dispute:

During the course of drilling abutment caisson #1 at abutment 1 for the bridge structure D-16-EB, BNSF Shoofly Structure, a conflict with a chunk of concrete was discovered. Concrete Express, Inc. (CEI) believes the concrete to be a differing site condition not identified in the Contract and has requested an Extension of Contract time and Monetary compensation for the delays’ impact to the project schedule critical path, extended jobsite overhead and direct expenses associated with mitigating the conflict. CDOT believes the concrete encountered was a known drainage structure, or part thereof, identified as a Contract removal item in the plans and believes no extension of contract time or monetary compensation is warranted as it is a nonexcusable delay. The dispute has been denied on merit at both the PE and RE review levels of the dispute process per section 105.  Both parties request the DRB determine merit and quantum for the compensable delay.  (Note:  During the pre-hearing phone conference, the parties requested the DRB to consider only the number of days of delay, if any, as CDOT has requested an audit of overhead expenses.)

Pre-hearing Submittal:

In addition to the Plans and Specifications for the Project, both parties provided the DRB with Pre-hearing Submittals per Spec. Section 105.23(e) which included but were not limited to documentary evidence relevant to the issues, serial letters, e-mails, speed memos, daily logs and handwritten notes.  Both parties essentially submitted the same documents in organized three ring binders.  Both parties provided the DRB with their lists of attendees.  The Contractor also provided an addendum to its submittal to correct the schedules that had been included in its original submittal.

Contractor Presentation on the Differing Site Condition:

Caisson #6 on the opposite end of the abutment was drilled with no problems.  While drilling Caisson #1on June 27, 2012 at approximately the 16’ depth, an obstruction was encountered which was thought to be the RCP or concrete collar which was shown on the plans as further away from the caissons.  Drilling was stopped and the hole backfilled to eliminate the possibility of a cave-in from train traffic. That same day the Contractor gave written notice of the “unforeseen condition” and delay to CDOT in accordance with the Contract requirements and requested CDOT’s direction on how to proceed.  The Contractor suggested installing a pipe in the RCP and filling the pipe with flow fill before continuing drilling but had a major concern with this method due to  the possible impact to the caisson that could cause problems with the cross sonic logging that was required.  The obstruction was also encountered on Caissons #2 and 3.

The Contractor’s position was that the RCP was not shown correctly on the plans in that the obstruction was closer to the caisson than the distance scaled on the plans.  The Contractor also maintained that the CDOT Survey Manual requires the location accuracy for the RCP of 0.2 feet.  The Contractor also referred to the Spearin Doctrine concerning the implied warranty of the plans.

The Contractor said that as the “discovering party” it gave proper notice to CDOT per Spec Section 104.02(a); however, CDOT as Engineer did not investigate the condition as required by Spec Section 104.02(a).  CDOT rather responded by letter on June 29, 2012 stating the RCP was shown on the plans to be removed and therefore was not an unforeseen condition.  The Contractor maintained that CDOT’s direction to remove the pipe was unconstructible because the pipe was needed for temporary drainage, there was no temporary drainage shown in the plans, and that temporary shoring for the pipe removal, amounting to perhaps as much as $100,000, would be required to meet the railroad requirements for shoring.  Also, the sequencing of caisson drilling due to the limited work area and the equipment required did not allow the remaining caissons to be drilled.

After several meetings with CDOT, the Contractor redrilled the caisson to the obstruction, installed a casing and had a man enter the caisson who drilled a hole through the concrete.  Using different drilling equipment, the concrete was penetrated.  In discussions with CDOT staff, the staff indicated that in a previous repair to the drainage structure in which RCP was installed, that waste concrete had been used to backfill a portion of the RCP.  The concrete that caused the obstruction was the backfill concrete and not the concrete box or the RCP.

CDOT Presentation on the Differing Site Condition:

CDOT did not want to discuss the shoring issue because shoring was never used to complete the caissons.

The Contractor asked for direction and stopped work.  The Contractor also wanted CDOT to assume some or all of the risk associated with the cross sonic logging.  The obstruction was foreseeable as the pipe was shown on the plans and was called out to be removed.    The Contractor proposed on June 28 to install a PVC pipe in the RCP for drainage and then fill the pipe with flowfill to continue drilling, to which CDOT verbally agreed.  CDOT did not direct the Contractor to stop work.

CDOT discussed the scaling of the plans for the caisson clearance from the caisson and said that the Contractor’s scaling interpretation of the pipe location was not correct.  The inlet was exposed before the temporary backfill was installed and the Contractor could have inspected the pipe from the inlet.

The Contractor was not available for a meeting on July 3 and a meeting was eventually held on July 9 where CDOT said it would not assume any of the cross sonic logging risk.    The Contractor   then started talking about visual inspection and alternate drilling equipment.  Once the Contractor restarted work, it only took three hours to get by the concrete.  The Contractor never performed a visual inspection of the obstruction until July 11.

Contractor Rebuttal on the Differing Site Condition:

The Contractor disagreed with CDOT’s position that the shoring was not relevant because CDOT said the pipe should be removed which would have required substantial design and cost to meet the railroad requirements.  This is one of the considerations in the Contractor stopping work to get the issue resolved.  The Contractor did come up with a solution and CDOT said they would discuss the cross sonic logging later if there was a problem.

As for CDOT’s comment that there was no visual inspection by the Contractor until July 11, the Contractor pointed out that Spec Section 104.02(a) states, Upon written notification, the Engineer will investigate the conditions…  Due to the cross sonic logging risk, the Contractor felt it needed written direction from CDOT and stopped work per Spec Section 104.02(a).

The Contractor reiterated its position on the pipe location as shown on the plans should have allowed the caisson to be drilled without interference.  The concrete that was encountered was a differing site condition and not the pipe or box.

Before the inlet was covered with the temporary fill, a steel plate larger than the top on the inlet was installed and it did not appear that there was a problem with the inlet and pipe that would affect the caissons.  When the obstruction was penetrated, the auger brought up a large piece of unreinforced concrete which was large enough to wedge itself in the auger.

In CDOT’s pre-hearing submittal, they said that portions of the RCP were removed on January 16, 2013 which rendered the pipe useless as a drainage feature.  The Contractor said the only pipe that was removed was for the wingwall caisson.

The Contractor said the agreement in the meeting with CDOT to pay for the pipe and flowfill was only verbal and therefore was non-binding.

CDOT Rebuttal on the Differing Site Condition:

There was nothing that prevented the Contractor from performing a visual inspection to determine where the concrete came from.  It was not the RCP that was hit but rather a concrete collar around the pipe. CDOT said that if they would have known what the obstruction was, they could have solved the problem.  Additionally, CDOT had no way to send an inspector into the hole but the Contractor did.

CDOT said its June 29 letter confirmed its previous verbal position on the flowfill.  (Note: A review of the June 29 letter does not indicate CDOT approved the flowfill proposal.)

CDOT said that during the July 9 meeting, the Contractor made no mention of CDOT assuming the risk for possible cross sonic logging problems.  Jonny Karpuk of CEI prepared the meeting minutes which make no mention of the risk for cross sonic logging problems.

CDOT’s direction to the Contractor was to remove the pipe or drill through the obstruction.  The Contractor drilled through the obstruction in three hours.

On January 16, 2013 where the Contractor removed some of the pipe, the Contractor made no provision for temporary drainage.  Water built up and the area froze.  The Contractor then provided temporary drainage.

CDOT pointed out that per the Specs, the caisson location tolerance allows the caisson to be moved 3”, which the Contractor did on the following caissons.

CDOT said that the Contractor did not backfill the caisson hole when it had to stop drilling on July 11 due to the Xcel requirements on the shutdown of its power lines and came back on July 12 to finish the hole.

Questions by the DRB on the Differing Site Condition:

1.  To the Contractor:  What did you find when you drilled into the concrete obstruction 		     in Caisson #1 and what did you find on Caissons #2 and 3?

The Contractor said it did not hit the RCP or the concrete box but hit a mass of unreinforced concrete at all three caissons.

2.  To CDOT:  What did CDOT do to comply with Spec Section 104.02(a) to investigate 	  	     the condition?

CDOT said it did not investigate the condition but did witness the inspection made by the Contractor on July 11.  CDOT did agree with the Contractor that there appeared to be a 12 foot long lens of concrete that ran adjacent to the three caissons.  When the Contractor drilled the hole into the concrete and pipe, water did enter the caisson hole.

CDOT said it did not have the capability to enter the hole and inspect but that the Contractor had the confined space procedures and equipment to do so.  CDOT felt that if they directed the Contractor to enter the hole, they would have gotten “push back” from the Contractor.

Contractor Presentation on Schedule and Delay:

The Contractor said the differing site condition caused an Excusable Delay because it was beyond the Contractor’s control. The delay was also Compensable Delay for which they were entitled to a time extension and monetary compensation per Spec Sections 108.08 (c) and 109.10.  The compensation includes direct costs and overhead costs, including the additional railroad flagging that was required.  Several letters were sent to CDOT regarding these matters.  There are also other delays around this time which are the subject of other disputes.  At a meeting with CDOT on October 19, CDOT said there was some merit on the pipe and flowfill that was installed but there was not a differing site condition.

The Contractor gave proper written notice on June 27and stopped work per Spec Section 104.02(a).  No direction was received from CDOT until June 29 and what CDOT directed was unconstructible.

The Contractor then went through the schedule dated June 19, 2012, prior to the delay, and the Schedule dated August 13, 2012, after the delay.  Based on the CDOT Time Count Sheets, the Contractor said it was delayed 9 work days.  Schedule Activities A1170, Drill/Pour Shoofly Caissons and A1030, Punch Walk, were used to show the delay to the Project. The delay shown in Activity A1030 from November 5 to November 20 = 15 days also reflects delays from other disputes.

The Contractor said it was aware that CDOT wanted to have an audit but they had not received an audit notice.  The Contractor said the DRB could still recommend on the number of days of delay.

CDOT Presentation on Schedule and Delay:

CDOT said that based on there being no Differing Site Condition and the timeline that was provided, the delay was nonexcusable.

The Contractor’s letter of June 27, which was not received by CDOT until June 28, was responded to in CDOT’s letter of June 29.  CDOT said formal notice of a Differing Site Condition was given by the Contractor in its letter of July 2.  On July 3 CDOT offered to meet that day but all of the Contractor’s personnel were not available so the meeting had to be scheduled for July 9.

Ultimately, the Contractor proceeded with the drilling of the caisson using the methods proposed by the Contractor on June 27.  Therefore the delay was in the Contractor’s control.  The Contractor did not attempt to mitigate the delay by drilling other caissons and stated, A contractor worried about schedule would have worked. When Caisson #1 was redrilled, it only took three hours and the Contractor never discussed the concrete problem on Caissons #2 and 3.

CDOT said that there might be concurrent delay based on other disputes so that it would be difficult to make a delay determination at this time.

Contractor Rebuttal on Schedule and Delay:

The Contractor said the total delays on the Project Schedule are confusing since there are 37 days of time that have been agreed to with CDOT but that have not yet been added to the Project time.  There is also the delay due to the dispute concerning a change in the character of the work due to work hour restrictions by Xcel.  The Contractor’s plan was to drill the caissons at all three locations continuously and not split the operation for different locations.

The Contractor said that in addition to the limited work area for drilling the other caissons, the Specs required leaving two caisson diameters between holes.

The Contractor said that there is no concurrent delay in the nine days it requested for the Differing Site Condition.

CDOT  Rebuttal on Schedule and Delay:

CDOT said that the Contractor taking only three hours to get through the obstruction is relevant based on the Contractor’s requested nine workday/sixteen calendar day time extension.  CDOT said if the Contractor would have been more proactive, there would have been minimum delay.

The Contractor did not submit Part 2 of the REA with the original submittal.  This led to confusion and the submittal of a revised REA.

During the Project Engineer and Resident Engineer reviews, there was some merit considered for the installation of the PVC pipe and flowfill.

CDOT still felt that work could have been done on the other caissons.

Questions by the DRB on Schedule and Delay:

1.  To the Contractor:  Schedule Activity A1170, Drill/Pour Shoofly Caissons, shows a 	     	     successor Activity of A1490, Form and Pour Abutment & Center Pier Caps.  The 	    	     Schedule dated June 19, prior to the delay, shows Activity A1490 estimated to 	 	  	     complete on July 23.   The Schedule dated August 13, after the delay, shows Activity 		     A1490 actually complete on July 27.   This indicates a delay of only four days.  	 	     Should this four day delay account for all prior delay on the bridge?

The Contractor could not answer the question as the Project Manager at the hearing was not the person who built the schedule.

Summation Statement by Contractor:

In analyzing a Critical Path Schedule, you have to look at the impact on the end of the schedule.  The Contractor suggested tabling the delay/schedule issue until the delays in other disputes can be reviewed.  CDOT objected to the tabling and said this dispute should stand alone and the DRB should make its recommendation based on the hearing today.  (Note:  The DRB reviewed the tabling issue and determined it would consider the delay, if any, in its deliberations in making the Recommendation.)

The Contractor said that a good contractor would have done what the Contract calls for, which is exactly what it did.  The shoring required to remove the pipe before drilling the caissons would have cast in excess of $100,000.  The other option offered by CDOT at the beginning, drilling through the obstruction, raised concerns on possible impacts on the cross sonic logging. CDOT did not do any of investigation that it was required to do.  The Contractor did do the investigation later when it was asked to.

CDOT understood that drainage needed to be maintained in various areas and showed temporary drainage installations in the Plans where there was no permanent drainage.  If the culvert/pipe was removed to eliminate the obstruction, major shoring would have been required for the existing railroad abutment to meet railroad requirements.

The obstruction that was hit on Caissons # 1, 2 and 3 was unreinforced concrete that the Contractor did not know was there and was not the concrete box or RCP.  The Contractor did not get clear direction but rather direction to do something that could not be done.

When considering delay in the schedule, the entire Critical Path and the effect on the end of the job must be reviewed.  The abutment wingwalls were also impacted by the delay and not just the abutment cap.

The Contractor did not continue on the other caissons because the protruding rebar from a completed caisson further limited the work area in an already tight area.  The spacing requirement between drilling caissons further limited the work area.  To have worked on the other caissons was like painting your way into a corner.

Summation Statement by CDOT:

You must look at the definition of a Differing Site Condition.  What the Contractor did was not continue to drill.  The Contractor has confined space procedures for inspection which CDOT does not have.  The Contractor did not follow CDOT’s direction but stopped work on the caissons.  CDOT did not direct the Contractor to accelerate and never changed its direction to the Contractor.  CDOT never assumed the risk for possible cross sonic logging problems.

The Contractor came up with the inspection method and how to remove the obstruction which only took three hours.  Temporary drainage could have been installed elsewhere in the area.  The PVC pipe and flowfill fix was a Contractor proposal.  If there was a problem on Caissons #2 and 3, CDOT never received notice.  There is no merit to the Differing Site Condition claim.  Therefore, the delay is the Contractor’s responsibility.

In reviewing the Critical Path in the schedule, you should look at the activity for removing the old railroad bridge.  The post delay schedule shows a start of January 23, 2013 but the work started in December 2012.  Therefore there was no impact.  The nine day delay the Contractor referred to was caused by letter writing and delayed meetings.  If the Contractor would have been proactive, there would not have been a dispute.

Discussion:

CDOT was asked by the Contractor when the audit would be scheduled.  CDOT’s reply was that CDOT Audit did not want to perform an audit until the Project was complete and all costs could be audited.

Accordingly, the hearing was recessed pending the audit.  The DRB will make its Recommendation on merit and delay days, if any.  If the parties cannot agree on a settlement after the audit, the issue will be referred to the DRB.

Findings:

- The Contractor encountered a concrete mass that was not the concrete box or RCP that was shown on the plans.  The unreinforced concrete mass constituted a Differing Site Condition.

- The Contractor complied with the Contract requirements and gave proper written notice.  It also followed up with the required submittals, including an REA.

- CDOT did not perform an inspection of the Differing Site Condition as is required by Spec Section 104.02(a).

- The Critical Path schedule shows the successor of activity A1170, Drill/Pour Shoofly Caissons, as activity  A1490, Form and Pour Abutment & Pier Caps.  The schedule dated June 19,2012, prior to the delay, shows an estimated completion date for activity A1490 of July 23.  The schedule dated August 13,2012, after the delay, shows an actual completion date for activity A1490 of July 27.  This would indicate an excusably delay beyond the Contractor’s control of four (4) days on the Critical Path.

Recommendation:

- The unreinforced concrete encountered in drilling the caissons is a Differing Site Condition as defined in Spec Section 104.02(a) and the Contractor should be compensated for the costs for investigating and removing the obstruction per Spec Section 109.04.

- The delay requested by the Contractor for the Differing Site Condition is an excusable delay per Spec Section 108.08(c) and  is also a compensable delay.  The Contract time should be extended by four (4) work days and the Contractor should be compensated per Spec Section 109.10.

Respectfully submitted, this 15th day of February 2013.

W. H. Hinton II