DISPUTE REVIEW BOARD REPORTAND RECOMMENDATION

SH 7 Cherryvale Road to 75th Street

BOULDER COUNTY, CO

CDOT PROJECT NO. STA 0072-010

DISPUTE #4 CONCERNING REMOVAL AND REPLACEMENT OF ASPHALT 		  			     PAVING AT CHERRYVALE ROAD

Hearing Date:  April 24, 2014

Hearing Location:   CDOT Region 4 Office									          1050 Lee Hill Road										          Boulder, CO

Hearing Attendees:	Joe O’Dea - CEI - CEO					      	          Matt Brenkle - CEI - Project Manager				  Theran Olsen - Brannan - Division Manager				   Grant Cruseturner - Brannan - PM of Public Projects	                   Jon Joesten - Brannan - Quality Control Manager		            William Caires - Brannan –President, Cesare, Inc.			    Robin Stoneman - CDOT - Acting Region 4 South Program Engineer   Dan Marcucci - CDOT - Resident Engineer				     Rick Chapman - CDOT -  Region 4 Materials			     Gary DeWitt - CDOT - Region 4 Materials Engineer		    Steve Gonser - CDOT -  Region 4 Lab Manager			   Daryl Miller - CDOT/AECOM - Consultant Project Engineer	   Joseph Burrows - CDOT - Assistant Project Engineer		   Laura Zamora - CDOT - Area Engineer				      Leo F. Milan, Jr. - CDOT - Attorney for State	                        Richard M. Wenzel III - CDOT - Observer				    Stacy DeWitt - CDOT - CDOT Observer

Background																								         On November 11, 2011 Concrete Express, Inc. (CEI) (Contractor) was awarded a Contract by CDOT for $18,094,575.69 for the full reconstruction and widening, major railroad structures, MSE walls, caisson walls, drainage structures, HMA pavement, and concrete curb, gutter and sidewalk on SH 7 from Cherryvale Road to 75th Street in Boulder, CO.  A Notice to Proceed was issued on December 1, 2011.  Brannan Sand and Gravel (Subcontractor) performed the Hot Mix Asphalt (HMA) paving work.

Section 7 of the Contract incorporates the Plans, the Standard Specifications for Road and Bridge Construction dated 2011 and any Special Provisions for this Project and Revised Standard Special Provisions.

On August 11, 2012, the Subcontractor placed the lower two lifts of HMA at the intersection of SH 7 and Cherryvale Road.  Tests on the HMA showed the VMA was more than 2V out of tolerance which required the removal and replacement of the HMA.  On September 11, 2012, CDOT issued Speed Memo #161directing the removal and replacement of the HMA.  After several meetings and additional testing, the Subcontractor removed and replaced the HMA on August 3 and 4, 2013.

The Subcontractor submitted a letter on May 30, 2013 which disputed the direction to remove and replace the HMA.  On June 26, 2013, the CDOT Project Engineer determined there was no merit to the Subcontractor’s dispute. Per Spec Section 105.22(c), the Contractor/Subcontractor elevated the dispute to the Resident Engineer on June 27, 2013.  On July 8, 2013, CDOT issued Speed Memo #226 again directing the removal and replacement of the HMA.

After numerous discussions, the Subcontractor submitted a Request for Equitable Adjustment (REA) on December 3, 2013.  Additional information was submitted by the Subcontractor on January 23, 2014.  Since the parties were unable to resolve the dispute, on February 18, 2014 the Resident Engineer requested a hearing by the Standing DRB.

Joint Statement of Dispute

CEI, on behalf of Brannan Sand and Gravel, and CDOT have come to an impasse on the dispute regarding the HMA placed on Cherryvale. CDOT believes that the asphalt placed by Brannan Sand and Gravel on August 11, 2012 at Cherryvale Road and portions of mainline SH7 failed to meet contract specifications. VMA value was more than 2V out of tolerance limits requiring removal and replacement at the Contractor's expense per revised standard specification 105.05 (9th Paragraph). Brannan contends that had the specifications and guidance in CDOT’s Field Materials Manual been followed the targets designated in the Form 43 would have been revised and the material would have been allowed to remain in place. Parties ask the DRB to determine merit and quantum of this dispute.

Pre-hearing Submittal

In addition to the Plans and Specifications for the Project, both parties provided the DRB with Pre-hearing Submittals per Spec. Section 105.23(e) which included but were not limited to documentary evidence relevant to the issues, serial letters, e-mails, speed memos, daily logs and handwritten notes.  Both parties essentially submitted the same documents in organized binders.  Both parties provided the DRB with their lists of attendees.

Subcontractor Presentation on HMA Removal and Replacement

The Subcontractor said the dispute centers around its mix design of March 2012, which was based on the materials it had stockpiled, and the subsequent Form 43 (Job Mix Formula) that was prepared by CDOT.  The job consisted of several in and out phases for paving to allow traffic switches until the final paving was done.  The Contractor had worked out a change to the Contract with CDOT which allowed the intersection to be closed for two weeks rather than perform the work in phases which kept some lanes open at all times.  In 2012, the Subcontractor stockpiled 330,000 tons of aggregate from Frei’s pit.  They try to monitor the HMA since they know the aggregate material can vary.

The Subcontractor was told to coordinate all items relating to paving through Mike Wells, the CDOT/URS inspector at the job site.  Before the August 11, 2012 paving, the Subcontractor had noted some possible mix problems and had spoken to Wells.  On August 9, 2012, they sent emails to Wells/CDOT to document the variations per its QC responsibilities.  This should have prompted due diligence on the part of CDOT as QA.  They were also concerned in getting the paving done to meet the two week closure of the intersection.  On August 13, the Subcontractor requested the aggregate belt cut sample that had been pulled by CDOT on August 11, 2012 be tested.  There was no response from CDOT.   On August 23, 2012, a meeting was held with CDOT to discuss the problem and the testing was again requested.  CDOT also refused to release a portion of the split sample so that the Subcontractor could have the aggregate tested.

The Subcontractor then explained the development of the mix design and how they depended on the densities of the aggregate materials.  The mix is then submitted to CDOT who then issues the Form 43 which show the allowable band width of the target values for various aspects of the HMA testing.  CDOT Procedure 56-09 - Guidelines for Using Maximum Specific Gravity (Rice) of Project Produced HMA to Change the Target Specific Gravity for Compaction Compliance, outlines how to handle  mix changes when the specific gravity changes.  Section 1.1 states, During the production of HMA, changes may occur in the maximum specific gravity of the mix.  This change may be detected, and target specific gravity corrected by measuring the maximum specific gravity of the project-produced material.  Note 2 then covers how the aggregate testing is to be done.

In the case of the HMA on August 11, the coarse aggregate got heavier.  When the weight goes up, the density goes up.  The Subcontractor said it initiated the CP 56 procedure by its email of August 9, 2012 when it brought up problems from the August 6 and 7 tests and requested the Rice value from CDOT’s Central Lab.  The calculations CDOT made on the August 11 HMA were not correct since CDOT did not use the correct specific gravity.  The material was out for VMA but the material was good.

At the meeting on August 23, 2012, CDOT proposed two durability tests – French Rut and Hamburg.  The Rut Test is a method for testing HMA but is not in the Colorado tests.  CDOT bumped the asphalt/cement (AC) up 0.2% on the Form 43 from the AC % in the mix that was submitted.  The Subcontractor questioned the richer mix with more AC and what this might do to the two alternate tests run by CDOT.  The Subcontractor insisted that the best way to review the problem was to test the belt cut sample which CDOT would not do in 2012.  Finally, after the HMA had been removed and replaced in August 2013, CDOT released the belt cut sample which the Subcontractor had tested by WesTest on August 9, 2013.  The test showed the ¾” aggregate got heavier and the fines matched earlier test results.  Accordingly, the test run on August 11, 2012 used the wrong specific gravity and the formula should have been rerun with the correct specific gravity.  The WesTest report said that using the correct specific gravity would lead to a VMA of 11.7 which would not be out more than 2V.

Bill Caires explained how the VMA considers the space around the rock plus air voids.  When the specific gravity of the coarse aggregate goes up, the surface area of the rock goes down resulting in the asphalt having less surface to coat.  The Rice test shows the change.

The Subcontractor said that since the ¾” got more dense, the target needed to be adjusted.  They do this every day on countless jobs.  Heavy traffic drove on the HMA for a year and the HMA held up fine and the top mat still had to be placed.  The Subcontractor did their due diligence and some engineering judgment is needed.  They did their investigation of the problem but CDOT did not.  The investigation was to find out why there was a problem.  Their investigation showed there was a specific gravity aggregate problem and the Form 43 should have been revised and the HMA would have been OK and could have remained in place.  They feel their August 9, 2012 email gave CDOT notice. The intent of CP 56 is to take care of fluctuations.  The paving done before August 11, 2012 and the resulting tests raised the concern on a possible problem.

The Subcontractor handed out Pages 41 and 42 from NCHRP Report 478 – Relationship of Superpave Gyratory Compaction Properties to HMA Rutting Behavior.  The complete report was provided to the DRB.  CDOT did not object to the report being provided at the hearing.

CDOT Presentation on HMA Removal and Replacement

The Subcontractor placed two mats of HMA totaling 4½” on August 11, 2012 at the Cherryvale intersection.  The Contractor had proposed the total closure of the intersection which was not per the original Contract requirements but was approved by CDOT.  The tests of the HMA showed a VMA of 10.9 which was more than 2V out of target range of 12.4–14.8 for VMA. Spec 105.05 covers the variation issues and when the HMA must be removed and replaced.

CDOT paid for the August 11, 2012 HMA but not the replacement HMA.  At the meeting on August 23, 2012, where the Subcontractor said that a higher specific gravity equaled better HMA, CDOT gave informal direction to remove and replace the HMA because it was not in spec.  The Subcontractor also said that their aggregate supplier was now blending the aggregate to meet specific gravities closer to design.  This blending was after the fact and the lab tests of the in place HMA confirmed remove and replace.  Also at the meeting, CDOT agreed to do two tests, French Rut and Hamburg Wheel Tracker, and if both tests passed, the HMA could remain in place with a cost reduction.  The two tests were run in late August 2012 with the French Rut Test passing and the Hamburg Wheel Tracker failing. CDOT Speed Memo #161 dated September 11, 2012 directed the removal and replacement of the HMA.

On August 14, 2012, the Contractor put the Subcontractor on notice and threatened termination.  On October 12, 2012, the Subcontractor submitted its Quality Control Improvements which stated, We will provide the quality product you deserve from here on out.

Exhibit 4 of CDOT’s Pre-hearing Submittal lists all the tests CDOT performed beginning with Check Teasing on April 2, 2012 and Production Testing on April 9, 2012.  CP 56 allows the contractor or CDOT to initiate testing.  CDOT did not.  If the Subcontractor wanted the testing, it should have initiated the request.  The Subcontractor did not initiate the request at the August 23, 2012 meeting.  The Subcontractor claims it made the request in its August 9, 2012 email which Mike Wells responded to.  It was ambiguous and there is nothing in the email referencing CP 56.

Per Spec 106, process control is mandatory and the Subcontractor failed.  The NCHRP       Report 478 information that the Subcontractor handed out is good background but is not a Contract document.

CDOT said the belt cut sample that was taken was used for moisture testing.  The Subcontractor mix design on Form 429 shows the aggregates.  With the belt cut, CDOT doesn’t know the aggregate mix.  RAP adds to the aggregate on the belt.  CDOT can’t get the exact aggregate used on August 11, 2012.

The Subcontractor said the HMA was not terrible but it was out of spec.  If CDOT allows the HMA to remain in place, CDOT has to live with it since there is no warranty.  If the lower two mats fail, CDOT has to fix all the HMA.  The two additional tests CDOT performed were to test the longevity of the HMA but one test failed and CDOT had no confidence in leaving the HMA in place.  Regardless of the Subcontractor’s reference to getting the intersection open, the HMA must meet the specs.

Contractor/Subcontractor Rebuttal

The Contractor said the closure agreement reached with CDOT for the Cherryvale intersection was based on not being able to maintain two lanes of traffic with all the drainage and utility work that had to be done. One-way traffic would have been required for 5 to 6 weeks.  Total closure caused less inconvenience for the public.

The Contractor said its August 14, 2012 email to the Subcontractor was contractual based to go forward and get issues addressed.  The Contractor did not agree with CDOT’s position on being a threat.

The Subcontractor said that its October 12, 2012 Quality Control Improvements letter was due to a “Condition Red” and what it was doing to address Quality Control.  Had the target for the HMA been changed, there would not have been a “Condition Red”.

Concerning CDOT’s comment that the Subcontractor’s August 9, 2012 email was ambiguous, a lot of people who are in the room are HMA experts and they were addressed on the email.  The Subcontractor’s intention was to get the CDOT Central Lab involved but that never happened.  CDOT did all the testing and it was agreed by both parties that the Central Lab would be the Third Party Lab.  The CDOT field people were inexperienced.  Although CP 56 was not referenced in the email, notice was given and it was given to key CDOT people.  CDOT never followed up.

The belt cut was taken by CDOT on August 11, 2012 and it represented what went into the mix that day.  The RAP would not put the VMA out the +2V.  The belt cut sample would have shown the worst case even with RAP.  No new mix design was needed, only the correct specific gravity for the coarse aggregate on Form 43 which would have increased the VMA.  The rock and fines make up 38% of the mix.  If the aggregate specific gravity was out 3.6% and the correction was made, the VMA would have been 11.6 and in the pay adjustment target area.

With three HMA test samples being out of spec, notice was given to the proper CDOT people that there was a Rice Value problem.  In production, specific gravity tests take two days.  That is why they used the Rice Value to notice the proper people at CDOT.

After the fact testing can be done which can measure samples back to production days or hours.  An in-place sample could have been taken and the materials extracted to perform tests.  There was the same asphalt to coat less material.  That is why the email notice was important.

In several meetings, CDOT was asked for testing of the belt cut sample which would comply with the Contract where the two additional tests CDOT performed do not.  Although CDOT said the belt cut sample was taken to measure moisture, it could have been used to test the aggregate.  The HMA was not perfect but it was in tolerance using the correct specific gravity.  CDOT acted in an arbitrary manner.  The CDOT Central Lab could have gotten involved as the Subcontractor requested but did not.

CDOT Rebuttal

The Subcontractor chose to use Frei as its aggregate supplier and knew the aggregate was variable as the Subcontractor stated in its Position Paper.

The Contract called for the road to be open during construction and detours could have been used to keep the road open.  The intersection closure was the Contractor’s proposal but CDOT did not agree to lower the standards to get the road open.

CP 56 addresses how values can be changed.  At the August 23, 2012 meeting, the Subcontractor did not want to change Form 43 and said they would meet the spec with better Quality Control.  The Subcontractor’s QC man was not familiar with the process since CP 56 is a requirement for a new Form 43.  The August 9, 2012 email was ambiguous.  It’s not what CDOT didn’t do but rather what the Subcontractor said in the email.

CDOT did not have to offer the two additional tests but did so with the requirement that both tests pass.  One of the tests failed badly.

The design mix aggregate sample was separated for testing.  There is no way to recreate the aggregate used on August 11, 20121 since there was RAP in the aggregate.  Also, the mix design cannot be changed after the fact for in-place material.  Using CP 56 requires a new Form 43 but the form is not retroactive.  The Subcontractor’s email of August 9, 2012 only requested the Central Lab’s involvement on the Rice Value.  The Subcontractor is being speculative.  The Form 43 said what the Subcontractor should produce but they could not do it.

Gary DeWitt said that when he walked the intersection, there were areas where some aggregate looked like it had less asphalt coating than other areas.  Note 1 on CP 56 covers how a change in specific gravity is to be treated on the Form 43 but it is for going forward and not retroactive.

The tests on August 6 and 7, 2012 indicate that the aggregate gradation was failing.  The HMA was also failing which was a sign of production problems.  CDOT thinks the problem was more than a ¾” aggregate problem.  The failing HMA showed signs of production problems.  If CP 56 had been followed and the aggregate had been in spec, there would not be a hearing today.

Additional Subcontractor Rebuttal

The Subcontractor said they don’t have material problems with Frei and do one million tons a year so this is not a big job.  They would like data from CDOT on Frei problems.  Frei is as consistent as other sources.  Frei has recently spent $50 million on improvements so CDOT should not have a stigma about Frei from the past.  They were in an out of the job several times over its duration and some material could change over time.  This is why the specs allow changes.

The Subcontractor said they had just today signed a revised Form 43 for the paving done last September on the Project.

Questions by the DRB

1.  To Both:  What were the test results on paving prior to August 11, 2012?

CDOT referred to Section 4 of their Pre-hearing Submittal.  The first HMA paving was done on April 9, 2012 and the paving on August 11 was the 4th mob.  Of the five tests taken before August 11, all tests had results outside the expected range for the measured %AC.

2.  To Subcontractor:  If the HMA material was good, why did the additional tests performed by CDOT fail?

The Hamburg test material was not from the paving the Subcontractor placed.  If the results were inconclusive, why didn’t CDOT go the belt cut sample?  CDOT did not understand the problem.

CDOT explained the Hamburg test was performed in water and is a good test for aggregate bond.

3.  To Both:  Explain the CP 56 sequence when it is requested and what results.

The Subcontractor said a new mix design and Form 429 would be submitted along with new aggregate samples.  If the new mix was OK, new targets would be agreed to and a new Form 43 would be issued.  New specific gravity test results from the CDOT lab take two weeks.  Their concern was the opening of the intersection.

CDOT said that the two week test time is what the spec says but the Subcontractor knows it is often two or three days.

4.  To Both:  What modifications to the mix were done later in the Project?

The Subcontractor said in October 2012, a new mix using different specific gravities for the aggregate was done.  The mix did not change the component ratios.

CDOT said adjustments were made in 2013 to mix design.

5.  To CDOT:  Why didn’t CDOT give some of the belt sample to the Subcontractor earlier than August 2013?

CDOT holds the samples for future tests if required.  CDOT gave the sample to the Subcontractor after the Subcontractor requested it on May 20, 2013.

The Subcontractor said the sample was requested at the August 23, 2012 meeting.

6.  To Subcontractor:  Explain how exceeding the upper target limits is better.

There is more surface area for the AC to grab.

Subcontractor Presentation on Quantum for HMA Removal and Replacement

The Subcontractor’s costs for the removal and replacement of the HMA were included in the REA dated December 2, 2013 and were shown in the Summary Table totaling $101,832 that was included in the Pre-hearing Submittal.  The Subcontractor handed out a package which contained the Summary Table and the cost details from its accounting records.  The material is broken down in a Force Account format. (CDOT said it would have to review the information before they could comment.)

The Subcontractor said CDOT had submitted an adjustment based on unit prices.  The Subcontractor had also suggested to CDOT a settlement based on paying for the two mats that were removed as Detour Pavement.

CDOT Presentation on Quantum for HMA Removal and Replacement

CDOT provided a handout of the removal and replacement costs based on Contract Unit Prices which totaled $68,637.76.  The Detour Unit Price included planning and removal from the job.

Discussion

The Subcontractor said the CDOT Unit Price approach made sense but the Milling Unit Price was for 2” of asphalt rather than the 4½” that had to be removed.  The HMA Unit Price was for all HMA on the project and small areas like the intersection are more expensive.

CDOT replied it was the same work either way.

NOTE:

Since both parties made comments on the cost sheets that were distributed at the hearing, both parties were directed to review the content of the material, not the dollars, and let the DRB know by May 1, 2014 of any concerns.

CDOT provided the following comments on April 28, 2014.

1. For Removal of Asphalt Brannan has milling charges of $21,202.04. CDOT requests clarification on the Alpha Milling detail. There are numerous charges and credits for identical items. Milling dates also refer to milling on 8/2 and 8/3. The Cherryvale R&R was completed on 8/3 and 8/4. Why are 8/2 charges included here? CDOT's estimated cost for this item was $6,265.50 based on bid prices. CDOT recognizes the milling was likely bid at 2 inches and approximately 4 inches were removed. In the event that merit is found for Brannan, CDOT would propose the bid price be doubled for milling (or double the area) to account for this with a revised total of $12,531.

2. Brannan includes $5,843.75 for hauling removed asphalt off the project. Hauling of 		material is included in the bid price of Removal of Asphalt Mat (Planing) and therefore 	should not be paid separately.

3. The values for Brannan's Paving items (Labor & equip, Haul, Material) very nearly 	match CDOT's estimated total for the bid item of HMA (Gr S) which is a complete in 	place price.

4. CDOT has no issue with Brannan's proposed flagging charges as they are lower than 	CDOT's estimate.

5. For the "BC Cherryvale 9/3-9/4" line item, CDOT requests additional info. There is no 	justification or even a description of what this line item represents while it represents 	nearly 20% of the request.

The Subcontractor provided the following comments on April 30, 2014.

Based on CDOT’s response, we have made the following revisions.  Since CDOT has agreed to the paving cost, we will agree to their assessment of the “Removal of Asphalt Mat (Planing)” using the proration of the contract price.  The pavement that was removed was 4.5” and not the 4” that CDOT stated so we would ask that the calculation be based on that.   Also, we revised our amount in the “BC Cherryvale” line to reflect the supporting documents that CEI provided to us justifying their back-charge.  Upon further review of those documents, we removed a few of the items that were intermingled in the backcharge assessed to us.  These items were indirectly but not a direct cost, so in fairness, we have removed them.

| Description of Work | Quantity | Unit | Unit Price | Total Amount |
| --- | --- | --- | --- | --- |
| Removal of Asphalt (Planing) 1 | 9398.25 | SY | $ 1.50 | $ 14,097.38 |
| Paving Labor and Equipment 2 | 1 | LS | $ 11,256.94 | $ 11,256.94 |
| Paving Haul 2 | 1 | LS | $ 6,999.85 | $ 6,999.85 |
| Paving Material 2 | 1 | LS | $ 34,800.28 | $ 34,800.28 |
| CEI Backcharge Cherryvale 8/3-8/4 3 | 1 | LS | $ 18,885.95 | $ 18,885.95 |
|  |  |  | TOTAL: | $86,040.40 |
| NOTES: |  |  |  |  |
| 1 - Actual removal depth was 4.5". Quantity prorated to reflect the thicker section of removal. (4.5" vs 2" contract depth) |  |  |  |  |
| 2 - Cost of the placement, haul, and material of the HMA Gr S |  |  |  |  |
| 3 - CEI backcharge to BSG for additionally cost incurred not compensated by CDOT for pavement markings, traffic control, lights plants, supervision. CEI's supporting documents attached. |  |  |  |  |

CDOT provided additional comments on May 1, 2014 and the Contractor on May 6, 2012.

Subcontractor Summary

The aggregate properties changed which is expected and it is common in the industry to see fluctuations.  They have QC to control the process.  There were conversations with CDOT prior to the August 11, 2012 paving concerning problems and they approached it considering CDOT a partner.  Why wasn’t the belt cut sample used in place of the two additional tests that CDOT ran?  It took CDOT a year to provide the belt cut sample for testing by an independent lab.  By the time CDOT provided the sample, they had already removed and replaced the HMA as the time was running out.

Small quantities had been placed prior to August 11, 2012.  There was commercial use of function for a year.  Failure would have shown before a year.  Their point is more about process than dollars.  They try to work out problems, especially when there are a lot of gray areas.  They have a concern on the precedence this dispute will have because it will eliminate contractors paving in good faith while testing is being completed and the work stopped for new tests because CDOT test results take time.

Past problems with Frei have been minimal.  They try to work with CDOT on the resolution of problems.

CDOT Summary

The HMA that was placed on August 11, 2012 was out of spec.  The contractor is responsible for QC. The Subcontractor should have known there was a change in specific gravity and reacted to the change.

The VMA was more than 2V out and CDOT questioned the reliability of the HMA.  There are no warranties on CDOT projects.  CDOT cannot find a request from the Subcontractor for cores nor a rejection by CDOT.  Until CDOT accepts the project, it is under the control of the Contractor.

The Subcontractor’s August 9, 2012 email is ambiguous and there is no reference to CP 56.  By saying CDOT people got the email, the Subcontractor is trying to “pass the buck” and the Subcontractor was responsible for QC.  CDOT was responsible for QA.  The Subcontractor’s October 12, 2012 Quality Control Improvements letter shows there were a lot of problems to improve.  It was system problems that caused the August 11, 2012 problem.

The Subcontractor’s reference to commercial use for a year has no basis since one month after the HMA was placed CDOT directed the HMA to be removed and replaced.

CDOT is aware that there can be changes in materials and that is why there are target ranges.  There is no way to prove that a higher aggregate specific gravity results in better HMA.  The material was out of spec.  If spec material would have been placed on August 11, 2012, we would not be here today.

Findings

1.  In their Position Paper, the Subcontractor discusses how the aggregate properties change over time and that such changes are not unexpected.  From the time the HMA mix design was submitted in March 2012 to August 2012 when the paving was done, the Subcontractor had received 312,137 tons of aggregate from the Frei quarry.  Based on these statements, it would be appropriate that Quality Control would address the changing properties of the aggregate and what the effects the changing properties could have on the HMA.

2.  A review of the CDOT tests on early HMA placements shows the following for the Maximum Specific Gravity which was 2.491 +/- 0.01 at a %AC of 4.80 +/- 0.3.  In addition, there were failures in aggregate gradation, void content, and VMA.

| Acceptance/ Verification Sample | Date | Maximum Specific Gravity | % AC Content | Comment |
| --- | --- | --- | --- | --- |
| 1 | 4/9/12 | 2.491 | 5.15 | Outside the range for the measured % AC |
| 2 | 6/11/12 | 2.525 | 4.98 | Outside the range for the measured % AC |
| 3 | 6/13/12 | 2.513 | 5.02 | Outside the range for the measured % AC / Condition RED |
| 4 | 6/13/12 | 2.522 | 5.01 | Outside the range for the measured % AC |
| 5 | 8/7/12 | 2.542 | 4.96 | Outside the range for the measured % AC |

Based on their knowledge of changing aggregate properties and the above results, it appears that the Subcontractor should have sent CDOT notices long before the email of August 9, 2012.

3.  CP 56-09 states:

1.1 During the production of Hot Mix Asphalt, changes may occur in the maximum 		      specific gravity of the mix. This change may be detected, and target specific gravity 	   	      corrected, by measuring the maximum specific gravity (CP 51) of the project-	 	  	      produced material.

5.2 The tests for maximum specific gravity should be performed as early during 	 	 	      production as possible. The best time to start is during the compaction test section.

NOTE 2: If the maximum specific gravity is adjusted, it is possible that the aggregate 	specific gravity has changed. The Contractor or the Engineer (emphasis added) may 	request that the individual aggregates be re-sampled and retested to determine a new 	aggregate specific gravity (AASHTO T 84 & T 85). The re-sampled individual aggregates 	will be split and the Contractor will keep one split for testing while the other split will

be immediately given to the Engineer (emphasis added) for possible testing. The new 	aggregate specific gravity will be entered on the new Form #43 and a new VMA target 	will be calculated. If the new VMA target does not meet the minimum requirements

specified in the Revision of 403, work shall be suspended and the Contractor shall 	complete and submit a new mix design meeting all of the requirements at no additional 	cost to the Department.

6.3 The new target maximum specific gravity shall be reported on the Form #43. The 		     Form #43 shall be dated when the contractor is notified of the new target. The Form 	  	    #43 shall be signed by all of the involved parties.

CP 56 is clear on what should be done when changes are being observed in the maximum specific gravity of the mix being produced.  The Subcontractor could have made the request citing CP 56.  The Subcontractor’s email of August 9, 2012 does not reference and makes no mention of maximum specific gravity or CP 56.  Although the Subcontractor references Rice Values, CP 56 makes no mention of Rice Value.4.    The test results for the HMA for June 13, 2012 show a Condition RED for Asphalt Content (MQL 41) and Air Voids (MQL 62).  The MQL for VMA was 69.  There was nothing presented at the hearing or in the Pre-hearing submittals, other than the Condition RED noted in CDOT’s Tab 4, Page 3, that shows the procedures shown in Spec 106.05(g)3 were followed.  This spec places responsibilities on both the contractor and CDOT.  The spec states: Production will remain suspended until the source of the problem is identified and corrected.

The Subcontractor’s Quality Control Plan also calls out increased test frequency for Condition RED.

With the earlier test problems and the Condition RED, it seems that neither the Subcontractor nor CDOT were proactive in pursuing a resolution when there were obvious problems.

5.  There does not appear to be a good or substantiated reason why CDOT refused to provide the Subcontractor with a split of the belt cut sample from August 11, 2012 or have the CDOT Central Lab test the aggregate.  This would have been a better indicator of the mix properties problem and could have led to a much earlier basis to review the VMA results.

6.  Spec 106.05(a) states:

Process Control Testing.  The Contractor shall be responsible for process control testing       on all elements listed in Table 106-1. …The Contractor shall develop a quality control plan (QCP)…

The Subcontractor’s Quality Control Plan states:

Quality Control testing is performed throughout the crushing process (emphasis added) utilizing CP-L 5120 (?). … Testing is done for…the effective specific gravity of each sample.

-Mix evaluation will be immediately followed up by corrective action if deemed necessary.

Had the Subcontractor followed its QCP, it appears the change in the specific gravity of the aggregate would have been known to the Subcontractor and appropriate changes made to the mix design or its components.

Recommendations

1.   The Subcontractor’s request for full compensation for the removal and replacement of the HMA placed on August 11, 2012 is without merit and is therefore denied.

2.   In the future, CDOT should not unreasonably withhold material samples that could assist in resolving a dispute.  When testing continues to indicate problems, CDOT should become more proactive with more attention paid to procedures involving CP 56, the instructions on Form 43 and the inclusion of the CDOT Central Lab in the investigation and resolution of the problem while it is occurring.

Respectfully submitted, this 15th day of May 2013.

W. H. Hinton II