## 7.22 COC
CONSTRUCTION OVERSIGHT CHECKLIST for LOCAL AGENCY PROJECTS
Project Code |  |  |  |  | Local Agency: | Standard Specification for Road and Bridge: YR
Project # /Project Name - |  |  |  |  | Location: | CDOT Field Materials Manual: YR
| NTP Date: |  |  |  | Local Agency Project Manager: | Final Acceptance Date:
| Substantial Completion Date (If Applicable) : |  |  |  | Prime Contractor: | On/Off System:
| Landscape Maintenance Period End Date: |  |  |  | Testing Firm: | Funding Source:
IGA Expiration Date from IGA or Option Letter - (Project must be closed prior to this date) |  |  |  | OJT: | CM: | Working or Calendar:
FHWA Construction End Date (If applicable) from IGA, Exh C - (Items on this checklist must be completed by this date) |  |  |  | DBE: |  | BA / BABA Yes or No: | If highlighted in green = Not required on state funded projects.
Project file folder # | Local Agency Construction Documentation |  | Date Received / Reviewed by CDOT Staff | When to submit to CDOT LA Coordinator | Reference | Comments
1 | ADMINISTRATIVE
1.01 | Distribute Award Plans and Specifications | X |  | Upon Award | LA Manual #7.1.10 (Federal funded); #7.2.10 (State funded) 1 set of electronically sealed Plans, 11 "X 17", Contract Documents & Construction Specs (sealed as well; Cover page through Table of Contents), Bridge Design Manual page 11 | 1 set of electronically signed and sealed plans (11"X17"), Contract Documents & Construction Specs OR as allowed by the CDOT Region. For Bridge Projects, plans in both PDF and native file format. Specifications in PDF and Microsoft Word. All PDFs shall be 300 dpi, page aligned, text searchable, compressed and in conformance with ISO PDF/A-1b archival specification.
1.02 | Materials Testing Schedule - Form 250 | CDOT | PROVIDED BY CDOT | At Award | LA to Review 250 | Provided by CDOT
1.03 | Independent Assurance Testing Schedule - Form 379 | CDOT | PROVIDED BY CDOT | At Award | LA to Review 379 | Provided by CDOT
1.04 | Notice to Proceed to the Contractor | X |  | When Produced |  | LA to send to LA Coordinator when NTP is issued
1.05 | Pre Meeting Date | X |  | Previous to PreCon Precon following conference | LA Roles and responsibilities. Ref. CDOT FMM CP16 use Form 1322 | Local Agency, Consultant Testing Firm Staff. (Project Support Staff) This meeting does not include the Contractor.
| Pre-Construction Meeting and Minutes | X |  | PreCon | LA Manual #8.3.1 Preconstruction Conference...https://www.codot.gov/business/designsupport/bulletins_manuals/construction-manual | Complete copy of agenda and minutes should go out to each attendee for review… Possible attendees if in CDOT Right of Way- Maintenance - Traffic Operations - Resident Engineer - Environmental - Region Civil Rights - Inspector - Staff Bridge
1.06 | Safety Management Plan |  |  | PreCon | Prior to safety critical work | Standard Specification 107.06 and or Project Special Provisions
1.07 | Emergency Notification Information | X |  | PreCon | Template in LA filing system | Phone list of Project Personnel contact information. If on State system LA Coordinator will distribute to applicable internal CDOT staff.
1.08 | Baseline (CPM) Schedule | X |  | Before Construction Starts/PreCon | LA Manual, #8.5.6 Submit Project Schedule and Conduct Progress Meetings, #8.3.1 Preconstruction Conference, item 11. Standard Specification 108.03. | Schedule is required at least 10 working days prior to start of work. Must be accepted by LA PE in writing prior to any work beginning.
| Monthly Updates with each Pay App | X |  | Monthly | LA Manual, #8.5.6 Submit Project Schedule and Conduct Progress Meetings | Monthly schedule updates must be provided by Contractor before payments are made. See 108.03 for additional documents. LA PM has 10 days to review and comment and may withhold payment for lack of schedule update.
1.09 | Project Engineer and Inspector Certifications | X |  | PreCon | LA Manual #8.5, Const. Manual Section 101.103.7 | Must comply for project work inside CDOT ROW. Make copy of certifications. (PE License of person in responsible charge and Inspector certifications)
1.1 | Certificate of Insurance (CDOT Named as additional insured) | X |  | PreCon | LA Manual #8.3.1.12, Standard Specifications R&B Section 107.15 | Contractor Insurance Company to provide, CDOT is included in list of additionally insured. LA PE to check expiration date and maintain current certifications. Ref. IGA
1.11 | Weekly Time Count Reports - Form 262 or 263 | X |  | Weekly NTP- Final Acceptance | LA Manual #8.5.5, Const. Manual 108.8.5 and 120.6.1, Appendix B 39 - B 46 | Verify Copies are in LA Project File. Keep Files Up to date from NTP through Final Acceptance | NTP through Final Acceptance
1.12 | Project Safety Management Plan w/ written acceptance | X |  | PreCon | LA Manual #8.2, Standard Specification 107.06 | Safety Plan is required to be project specific and accepted in writing by the Project Engineer.
| Safety Critical Plans and Conference | X |  | Prior to safety critical work | Standard Specification 107.06 and or Project Special Provisions | The Contractor shall submit the detailed construction plan two weeks prior to the safety critical element conference described below.The Contractor shall stamp and sign the construction plan “Approved for Construction”. The Engineer will review the construction plan for acceptance. CDOT review of this information shall not relieve the Contractor of liability. The Contractor shall hold a Safety Critical Element Conference two weeks prior to beginning construction on each safety critical element. The Engineer, the Contractor, the safety critical element subcontractors, and the Contractor’s Engineer shall attend the conference. The Contractor shall perform safety critical work only when the Engineer, or an authorized representative, is on the project site.
1.13 | Copy of Prime Contractor Contract | X |  | PreCon | 23 CFR 633.102 (d) - https://www.ecfr.gov/current/title-23/chapter-I/subchapter-G/part-633/subpart-A/section-633.102; IGA | The contract between the Local Agency and the Prime is needed per Federal Law. CDOT staff must verify that their contract contains FHWA Form 1273 as an attachment. | Not required on State Funded or Federal Recovery Fund projects. However, recommended as IGA can require statements in Contract between LA, Contractor and Subcontractors.
1.14 | Placeholder
1.15 | Mid Project Review (CRLC & Materials) | X | COMPLETED BY CDOT | First half of project | Audit Report 19-003 | CDOT LA Coordinator confirms LA is keeping project documentation correctly and files status copy of Construction Oversight Checklist in PW.
1.16 | Local Agency Public Info |  |  | Required for On-System Projects | Standard Spec 626- Tier I; II; III & IV requirements | When applicable, LA to coordinate and maintain PI. Stakeholder list, LCR; Call Logs; Copy CDOT PIM on releases
2 | Civil Right & Labor Compliance
2.01 | LCPtracker & B2GNow Information & Forms | X |  | Precon | CRBRC webpage>System Forms>Construction - https://www.codot.gov/business/civilrights/la-compliance/overview | LCPtracker is not required on State Funded or Federal Recovery Fund projects. Use of B2GNow is required on all construction projects. | Use of LCPtracker is only required if Davis Bacon applies to the project. It is not required on State Funded or Federal Recovery Fund projects. Use of B2GNow is required on all construction projects.
2.02 | Sublet Permit Application - Form 205E | X | B2G | Prior to Sub being on Project | LA Manual #8.3.1.2, , 2018 Constr Manual 107.1.3.2 See flowcharts LA-B-8.0 Approve Subletting & Accept Suppliers, and LA-B-9.0 Monitor Prompt Payment | One approved Form 205e for each subcontractor. Form must be submitted and approved by LA PE before subcontractor may go to work. Note: Embedded in B2GNow, no paper form req'd.Contractor completes and submits in B2GNow. LA reviews/approves or denies. RCRO reviews/approves/denies.
| Form 1425 | X | B2G | Submit with 205 | LA Manual #8.3.1.3. See flowcharts LA-B-8.0 Approve Subletting & Accept Suppliers, and LA-B-9.0 Monitor Prompt Payment | Required to identify contractors that contribute materials to the total of $10,000 or more. Participating DBE suppliers can count towards the Contract goal. A Form 1425 should be collected with every Form 205 when applicable- $10K+. Note: Embedded in B2GNow, Contractor completes and submits in B2GNow. LA recommends approval or denial. RCRO reviews/approves/denies. Not retained in PW.
2.03 | EEO Bulletin Board (Pictures) | X |  | Verify Monthly | https://www.codot.gov/business/civilrights/compliance/construction/bulletin-board-postings | Verify Bulletin Board is posted and accessible to Project Employees. Submit picture of postings every calendar year. Posters vary depending on funding. See RCRO.
2.04 | OJT Commitment - Form 1337 | X | LCPTracker | PreCon | LA Manual #10.5. See Standard Special - OJT Requirements. See flowchart LA-B-7.0 Monitor OJT Participation | Summarizes the classifications that will be utilized on the project for training. The commitment form acknowledges the Prime's understanding of their goal. Submit with the Contractor's approved training program. Note: Contractor completes and provides to LA who forwards to LAC and RCRO. RCRO uploads form into LCPtracker. | Not required on State Funded or Federal Recovery Fund projects.
2.05 | OJT Trainee - Form 838 | X | LCPTracker | Prior to Trainee on site | LA Manual #10.5. See Standard Special - OJT Requirements, Subsection 5. See flowchart LA-B-7.0 Monitor OJT Participation | Submitted for each trainee that will be training on the project. Submit along with their enrollment certificate. The Form 838 must be approved by CDOT prior to trainee hours counting toward the project OJT goal. Note: Contractor completes and provides to LA who forwards to LAC/RCRO. RCRO uploads form into LCPtracker. | Not required on State Funded or Federal Recovery Fund projects.
2.06 | Monthly OJT Trainee Status - Form 832 | X | LCPTracker Attach to 266 | Monthly | LA Manual #10.5. See Standard Special - OJT Requirements, Subsection 5 and 7. See flowchart LA-B-7.0 Monitor OJT Participation | Trainee hours worked on the project. Submitted monthly & verified against payrolls. Only Classifications approved on Form 838 are applicable toward the trainees OJT Goal. Note: Contractor completes and submits monthly to LA who reviews/approves/certifies and forwards to LAC/RCRO. RCRO uploads into LCPtracker. | Not required on State Funded or Federal Recovery Fund projects.
2.07 | Annual EEO Report - FHWA Form 1391 | X |  | Annually Due in August by Contractor | LA Manual #10.7 | Annual EEO Report is only required for Federal-Aid construction. Submit for projects that had active construction during the month of July. LA forwards request for information to all contractors. Contractors submit info to CRBRC or via LCPtracker (automatically done) when payrolls are up to date. Not retained in PW. | Not required on State Funded or Federal Recovery Fund projects.
2.08 | Contractor's EEO Policy | X |  | PreCon | LA Manual #8.3.1.5 | Submit a copy of the Contractor's EEO Policy.
2.09 | Project EEO Meeting Minutes and Attendance Roster | X |  | As new subcontractors are added | LA Manual #8.3.1.9 | Submit a copy of the meeting agenda and roster of attendance. Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less than once every 6 months.
2.1 | Prime Contractor Supervisory EEO Meeting Minutes and Attendance Roster | X |  | PreCon | LA Manual #8.3.1.8 | Submit a copy of the meeting agenda and roster of attendance. Periodic meetings of supervisory and personnel office employees will be conducted before the start of work and then not less than once every 6 months.
2.11 | EEO Interviews (Number Required ) - Form 280 | X | Secure Access in LCPTracker | Monthly | 2024 Construction Manual Section 107.1.5.2 See flowcharts LA-B-6.0 Labor interviews, LA-B-4.0 Accept Weekly Payrolls, and LA-B-4A Prime Payroll Approval | Interview completion is based on contract amount. LA required to do a minimum of 4 interviews/month of active construction. All OJT trainees must be interviewed. EEO section must be completed on all projects. Only complete Labor Compliance section when D-B wages are req'd.
2.12 | Contractor Payroll Submittals | X | LCPTracker | Weekly | LA Manual #10.1.1, Contract Documents Project Special Provisions, Required Contract Provisions (Instructions & PR 1273) See flowchart LA-B-4.0 Accept Weekly Payrolls | Payroll audits must be checked and completed weekly. Payrolls are done weekly for each week a contractor is active. Identify "no work" periods. All deductions must be explained. The Contractor approved subcontractor payrolls weekly, then the LA reviews/accepts weekly. | Note: If the project has force account work you will need payrolls - only for the force account work. Otherwise certified payrolls not required on state funded or Federal Recovery Fund projects.
| Request for Authorization of Additional Classification and Rate - DOL SF 1444 | X | LCPTracker | Submit to CDOT Coordinator | LA Manual #10.5 See flowchart LA-B-5-9 Wage Conformance Request | Form is to request a wage for a classification that is not listed in Davis Bacon Wage Decision, found in project specs. Contractor submits form to LA who forwards to LAC/RCRO. Plan accordingly - could take up to two (2) months. | Note: If the project has force account work you will need payrolls - only for the force account work. Otherwise certified payrolls not required on state funded or Federal Recovery Fund projects.
2.13 | Contractor DBE Payment Certification | X | B2G | Monthly | LA Manual #8.19.1, #10.1.4 LA Manual # 6.4, #8.10, #10.1.5 | Maintain monthly audits in B2G | Note: If the project has force account work you will need payrolls - only for the force account work. Otherwise certified payrolls not required on state funded or Federal Recovery Fund projects.
| DBE Plan Modification - 1420 package | X | B2G | As Needed |  | Reference project DBE Specification. This is a process, not just a form.
2.14 | Prompt Payment | X | B2G | Monthly | LA Manual # 6.4, #8.10, #10.1.5 | Prompt Payment verification and any withholdings of payment should be submitted monthly. Contractors report payment. LA conducts monthly auditing. (7 calendar days after receiving payment for that work)
2.15 | Contractor's Affirmative Action Plan | X |  | PreCon | https://www.dol.gov/ofccp/regs/compliance/aaps/aaps.htm | 41 CFR 60-4
2.16 | Commercially Useful Function - Form 1432 | X | B2G | Required For All participating DBE's | LA Manual #10.4. See Standard Special - DBE Requirements, Subsection 8. See flowchart LA-B-10.0 Validate DBE Counting | Required form for projects with a DBE contractor listed on Form 1417. Contractor complete sec 1 when DBE begins work. DBE completes sec 2 w/in 10 days. Contractor completes sec 3 w/in 10 days of receipt of DBE info. LA completes sec 4 and forwards to LAC/RCRO. RCRO files in B2GNow. | Not required on State Funded or Federal Recovery Fund projects.
2.17 | LA EEO Certification Acceptance Letter | X |  | End of Project | LA Manual #11.5, Appendix F-4 | Template in LA filing system and completed by LA Project Engineer
2.18 | ADA Ramps - PROWAG Compliant. | X |  | Prior to Payment | M&S Standard M608-1 https://www.codot.gov/business/civilrights/ada/resources-engineers | Coordinate measurement with CDOT. https://www.codot.gov/business/civilrights/ada/resources-engineers
3 | MATERIALS
3 | Form 1322 Required for all projects | X |  | Precon | Prestesting Meeting Agenda | Download agenda from CDOT Forms Catalog. https://www.codot.gov/about/forms
3.01 | Create & Maintain Materials Book | X |  | Ongoing | Field Materials Manual Documentation - CDOT Local Agency, Section 5, 6 | LA to set up Materials Books at beginning of project. LA must turn in documentation for CDOT review. An electronic version is preferred. Required electronic books.
3.02 | Concrete Mix Designs - Form 1188 and Follow CP 62 | X |  | Before Use | LA Manual #8.3.1.13, #9.8 Field Materials Manual CP 62 | LA to follow CP-62 for On-System projects or LA equivalent for Off-System projects. Submit to CDOT Project Manager for approval.
| Asphalt Mix Formula - Form 429 and Follow CP 52 | X |  | Before Use | LA Manual page #8.3.1.13, #9.8 Field Materials Manual CP 52 | LA to follow CP-62 for On-System projects or LA equivalent for Off-System projects. Submit to CDOT Project Manager for approval.
3.03 | Concrete Truck Mixer Inspection / On-Demand Truck Certification | X |  | PreCon | Noted on PreCon Agenda, LA Manual Appendix B. Construction Manual, Appendix B. 601.07(c) of Standard Specifications. | Form 46 required for mixer trucks. Volumetric certification required for on-demand trucks.
3.04 | Finals Materials Documentation Review and Audit Checklist - Form 1199 | X |  | End of Project | Field Materials Manual, Documentation Tab | LA completes page 1 and CDOT completes page 2. LA project personnel are to review 100% of the items and materials documents. CDOT checks on p.2 top 4 major items and if errors, reviews 100% of items.
| Project Final Quantity Estimate | X |  | End of Project | Required by the Form 1199 | Last estimate before retainage is released
| Random Sample Schedule | X |  | PreCon | Per CP75 and Required by the Form 1199 | Generated by LA Owner Acceptance Tester/Testing Firm
| Price Reduction Calculations | X |  | Each Occurrence | Required CDOT Standard Specifications. | Reductions are record on Form 626 & Form 266 and codified on a CMO for the respective pay period. Cost reductions are calculated by CDOT.
| QC/QA Data for paving items | X |  | Monthly | As Applicable for Large Paving Projects That include incentive disincentive | Per specifications, Contractor is required to complete QC testing book for asphalt and concrete paving materials. FMM 106.01
| CP 16, Evaluation of Materials Testing - Form 1324 | X |  | End of Project | Required by the Form 1199 | LA PE fills out for consultant tester on project.
3.05 | Monthly Buy America Certifications & Summaries | X |  | Monthly | Field Materials Manual, Special Notice to Contractors Tab and Standard Specification 106.11 https://www.codot.gov/business/designsupport/materials-and-geotechnical/buy-america-requirements-and-documentation | BA Monthly COCs and Summaries are due each month from NTP to Final Acceptance; including months the contractor is not on-site. See example in CDOT FMM Special Notice to Contractors
| Monthly Build America - Buy America Documentation (BABA) | X |  | Monthly | https://www.codot.gov/business/designsupport/buy-america-requirements | BABA Monthly Certifications are recorded on a Form 1600 and due each month from NTP to Final Acceptance. The Form 1610 is required for projects that are exempt from BABA. Reference the CDOT Field Materials Manual Special Notice to Contractors and CDOT Standard Spec 106.11. | Monthly NTP through Final Acceptance
3.06 | Certification for testing lab and testers (on file) | X |  | PreCon | ACI Certs, Soils Materials Certs, PCI Certs, CP 10 by CDOT or AASHTO Accredited Lab. | LA needs to verify with coordinator they have this on file
3.07 | Completed Materials Testing Schedule - Form 250 | X |  | End of Project | Field Materials Manual, Documentation for Maintenance and LA | Checked, signed, and stamped by Local Agency Professional Engineer. All Tests and COC's shall be referenced on 250.
| Rebar Pull Test | X |  | Prior to Payment | FMM OA Schedule 602 | Tested by independent lab (not CDOT) - One per source. Prior to incorporation into the project.
3.08 | Completed Independent Assurance Test Schedule w/supporting documentation - Form 379 | X |  | End of Project | Field Materials Manual, Documentation for Maintenance and LA Tab | Completed by LA *Note - If on On-system, then contact the CDOT Local Agency Coordinator for clarification. Make sure the project materials lab is inspected in accordance with CP 10 and recorded on the form. The company performing Independent Assurance Testing (IAT) shall not be the same company performing the Owner Assurance Testing (OA).
3.09 | Materials Certification Letter from LA - Form 473-LA | X |  | End of Project | Field Materials Manual, Documentation for Maintenance and LA Tab | Signed by Local Agency Project Engineer and Local Agency Resident Engineer.
3.1 | Explanation of Exceptions - Form 474 | X |  | End of Project | Field Materials Manual, Documentation for Maintenance and LA Tab | Explanation of all Exceptions with supporting documentation that addresses any exceptions or deviations.
3.11 | Ensure COC's & CTR's are assembled with their respective items in the Materials Book | X |  | Monthly | Field Materials Manual, Documentation for Maintenance and LA Tab. See Standard Spec. 106.12 & 106.13 Ref CDOT FMM OA Schedule | Submitted by Prime, reviewed and accepted project
3.12 | Review Small Quantities | X |  | Minimum Two Weeks prior to Placement | Identify small quantities a minimum of two weeks in advance of need. | Small quantity testing reductions must be submitted to and approved by CDOT. Guidance can be found at the end of the CDOT FMM OA Testing Frequency Tab.
4 | PAY QUANTITY DOCUMENTATION
4.01 | Pay Quantity Documentation - Form 266's; Form 7 & Form 10's for F/A Work | X |  | Monthly Corresponding w/ Pay Apps | LA Manual #8.5.1 Construction Inspection and Documentation Responsibilities and #8.5.3 Force Account Work, Const Manual Sec 100 | The LA shall submit written documentation to support all contractor payments. Each item shall have documentation showing item #, description, project #, date, location, method of measurement, quantity paid, signature of inspector.
4.02 | Daily Diaries Form 103 kept and signed | X |  | Monthly Corresponding with Pay Apps | LA Manual #8.5.4 Maintain Diaries, Const. Manual Section 100 | Verify LA is keeping Daily Diaries in Project Files and that they are signed. The diaries should be available on demand by the LAC.
4.03 | Scale Certifications / Weigher Certification / Scale Check | X |  | PreCon | Standard Specifications R&B Section 109.01 | Verify Scale Check done for more than 2500 tons of material and in Local Agency Project File.
4.04 | Tickets for Items paid by the ton | X |  | Monthly | Construction Manual 121.2.1 | Verify tickets were collected at time of material delivery
4.05 | Monthly Request for Reimbursement | X |  | Monthly | Per the IGA, Reimbursement requests shall not be delayed more than 60 days after the costs have been incurred | LA to submit monthly Request for Reimbursement for project. Proof of payment shall be project specific.
4.06 | Change Orders / CMOs and supporting documentation - Form 90 | X |  | Prior to CMO work | LA Manual #8.12 and #8.13, Construction Manual Section 120.7 | CDOT MUST approve all change orders BEFORE work begins otherwise might be subject to non-reimbursement. LA MAY NOT tap MCR Budget WITHOUT CDOT Approval.
5 | ENVIRONMENTAL DOCUMENTS (EROSION CONTROL, etc.)
5.01 | CDPS Permit | X |  | Precon | Refer to current Water Quality Control specification | Erosion Control Inspection Form Completed by LA. Check with Environmental unit to see if Consent Order specifications apply.
5.02 | 404 Permit | X |  | Precon
5.03 | Dewatering Permit | X |  | Precon
5.04 | Specialty Inspections, if Required | X |  | As Needed | Refer to the project SWMP and CDOT Region Environmental Specialty Unit | Include necessary inspections for wildlife (birds, fish, rodents, etc.) and waterways, ditches, wetlands, etc.
5.05 | Hazardous Assessment Site Plan (HASP) and Materials Management Plan (MMP) | X |  | As Needed | As required by the contract documents | Shall be submitted to the CDOT Project Manager for approval at the preconstruction meeting.
5.06 | Inspection & Storm Event Reports | X |  | Monthly | Per Stormwater Discharge Permit
6 | TRAFFIC CONTROL
6.01 | Signed Contractor's Method of Handling Traffic - One for Each Traffic Situation | X |  | PreCon | LA Manual #8.3.1.10, Standard Specifications R&B Section 630.09 | Approved by LA - Submit to Region Traffic Unit for review if on CDOT Right of Way (ROW)
6.02 | Traffic Control Manager's Daily Report | X |  | Daily | LA Manual #8.7. Standard Specifications 630.11 & Construction Manual 630.2.3 | Verify LA is collecting the TCS Diaries. Nighttime inspections: LA PE should make at least one nighttime inspection upon implementation of a new MHT. TCS shall inspect once per week that includes nighttime traffic control devices per the Construction Manual.
6.03 | Weekly & Night Inspection | X |  | Weekly | LA Manual #8.7. Standard Specifications 630.11 & Construction Manual 630.2.4 | LA to collect and review TCS diaries. Nighttime inspections: LA PE should make at least one nighttime inspection upon implementation of a new Method of Handling Traffic that includes nighttime traffic control devices per the Construction manual.
6.04 | Copies of ATSSA and Flagging cards | X |  | PreCon |  | Submit with Pre-construction paperwork. New staff=New Cards
6.05 | Speed Reduction - Form 568 | X |  | As needed | Applies to ON System Projects | Use nuegov.com Form needs to be completed and submitted to CDOT Project Manager on CDOT ROW. CDOT Project Manager will submit for approval
6.06 | Wide Load Restriction (Letter to project staff) | X |  | As needed | Applies to ON System Projects | Headquarters permits approves. Requests need to be made to the CDOT Project Manager as soon as possible. Minimum 5 day notice. All the required information must be included.
6.07 | Traffic Control Review | X | COMPLETED BY CDOT | Minimum Once Per Project | LA Manual #8.7 | Complete Traffic Control Review Form with LA PE.
6.08 | Situation, Background, Assessment, Recommendations (SBAR) | X |  | As Needed | Completed LA Project Staff | Required when working outside the contract Lane Closure Strategy hours for On System Projects
7 | STRUCTURES
(Includes work on bridges or culverts with a span (or diameter) >=4', tunnel, walls over 4' high, traffic signal structure and/or overhead sign structure.)
7.01 | List of Structural Items to be built on the project | X |  | PreCon by LA | Complete attachment found in the welcome email | From Project Development staff, initial list of structures that are going to be built/installed on the project. From Prime Contractor, approximate dates of install.
7.02 | Furnish project documentation to Staff Bridge on ongoing basis during project | X |  | Weekly throughout project | Bridge Design Manual page 10, E.4 Form 1333 are required for caissons | All projects that include work on bridges or culverts with a span (or diameter)>=4', tunnel, walls over 4' high, traffic signal structure and /or overhead sign structure. See Bridge Design Manual (Policies & Procedures, P3: Staff Bridge Managed Structural Assets) for definitions. All PDFs shall be 300dpi, page aligned, text searchable, compressed and in conformance with ISO PDF/A-1b archival specification.
7.03 | Fabrication Inspectors performing OA/QA | X |  | PreCon | LA Responsible for Fabrication Inspection | LA Coordinator forwards contact info to Staff Bridge. See Bridge Design Manual
7.04 | Notifications | X |  | Ongoing | LA Manual #8.5 | Notify LA Coordinator of date for fabrication of structural items. LA Coordinator to notify Staff Bridge. Notify of date for demolition of structures and for erection of girders.
7.05 | Drawing, Shop, Working & Other Drawing | X |  | Prior to Install | Ref. the CDOT Bridge Design Manual
7.06 | Safety Critical Plans and Conference | X |  | Prior to safety critical work | Standard Specification 107.06 and or Project Special Provisions | The Contractor shall submit the detailed construction plan two weeks prior to the safety critical element conference described below.The Contractor shall stamp and sign the construction plan “Approved for Construction”. The Engineer will review the construction plan for acceptance. CDOT review of this information shall not relieve the Contractor of liability. The Contractor shall hold a Safety Critical Element Conference two weeks prior to beginning construction on each safety critical element. The Engineer, the Contractor, the safety critical element subcontractors, and the Contractor’s Engineer shall attend the conference. The Contractor shall perform safety critical work only when the Engineer, or an authorized representative, is on the project site.
8 | FINALS DOCUMENTATION
8.01 | Local Agency Final Data Form | X |  | End of Project | https://www.codot.gov/business/localagency/manual/resources | Completed by LA
8.02 | Final Walk through of Project with CDOT - Form 1212 LA | X |  | End of Project | LA Manual #11.1, #11.1.1, #11.10 | CDOT/LA joint inspection schedule 2 - 3 weeks prior to completion. Hard Copy generated by LA Coordinator and signed by RE.
8.03 | Form 96 or equivalent | X |  | End of Project | LA Manual #11.2 | Completed by LA Example see page B-70 of LA Manual. This includes all Acceptance Letter. Initial; Partial; Substantial Completion & Final Acceptance. Needs to match total $ amount in B2G. | DO NOT ACCEPT PROJECT UNTIL DOCUEMNATION IS COMPLETED FOR SECTIONS 2.0/3.0
8.04 | As Constructed Plans | X |  | End of Project | LA Manual #11.4 Construction Manual Section 100 (121.2.3); Bridge Design Manual page 11, #4. | 1 set of electronically signed and sealed plans (11"X17"), Contract Documents & Construction Specs OR as allowed by the CDOT Region. CADD files preferred within CDOT ROW or on NHS. For Bridge Projects, plans in both PDF and native file format. Specifications in PDF and Microsoft Word format. All PDFs shall be 300dpi, page aligned, text searchable, compressed and in conformance with ISO PDF/A-1b archival specification. | Note: Some regions are collecting as constructed information for on-system ADA ramps or those required by CDOT permit (via Survey 123 or by form). That information should be stored in this folder.
8.05 | EEO Certificate of Compliance from CDOT Region Civil Rights Officer | CDOT | COMPLETED BY CDOT | End of Project |  | CDOT provides after EEO review of project.
8.06 | Final bill with closure letter | X |  | End of Project | LA Manual #8.14, #11.11 | Needs to match total $ amount in B2G.
8.07 | Advertise for Final Settlement | X |  | End of Project | LA Manual #11.3 | Completed by LA PE immediately after acceptance
The project has been completed in reasonably close conformity with plans and specifications including authorized changes. The Entity accepts the project as complete.
Signature of the Entity Official/Title______________________________________________________ Date______________________
Version 2025-09-02