## Precon Agenda Assembly
INSTRUCTIONAL NOTES: (PLEASE READ THROUGH)
Edit text only on this worksheet ("Precon Agenda Assembly")!. Please read through the entire worksheet carefully and add information wherever there are blanks or empty cells. The other sheets are linked to this one and will reflect your edits with the exception of the "Proj Emergcy Notifications List" sheet has some additional information highlighted in red that you may want to add. Column A contains the option "YES" or "NO" as to their relevency to your project (some only have "YES" because they should always be included). When you select "NO" the formatting automatically changes to a red background so that the rows are easily identifiable. Then you can select the entire rows by "left" clicking on the row number and then "right" clicking on the row number and select "Hide" so that it will not be included in your printed agenda. Your selections on the "Precon Agenda Assembly" worksheet will be reflected on the other worksheets - so you can duplicate the process above to Hide the rows you do not want printed on each of these sheets. Also, note that the "Submittals" and "Contacts" are included in the Precon Agenda under the relative category to hopefully make the meeting "flow" more easily. However, seperate spreadsheets with just a Submittal List and just the Contacts are automatically created so that you do not have to "wade" through the entire agenda to find the information or if you want to print them seperately. An effort was made to make the printout paginate properly in PORTRAIT ORIENTATION, but you should check this once you have completed your edits - you may need to remove some page breaks under the "Page Layout" tab to make the worksheets print properly.
SIGN-IN SHEET
Include in this Project? | Name |  | Title |  | Organization |  | Phone Number | E-Mail Address
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
SIGN-IN SHEET
YES | Name |  | Title |  | Organization |  | Phone Number | E-Mail Address
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES
YES | I. PROJECT INFORMATION
YES | Local Agency:
YES | Project Number: |  |  |  |  | Project SA#:
YES | Hwy Location: |  | SH |  | MP: |  |  | to MP:
YES | Project Location:
YES | Description:
YES
YES
YES | Estimated Start Date: |  | JAN | 1 | Estimated End Date: |  |  | JAN | 1
YES
YES | I. INTRODUCTORY STATEMENT
YES | <TYPE IN INTRODUCTION AND WELCOME MESSAGE>
YES | II. EMERGENCY PHONE NUMBERS
YES | PHYSICIAN NAME: | [5 empty] | PHONE:
YES | PHYSICIAN NAME: | [5 empty] | PHONE:
YES | HOSPITAL: | [5 empty] | PHONE:
YES | HOSPITAL: | [5 empty] | PHONE:
YES | AMBULANCE: | [5 empty] | PHONE:
YES | AMBULANCE: | [5 empty] | PHONE:
YES | FIRE DEPT.: | [5 empty] | PHONE:
YES | FIRE DEPT.: | [5 empty] | PHONE:
YES | POLICE: | [5 empty] | PHONE:
YES | POLICE: | [5 empty] | PHONE:
YES | USE CDOT Form #140 1/93
YES | III. KEY PROJECT PERSONNEL & PROJECT ADMINSTRATION
YES | Local Agency Personnel
YES | Project Engineer Design
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Project Engineer Construction
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Assistant Project Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Inspector
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Inspector
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Owners Certified Materials Testing Firm Representative
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Maintenance Representative
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Key Representatives
YES | CDOT Resident Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Local Agency Coordinator
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Other/Additional
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Company Name:
YES | Street Addr. City, State Zip |  |  |  |  | Office #:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | Project Manager
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | Superintendent
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | Superintendent Designee # 1
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | Superintendent Designee # 2
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | Other
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Authorized to sign Change Orders?
YES | A. Authority of the Engineer
YES | The Contractor is reminded of the requirements of subsections 105.01 and 105.14 of the CDOT Standard Specifications relative to the authority and duties of the Project Engineer. The Project Engineer has immediate charge of the administrative and engineering details of the project. The Contractor is cautioned that only the Project Engineer is authorized to provide information, clarification, or interpretation regarding plans, specifications, and any other contract documents or requirements, per subsection 105.09 of the Standard Specifications. Solicitation and receipt of information by the Contractor from any other individuals will not be considered valid for administration of the project. Shop drawings and all other submittals required by the Contract shall be submitted to the Project Engineer. Submittals made to and received by other individuals will not be considered valid for the purpose of administration of the Contract.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | III A1 | Dispute Review Board Members (Standing DRB) |  |  |  |  | 105.23(l) | Pre-Con
YES | III A2 | Form 1378 - Contractor Selection of Litigation or Arbitration |  |  |  |  | 105.24(f) | Pre-Con
YES | B. Payment
YES | 1. Estimate cutoff date:
YES | 2. Electronic Funds Transfer (EFT) - Local Agency Contact Name and contact information:
YES | 3. Prompt Payment: §107.01 requires all Contractors to comply with the Prompt Payment Law (CRS 24-91-103(2)). Per Standard Specification 109.06, the Contractor shall submit monthly payment confirmation through B2GNow. Failure to submit required information may result in withholding of subsequent payments.
YES | 4. Does the Contractor intend to provide securities in lieu of cash retainage to be withheld from payments?
YES | 5. Retainage will not be reduced until all project work is complete, the project has been accepted, and all required documentation has been received and accepted.
YES | 6. Forms: The Contractor shall be responsible for completing and submitting all required forms, instructing all subcontractors on the proper procedures for completing required forms, and for ensuring that all forms and reports are submitted and approved on a timely basis. Failure to do so may result in delays in payment of progress estimates.
YES | 7. If required by the Local Agency, the Contractor's Drawdown schedule is required to begin work. An update is required on the first day of each month during construction. Failure to provide an update may result in a delay of the next progress payment.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | III B1 | Monthly Subcontractor Payment information submitted via B2GNow System |  |  |  |  | 108.04(b) | Monthly
YES | III B2 | Payment/Drawdown Schedule (if required) |  |  |  |  | 108.04(a) | Pre-Con
YES | III B3 | Payment/Drawdown Schedule Update (if required) |  |  |  |  | 108.04(b) | 1st Day / Month
YES | C. Contract Time
YES | 1. Notice to Proceed Date: _______________ | [5 empty] | Anticipated Start Date: _______________
YES | 2. Time count is: ____ Working Days, or ____ Calendar Days, or __ /__ /____ Fixed Completion Date
YES | 3. Date project time charges begin:
YES | 4. Working time restrictions noted in the plans are:
YES | 5. The Contractor will work _________________ days per week.
YES | 6. The Contractor's working hours will be from | [6 empty] | to
YES | 7. Special concerns:
YES | D. Schedules & Methods Statements
YES | 1. The Contractor's schedule is required to begin work. A monthly update is required on the _______________________ day of the month.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | III B1 | Monthly Payment submitted via B2GNow System |  |  |  |  | 108.04(b) | Monthly
YES | III B2 | Payment/Drawdown Schedule |  |  |  |  | 108.04(a) | Pre-Con
YES | III D3 | Baseline Schedule (Note may be submitted in 14 days of award instead of Preliminary Schedule). |  |  |  |  | 108.03(e) | Within 45 days after award.
YES | III D4 | Method Statements for each Salient Feature. i.e. Paving Method, etc. |  |  |  |  | 108.03(f), 105.02(b) | Prior to any work on salient feature.
YES | III D5 | Project Schedule Updates |  |  |  |  | 108.03(g) | Monthly by progess paym't cut-off date
YES | III D6 | Weekly Planning Schedule (two week look ahead for planned activities) |  |  |  |  | 108.03(h) | Weekly (progress meeting)
YES | E. Weekly Progress Meeting / Office & Lab Info
YES | 1. Day and time of weekly progress meeting:
YES | 2. Location of weekly progress meeting:
YES | 3. Field office location:
YES | 4. Field lab location:
YES | F. Legal Gross Truck Weights
YES | Legal gross truck weights on all public roads, including within the project limits, will be controlled as follows (§105.18)
YES | 1. If material is delivered to the project in a vehicle with a gross weight exceeding the legal limit, the material and the scale ticket will not be accepted. If material is inadvertently incorporated into the project, it will be price reduced per section 105.18.
YES | 2. Truck scale tickets will be delivered on site
YES | 3. Truck scale tickets will be collected by
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | III F1 | List of Haul Vehicles |  |  |  |  | 109.01, 412.07(a) | Prior to the time of delivery
YES | III F2 | Weigher Certifications |  |  |  |  | 109.01 | Prior to the time of delivery
YES | G. Fuel Cost Adjustments
YES | On Form 85, submitted at the time of bid opening, per Revision of Section 109 Fuel Cost Adjustment, the Contractor chose to either accept or decline the Fuel Cost Adjustments for this project as follows:
YES | Once bids were opened, the Contractor is not allowed to change this decision.
YES | H. Comments, Concerns, and Follow Up Items on Project Administration
YES
YES | IV. Civil Rights & Labor Compliance
YES | Agency Personnel
YES | CDOT Region Civil Rights Manager
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Region Civil Rights Specialist
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Local Agency Civil Rights Specialist
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Project EEO Officer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | A. Civil Rights
YES | 1. DBE Goal for this project: ______________ DBE Commitment: __________________
YES | 2. On the Job Training (OJT) Goal for this project: ____________________________ Contractor to provide list of OJT trainees and their roles on the project.
YES | 3. CDOT Form 280 - EEO Interviews for this project (per month): ______________________
YES | 4. The Contractor shall submit all documents pertaining to Civil Rights and Labor Compliance to the Project Engineer and the CDOT Region Civil Rights Office.
YES | 5. CDOT Form 205 - Sublet Permit Application needs to be submitted by the Contractor for each subcontractor (including Truck Drivers) working on the project. (Automated by B2G if used)
YES | 6. CDOT has a zero tolerance policy against sexual harassment, workplace violence, and drug or alcohol abuse. Complaints regarding these issues should be referred to agency Civil Rights personnel. Does everyone understand this policy? | [6 empty] | ___Yes | ___No
YES | 7. Does the Contractor have a company policy on drug and alcohol use in the workplace? | [6 empty] | ___Yes | ___No
YES | 8. Subcontracts, including lower tiers, must physically incorporate the FHWA 1273 - Required Contract Provisions Federal-Aid Construction Contracts for all federally assisted projects. The applicable requirements of Form FHWA-1273 are incorporated by reference for work done under any purchase order, rental agreement or agreement for other services.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | IV A1 | Form 1391 - Federal-Aid Highway Construction Contractors Annual EEO Report |  |  |  |  | Affirmative Action Reqrmnts SSPs | Each July for the duration of the project.
YES | IV A2 | Supervisor EEO Orientation |  |  |  |  | Affirmative Action Reqrmnts SSPs | Prior to the initiation of work at any job site.
YES | IV A3 | Project EEO Meeting |  |  |  |  | FHWA 1273 | Prior to the completion of work at any job site.
YES | IV A4 | Written notification to the Director of the Office of Federal Contract Compliance Programs for any construction subcontract in excess of $10,000. |  |  |  |  | Affirmative Action Reqrmnts SSPs | Within 10 working days of award of any const. sub-contract
YES | IV A5 | DBE Participation (via B2GNow - based off Project's Utilization Plan). |  |  |  |  | DBE Requirements SSP & Goal | Monthly & after final payment.
YES | IV A6 | Form 1420 - DBE Participation Plan Modification Request (Changing Form 1417) - must be approved in order to count toward the goal. |  |  |  |  | DBE Requirements SSP & Goal | Before modif-ication to DBE Plan
YES | IV A7 | Form 1337 - Contractor Commitment to Meet OJT Requirements |  |  |  |  | On the Job Train. Goal SSP | Before training begins (PreCon)
YES | IV A8 | Form 838 - On-the-Job Trainee/Apprentice Record & OJT training program and copy of trainee acceptance / certification approved by Engr. |  |  |  |  | On the Job Train. Goal SSP | Before training begins (PreCon)
YES | IV A9 | Form 832 - Trainee Status and Evaluation Report |  |  |  |  | On the Job Train. Goal SSP | Monthly by progess paym't cut-off date
YES | IV A10 | Form 1336 - OJT Modification Request - must be approved in order to count toward the goal. |  |  |  |  | OJT Requirements SSP & Goal | Before modif-ication to OJT Goal
YES | IV A11 | Form 205 - Sublet Permit Application |  |  |  |  | 108.01 | Prior to the initiation of sub work at any job site.
YES | IV A12 | Form 1432 - Commercially Useful Function Questionnaire |  |  |  |  | DBE Requirements SSP & Goal | Prior to the relase of retainage | Applies to all projects. State & Fed
YES | IV A13 | Prompt Payment (via B2GNow) (based off approved Form 205(s)). |  |  |  |  | DBE Requirements SSP & Goal | Monthly & after final payment. | If no B2G then FM1418
YES | IV A14 | Form 1425 - Supplier List (list all materials/items the sum of which is $10,000) |  |  |  |  | DBE Requirements SSP & Goal | Prior to work on the project beginning
YES | B. Bulletin Board
YES | 1. Location of Project Bulletin Board:
YES | Items posted to the bulletin board shall be legible at all times. The latest version of the documents may be obtained from: https://www.codot.gov/business/bidding/bulletin-board-posting
YES | C. Certified Payrolls
YES | 1. Contractor and each subcontractor shall submit their certified payrolls directly into LCPtracker. Certified payrolls from the Contractor and subcontractors are to be submitted within seven days of payment. The classification name and classification code must be identifed on each payroll for each employee. A unique identification number must accompany an employee's name the first time it appears on payroll. All subcontractors are to remit payrolls to the Contractor who, in turn, will check and approve payrolls for compliance prior to submittal to the Project Engineer. Failure to submit Certified payrolls, may result in the withholding of payment and/or retainage.
YES | 2. Contractor Fringe Benefit Statement shall be submitted for each individual, or for groups of people, for all employees who perform work on the project and whose wages are covered by the Davis-Bacon Related Acts. Other approved deductions shall be noted within LCPtracker, and supporting documentation shall be attached. If for any reason the fringe benefits are altered during the life of the project, the Contractor, subcontractor, or both shall submit a revised Contractor Fringe Benefit Statement to accurately reflect the changes.
YES | D. Submittals
YES | The Contractor should reference the submittal list to know which documents are required to be submitted.
YES | E. Comments, Concerns, and Follow Up Items on Civil Rights and Labor Compliance
YES | Note: A Separate Civil Rights & Labor Compliance Mtg. may be held to review more detailed information.
YES | V. Specialty Units
YES | A. Environmental and Wetlands
YES | Personnel
YES | Agency Principal Contact
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Environmental Specialist
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Erosion Control Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | 1. Are any restrictions in place for this project?
YES | If yes, discuss restrictions:
YES | 2. All mulch, seed, sod, plants, shrubs and other similar biological material must be free from noxious weeds to minimize their propagation.
YES | 3. Review staked or delineated wetland areas and/or animal habitat areas.
YES | 4. Review protected trees and shrubs and highly erodible soils.
YES | 5. Environmental Pre-Con. Mtg. will be on the ______________ day of ______________
YES | 6. Review historical sites and markers withing the limits of the project that are to be preserved.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | V A1 | Colorado Discharge Permit System Stormwater Construction Permit (CDPS-SCP) |  |  |  |  | 107.25(d) SSP | PreCon
YES | V A2 | Temporary/Permanent Erosion Control Schedule |  |  |  |  | 208.03(b) | With Project Schedule
YES | V A3 | Clean Equipment Certification |  |  |  |  | 107.25(b)21 | Prior to equipment arrival to site.
YES | V A4 | SWMP Notebook |  |  |  |  | 208.03(d)1 | Engineer provides Contractor
YES | V A5 | Potential Pollution Source Report |  |  |  |  | 107.25(b)6 | Prior to Environ. PreCon
YES | V A6 | Proof of Erosion Control Supervisor satisfactory completion of CDOT authorized training program. |  |  |  |  | 208.03(c) | Prior to Environ. PreCon
YES | V A7 | Spill Prevention, Control, and Countermeasure Plan |  |  |  |  | 208.06(c) | Prior to const. & when revisions are made to SWMP
YES | V A8 | Concrete Washout Method Statement |  |  |  |  | 208.02(j) | With updated SWMP Notebook
YES | V A9 | Weed Free Certification |  |  |  |  | 208.02(a), 213.02 | With Submittal for particular item
YES | B. Right-of-Way
YES | CDOT or Local Agency Personnel
YES | Region ROW Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Local Agency ROW Contact
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | 1. Construction Surveying should be completed in accordance with Section 625 of the Conract Specifications. Ensure that all survey benchmarks, monumentation, and stakes are adequately marked and preserved.
YES | 2. Review the Limits of Construction, Historical Sites and Markers within limits, and insure that Archaeological and Paleontological Sites are staked.
YES | 3. Are any restrictions in place for this project?
YES | If yes, discuss restrictions:
YES | 4. Agreements to Access Private Property
YES | The Contractor shall furnish the Project Engineer properly executed written documentation from property owners that authorizes the Contractor to trespass on private property for any of the following conditions: a. Temporary livestock fencing outside the ROW b. Not installing livestock fencing and who will be held responsible until fence is installed c. Haul roads on private property not designated on the plans d. Waste or stockpile areas on private property not designated on the plans e. Equipment, camp, plant, or crusher sites on private property not designated on the plans f. Sources of aggregates, borrow, etc. on private property not designated on the plans.
YES | Comments:
YES | 5. Visual aids can substantially complement the written documentation required by CDOT (especially in verifying existing site conditions, etc.). Prior to and during the project, use cameras and video recorders to document field conditions and results.
YES | C. Utilities
YES | Agency Personnel
YES | Local Agency Utilities Contact
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Region Utilities Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Utility Personnel - And Discussion of Restrictions or Conflicts
YES | Electric:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Gas:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Communications (Telephone):
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Water:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Sewer:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Cable:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | ITS:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Railroad:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Irrigation:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | Other:
YES | Company: |  |  |  |  | Title:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES
YES
YES | D. Materials
YES | Personnel
YES | Owners Quality Assurance Supervisor/Head Tester
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Project Tester
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Region Materials Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Quality Assurance Personnel
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Agenda Items
YES | 1. The Contractor should reference the submittal list and the CDOT Approved Product List (APL) to know which documents are required to be submitted. The APL list can be accessed at https://www.codot.gov/business/apl/notice-to-contractors.html.
YES | 2. Mix Designs and Material Samples
YES | Required mix designs are shown on the submittals list. Any unapproved materials will not be placed on the project. The Contractor shall reference the "Special Notice to Contractors" (CDOT Field Materials Manual) for information concerning timely submittal of material samples.
YES | 3. Land Reclamation Pit
YES | The Contractor shall comply with the requirements of the Land Reclamation Permit, including pit limits.
YES | Comments:
YES | 4. Test Data
YES | Test data will be available for the Contractor's review on a daily basis. CDOT Form 626 - Field Lab Tests Results will be given to the Contractor for failing tests. Who shall receive this form, if required? _________________________________________________________________________
YES | 5. COCs and CTRs
YES | a. COCs and CTRs must contain all eleven items shown in Standard Specification 106.12 and 106.13 respectively and the following statement with an original signature and date:
YES | "I hereby certify under penalty of perjury that the material listed in this Certificate of Compliance/Certified Test Report represents (QTY) of pay item (PAY ITEM # & Description) for installation on project number (PROJECT NUMBER).
YES | b. Certified Invoices must contain the following statement with an original signature and date:
YES | "We certify, by photocopy of this invoice, that the quantity of material/rental or lease/specialty work, represented by this invoice was purchased and received for CDOT Project No. (PROJECT #) and that the prices shown are actual costs."
YES | 6. Salvable Materials
YES | Salvable materials that become the property of the owner must be carefully removed in sections and properly marked and stored. Where required, the Contractor is to utilize match markings for the reassembly of structures. If materials are to be reused on the project, they will be inspected for damage after they are removed. Discuss any special requirements as per Project Provisions.
YES | 7. Buy America
YES | The Contractor is required to follow all requirements outlined in the contract regarding Buy America. Failure to comply will result in removal of the non-complaint steel or iron at the Contractor's expense. NOTE: All required documentation for the Buy America program must be received prior to fabrication and/or installation. (Refer to Section 206.11 of the Standard and Special Provisions for this Project).
YES | Comments:
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | V D1 | List of Proposed Material Suppliers, Form 1425 |  |  |  |  | 106.01 | PreCon & updated two weeks prior to delivery or fabrication for each material.
YES | V D2 | Source of Undesignated Materials |  |  |  |  | 106.02(b) | Before used on the project for each particular item
YES | V D3 | Pipe Material to be used |  |  |  |  | 624.02 | PreCon
YES | V D4 | What Structural Plate Material will be used - Aluminum or Steel? |  |  |  |  | 510.02 | PreCon
YES | V D5 | Waterstops and Expansion Joints - manufacturer and model number of the designated devices. |  |  |  |  | 518.04, 518.05, 518.07 | PreCon
YES | V D6 | Lighting Materials & equipment |  |  |  |  | 613.02(i) | PreCon
YES | V D7 | Concrete Mix Design |  |  |  |  | 601.05 | For Approval Prior to Placement
YES | V D8 | Certified Cement Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Prior to use of Cement.
YES | V D9 | Certified Fly Ash Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Prior to use of Fly Ash.
YES | V D10 | Flow fill Mix Design |  |  |  |  | 206.02(a) | For Approval Prior to Placement
YES | V D11 | Concrete Quality Control Plan |  |  |  |  | 106.06(a)1 | PreCon
YES | V D12 | Form 46 - Concrete Truck Mixer Inspection Certification |  |  |  |  | 601.07(c)3 | When each concrete truck is delivering to the site.
YES | V D13 | Scale Certifications |  |  |  |  | 109.01 | When each truck is delivering to the site.
YES | V D14 | HMA Mix Design |  |  |  |  | 401.02(a)1 | For Approval Prior to Production of the Material
YES | V D15 | HMA Quality Control Plan |  |  |  |  | 106.05(a)1 | PreCon
YES | V D16 | HMA Segregation Quality Control Plan |  |  |  |  | 403.02 PSP | For Approval Prior to Paving
YES | V D17 | NCHRP 350 Certification for Work Zone Devices |  |  |  |  | 630.09 | Before used on the project for each particular item
YES | V D18 | COCs |  |  |  |  | 106.12 | Prior to the installation of the material.
YES | V D19 | CTRs |  |  |  |  | 106.13 | Prior to the installation of the material.
YES | V D20 | Paint Certification |  |  |  |  | 708 | Prior to use on the project.
YES | V D21 | Quality Control Plan for Embankment |  |  |  |  | 203.03(a) | For Approval Prior to Placement
YES | V D22 | Buy America Certification |  |  |  |  | 106.11 | Prior to the perm-anent incorpor-ation of steel or iron on the project.
YES | E. Hydraulics
YES | Personnel
YES | Local Agency or CDOT Hydraulics Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | F. CDOT Staff Bridge
YES | CDOT Personnel
YES | Staff Bridge Unit Leader
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Bridge Construction Engineer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | 1. Are any restrictions in place for this project?
YES | If yes, discuss restrictions:
YES | 2. Fabrication Quality Assurance Inspection required from Staff Bridge?
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | V F1 | The Erection Plan, Precast Bridge Girders and Falsework -Review from CDOT Bridge Fabrication Unit Provide either 1 week prior to the Pre-Erectio Confrnce or 2 weeks prior to fabrication. |  |  |  |  | 509.27, 601.11, 618.14 | Earliest of before Pre-Erec. Con. or fabrication.
YES | V F2 | Written documentation of daily inspections of the erected girders and other permanent and temporary bridge elements until the deck concrete has attained the Field Compressive Strength. |  |  |  |  | 509.27, 601.11, 618.14 | Within 24 hours following each inspection.
YES | V F3 | Shop drawings for all prestressed components. |  |  |  |  | 618.04 | With the Erection Plan
YES | V F4 | Shop drawings, design calculations and load data for review of Type III bearing devices. |  |  |  |  | 512.17 | With the Erection Plan
YES | G. Comments, Concerns, and Follow Up Items on Specialty Units:
YES
YES | VI. Safety
YES | Agency Personnel
YES | Agency Safety Officer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Safety Officer
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | A. Submittals
YES | 1. The Contractor should reference the submittal list to know which documents are required to be submitted.
YES | 2. The Contractor shall conduct field safety meetings (also known as Toolbox or Tailgate meetings) at the frequency specified in the Plan, which shall be at least once per week.
YES | 3. The Contractor shall fill out the Notification for Serious Accident or Event on Construction Projects for any fatality, major injury (life threatening), or if 2 or more people are injured (non-life threatening) within the work zone.
YES | 4. The Contractor will be allowed to resume operations only after providing written documentation, certified by the Project Safety Manager or alternate, regarding the corrective actions taken to prevent recurrence. See Standard Specifications 107.06(f).
YES | Comments:
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | VI A1 | Health and Safety Plan (HASP) - including First Aid/Hospital/EMT Statement |  |  |  |  | 250.03(c) | For Approval Prior to const.
YES | VI A2 | Form 140 - Emergency Phone Number Cards to be posted at the job site. |  |  |  |  | included in this agenda | PreCon
YES | VI A3 | Project Safety Management Plan |  |  |  |  | 107.06(a) | Prior to construc.
YES | VI A4 | Safety "Toolbox" Meeting Schedule |  |  |  |  | 107.06(a)4 | Prior to const.
YES | VI A5 | PPE Statement |  |  |  |  | 107.06(e), 250.03(d)2F | Prior to const.
YES | B. Construction Zone Traffic Control
YES | Contractor Personnel
YES | Traffic Control Contractor Company Name:
YES | Street Addr. City, State Zip |  |  |  |  | Office #:
YES | Traffic Control Supervisor
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | 1. Contractor's Superintendent and all others serving in a similar capacity are required to complete a CDOT-approved two-day Traffic Control Supervisor training.
YES | 2. NCHRP 350 Requirements shall be met and fully implemented.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | VI B1 | Superintendent & TCS Traffic Control Certifications and CDOT or Alternate Training Certifications for all personel handling traffic. |  |  |  |  | 630.11 | PreCon
YES | VI B2 | NCHRP, Test Level 3 Certification for all Traffic Control Devices (as required) to be used on the project. |  |  |  |  | 630.10(a) | PreCon with initial TMP
YES | C. Transportation Management Plan (TMP)
YES | Agency Personnel
YES | Local Agency Public Information
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | CDOT Public Information
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Contractor Personnel
YES | Public Information Manager
YES | Name: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | 1. Is this project considered a significant project? (See CDOT Work Zone Safety and Mobility Rule Procedures Document - Published July 2014 for definition of significant project.)
YES | If so, has the TMP been submitted?
YES | The Contractor shall prepare a TMP for each phase of the project, as required.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | VI C1 | Transportation Management Plan (TMP) - Initial Plan provided at PreCon |  |  |  |  | 630.1 | For Approval Prior to each const. phase
YES | VI C1a | Traffic Control Plan (TCP) |  |  |  |  | 630.10(a) | with TMP
YES | VI C1b | Transportation Operations Plan (TO) |  |  |  |  | 630.10(b) | with TMP & weekly
YES | VI C1c | Public Information Manager (PIM) & Plan (PIP) |  |  |  |  | 630.10, PSP 626.01 | PreCon with initial TMP
YES | VI C1c(1) | Stakeholder list |  |  |  |  | PSP 626.01 | with PIP
YES | VI C1c(2) | Specific Stakeholders needing ongoing communication |  |  |  |  | PSP 626.01 | with PIP
YES | Other Stakeholders
YES | Organization:
YES | Name: |  |  |  |  | Title:
YES | Address: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Organization:
YES | Name: |  |  |  |  | Title:
YES | Address: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | Organization:
YES | Name: |  |  |  |  | Title:
YES | Address: |  |  |  |  | Office #:
YES | Mobile #: |  |  |  |  | Email:
YES | D. Method of Handling Traffic (MHT) - Initial submittal required at PreCon
YES | 1. Does the MHT contain a detailed diagram showing the location of all traffic control devices? | [6 empty] | ___Yes | ___No
YES | 2. Does the MHT show the method, length, and time duration for lane closures? | [6 empty] | ___Yes | ___No
YES | 3. Does the MHT show the location of flaggers and time duration of flagging operation? | [6 empty] | ___Yes | ___No
YES | 4. Doe the MHT contain a tabulation of all traffic control devices? | [6 empty] | ___Yes | ___No
YES | 5. Does the MHT address details of a mobile pavement marking zone (as required by the contract) | [5 empty] | _____ N/A | ___Yes | ___No
YES | 6. Does the MHT list supporting references? | [6 empty] | ___Yes | ___No
YES | 7. Does the MHT show an access maintenance plan showing access for all properties? | [6 empty] | ___Yes | ___No
YES | 8. Does the MHT show areas where equipment will be stored, vehicles parked, and construction signs and materials will be stored? | [6 empty] | ___Yes | ___No
YES | 9. Does the MHT have a plan for maintaining and controlling pedestrian, bicycle, and other non-vehicular traffic? | [6 empty] | ___Yes | ___No
YES | 10. Are verifications needed by survey of horizontal or vertical clearances? | [5 empty] | _____ N/A | ___Yes | ___No
YES | Comments:
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | VI D1 | Method of Handling Traffic (MHT) to implement the TCP - Initial MHT with the TMP provided at PreCon |  |  |  |  | 630.10(a) | For Approval Prior to each const. phase | N/A
YES | VI D2 | Construction Traffic Information Signs |  |  |  |  | Drawing S-630-1 note:6 | After Award
YES | E. Construction Signing
YES | 1. All signing shall conform to the latest adopted version of the MUTCD, including the Colorado Supplement. The current MUTCD can be found at: https://www.codot.gov/library/traffic/traffic-manuals-guidelines/fed-state-co-traffic-manuals/mutcd.
YES | 2. Is there any construction signing on the project that is not the responsibility of the Contractor? If yes, explain:
YES | F. Speed Limits/Uniform Traffic Control
YES | 1. The Form 568 has been approved based on plans and specifications for a reduction of speed to ________ MPH. (US and State Highways only) | [6 empty] | ___Yes | ___No
YES | 2. Uniform Traffic Control (UTC) will be utilized on this project. | [6 empty] | ___Yes | ___No
YES | - The Contractor shall conform to and submit a copy of the local jurisdiction's policy regarding authorized duties of the UTC on the project.
YES | Submittal | [5 empty] | Spec./ Standard | Due | Recvd?
YES | VI F1 | Form 568 - Authorization and Declaration of Temporary Speed Limits |  |  |  |  | 630.13, Drawing S-630-1 note.3 | By Project Engineer with Project Schedule Review
YES | G. Restrictions (Performed by Project Engineer)
YES | 1. Oversize/Overweight Vehicles
YES | Is a restriction needed for oversize/overweight vehicles on this project? | [6 empty] | ___Yes | ___No
YES | If oversize/ overweight or vertical/horizontal restrictions are required, the Project Engineer shall submit the following information to the Permits Unit of the Maintenance and Operations Branch at least 10 days in advance of the restriction.
YES | Start of Closure: |  |  |  |  | Width:
YES | End of Closure: |  |  |  |  | Length:
YES | Restriction: |  |  |  |  | Highway No:
YES | Closure/Detour: |  |  |  |  | Beginning Milepost:
YES | Town: |  |  |  |  | Ending Milepost:
YES | Junction: |  |  |  |  | Other:
YES | 2. Vertical and/or Horizontal Restrictions
YES | Is a restriction needed for oversize/overweight vehicles on this project? | [6 empty] | ___Yes | ___No
YES | Start of Closure: |  |  |  |  | Width:
YES | End of Closure: |  |  |  |  | Length:
YES | Restriction: |  |  |  |  | Highway No:
YES | Closure/Detour: |  |  |  |  | Beginning Milepost:
YES | Town: |  |  |  |  | Ending Milepost:
YES | Junction: |  |  |  |  | Other:
YES | H. Hazardous Materials & Operations
YES | Ensure that all suspected hazardous material/hazardous waste sites that have been identified during the Modified Environmetal Site Assessment and Site Investigation are properly staked or otherwise delineated. All special requirements of the Contract should be strictly enforced. Hazardous materials include lead paint, methamphetamine by-products and lab waste (death bags), etc. If anyone suspects hazardous materials on their projects they should immediately notify the Project Engineer. The Contractor is solely responsible for adhering to Federal and State laws and local ordinances with respect ot the safety of project personnel and the general public.
YES | I. Comments, Concerns, and Follow Up Items on Safety:
YES
YES | VII. Other Items
YES | A. Items of Note:
YES | Are there any Project Special Provisions that should be discussed? | [6 empty] | ___Yes | ___No
YES | Comments:
YES | B. Contractor Comments:
YES | Does the Contractor have any additional concerns/comments not previously discussed in this meeting? | [6 empty] | ___Yes | ___No
YES | Comments:
YES | C. Uncompleted Items Prior to Starting Work:
YES | Comments:
YES | D. Possible Change Orders:
YES | Comments:
VIII. Additional Meeting List
| Meeting |  |  |  | Date | Time | Location | Comments
Pre Survey Meeting
Asphalt Pre Paving & QC/QA Meeting
Concrete Pre Paving Meeting
Pre-Erection Meeting
Environmental Pre Construction Conference
Partnering Meeting
Weekly Progress Meeting
Standing DRB Update Meeting
Civil Rights & Labor Compliance Meeting
Accept Fuel Cost Adjustments
Decline Fuel Cost Adjustments

## CDOT Form 140 Emergency Phone
CDOT FORM 140 - EMERGENCY PHONE NUMBERS
SA#
EMERGENCY PHONE NUMBERS
| PHYSICIAN NAME: | PHONE:
| PHYSICIAN NAME: | PHONE:
| HOSPITAL: | PHONE:
| HOSPITAL: | PHONE:
| AMBULANCE: | PHONE:
| AMBULANCE: | PHONE:
| FIRE DEPT.: | PHONE:
| FIRE DEPT.: | PHONE:
| POLICE: | PHONE:
| POLICE: | PHONE:
CDOT Form #140 1/93

## ProjEmergency Notification List
PROJECT EMERGENCY NOTIFICATION LIST
Project Emergency Notification List
Date Last Updated: | [9 empty] | 2022-04-07 11:01
Project No.: |  |  | 0 | [7 empty] | Project Code: |  |  | 0
Description:
Location: |  |  | SH | 0 |  |  | MP: |  | 0 |  | to MP: |  | 0
Project Location: |  |  |  | 0
Estimated Construction Dates: | [7 empty] | JAN | 1 |  |  | TO | JAN | 1
Local Agency:
CDOT
Project Engineer | [6 empty] | Resident Engineer |  |  |  |  | Area Maintenance Supervisor
Name: |  | 0 |  |  |  |  | Name: |  | 0 |  |  | Name: |  | 0
Office Phone: |  |  | 0 |  |  |  | Office Phone: |  |  | 0 |  | Office Phone: |  |  | 0
Cell Phone: |  |  | 0 |  |  |  | Cell Phone: |  |  | 0 |  | Cell Phone: |  |  | 0
Fax: | [6 empty] | Fax: |  |  |  |  | Fax:
Radio: | [6 empty] | Radio: |  |  |  |  | Radio:
(Local Agency Name Here)
Project Engineer | [6 empty] | Field Inspector |  |  |  |  | Road Maintenance
Name: | [6 empty] | Name: |  |  |  |  | Name:
Office Phone: | [6 empty] | Office Phone: |  |  |  |  | Office Phone:
Cell Phone: | [6 empty] | Cell Phone: |  |  |  |  | Cell Phone:
Fax: | [6 empty] | Fax: |  |  |  |  | Fax:
Radio: | [6 empty] | Radio: |  |  |  |  | Radio:
Prime Contractor
Project Superintendent | [6 empty] | Project Manager |  |  |  |  | Alternate Superintendent
Name: |  | 0 |  |  |  |  | Name: |  | 0 |  |  | Name: |  | 0
Office Phone: |  |  | 0 |  |  |  | Office Phone: |  |  | 0 |  | Office Phone: |  |  | 0
Cell Phone: |  |  | 0 |  |  |  | Cell Phone: |  |  | 0 |  | Cell Phone: |  |  | 0
Prime Contractor: |  |  |  | 0 | [7 empty] | Office Phone:
Address: |  |  |  | 0 | [7 empty] | Fax:
Traffic Control Contractor
Traffic Control Supervisor | [6 empty] | Alternate TCS
Name: |  | 0 |  |  |  |  | Name: |  | 0
Office Phone: |  |  | 0 |  |  |  | Office Phone: |  |  | 0
Cell Phone: |  |  | 0 |  |  |  | Cell Phone: |  |  | 0
Traffic Control Contractor: | [5 empty] | 0 | [5 empty] | Office Phone: |  |  | 0
Address: |  |  |  | 0 | [7 empty] | Fax:
cc | State Patrol Dispatch |  |  |  | Dispatch |  |  |  |  | Local County Sheriff
| Local State Patrol – | [8 empty] | Area Maint. Super. –
| RTD – | [8 empty] | Residency Engr. –
| Program Engineer – | [8 empty] | Project Manager –
| Region Maint.Supt. – | [8 empty] | Finals –
| Region EEO – | [8 empty] | Prime Contractor –
| Region Materials – | [8 empty] | TCS
| Region Safety – | [8 empty] | File

## Key Personnel
KEY PROJECT PERSONNEL
Include in this Project?
YES | CDOT Personnel | [6 empty] | SA# | 0
YES | Project Engineer Design
YES | Name: | 0 |  |  |  | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Project Engineer Construction
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Assistant Project Engineer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Inspector
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Inspector
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Owners Certified Materials Testing Firm Representative
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Maintenance Representative
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Key Representatives
YES | CDOT Resident Engineer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Local Agency Coordinator
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Other/Additional
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Project Manager
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Authorized to sign Change Orders? |  |  |  | 0
YES | Superintendent
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Authorized to sign Change Orders? |  |  |  | 0
YES | Superintendent Designee # 1
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Authorized to sign Change Orders? |  |  |  | 0
YES | Superintendent Designee # 2
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Authorized to sign Change Orders? |  |  |  | 0
YES | Other
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Authorized to sign Change Orders? |  |  |  | 0
YES | CDOT Personnel
YES | CDOT Region Civil Rights Specialist
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Project EEO Officer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Personnel
YES | Agency Principal Contact
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Erosion Control Supervisor
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Personnel
YES | Region ROW Supervisor
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Local Agency Utilities Contact
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Utility Personnel
YES | Electric:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Gas:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Communications (Telephone):
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Water:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Sewer:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Cable:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | ITS:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Railroad:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Irrigation:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Other:
YES | Company: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Personnel
YES | Owners Quality Assurance Supervisor/Head Tester
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Project Tester
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Region Materials Engineer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Quality Assurance Personnel
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Personnel
YES | Local Agency or CDOT Hydraulics Engineer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 109.01 | When each truck is delivering to the site. | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 401.02(a)1 | For Approval Prior to Production of the Material | 0
YES | Staff Bridge Unit Leader
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Bridge Construction Engineer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Agency Safety Officer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Safety Officer
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Traffic Control Supervisor
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | CDOT Personnel
YES | Local Agency Public Information
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Contractor Personnel
YES | Public Information Manager
YES | Name: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Other Stakeholders
YES | Organization:
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Address: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Organization:
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Address: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0
YES | Organization:
YES | Name: | 0 | 0 | 0 | 0 | Title: | 0 | 0 | 0
YES | Address: | 0 | 0 | 0 | 0 | Office #: | 0 | 0 | 0
YES | Mobile #: | 0 | 0 | 0 | 0 | Email: | 0 | 0 | 0

## Submittal List
SUBMITTAL CHECK LIST
| Project: |  |  |  | Project Code: |  | 0
Local Agency:
| Highway Location: | SH | 0 | MP: | 0 | to MP: | 0
Project Location:
Description:
SUBMITTAL | [5 empty] | SPECIFICATION/ STANDARD | DUE | RECEIVED? | INCLUDE IN THIS PROJECT?
III A1 | Dispute Review Board Members (Standing DRB) |  |  |  |  | 105.23(l) | Pre-Con | 0 | YES
III A2 | Form 1378 - Contractor Selection of Litigation or Arbitration |  |  |  |  | 105.24(f) | Pre-Con | 0 | YES
III B1 | Form 1418 - Monthly Payment Summary |  |  |  |  | 108.04(b) | Monthly | 0 | YES
III B2 | Payment/Drawdown Schedule |  |  |  |  | 108.04(a) | Pre-Con | 0 | YES
III B3 | Payment/Drawdown Schedule Update |  |  |  |  | 108.04(b) | Monthly, 1st day each month | 0 | YES
III D1 | Preliminary Schedule (Optional - Baseline Schedule may be submitted instead in this timeframe). |  |  |  |  | 108.03(d) | Within 14 days after award. | 0 | YES
III D2 | Scheduling Software Selection (MS Project or Primavera) |  |  |  |  | 108.03(b) | Pre-Con | 0 | YES
III D3 | Baseline Schedule (Note may be submitted in 14 days of award instead of Preliminary Schedule). |  |  |  |  | 108.03(e) | Within 45 days after award. | 0 | YES
III D4 | Method Statements for each Salient Feature. i.e. Paving Method, etc. |  |  |  |  | 108.03(f), 105.02(b) | Prior to any work on salient feature. | 0 | YES
III D5 | Project Schedule Updates |  |  |  |  | 108.03(g) | Monthly by cut-off date for progress pay estimate | 0 | YES
III D6 | Weekly Planning Schedule (two week look ahead for planned activities) |  |  |  |  | 108.03(h) | Weekly (progress meeting) | 0 | YES
III F1 | List of Haul Vehicles |  |  |  |  | 109.01, 412.07(a) | Prior to the time of delivery | 0 | YES
III F2 | Weigher Certifications |  |  |  |  | 109.01 | Prior to the time of delivery | 0 | YES
IV A1 | Form 1391 - Federal-Aid Highway Construction Contractors Annual EEO Report |  |  |  |  | Affirmative Action Reqrmnts SSPs | Each July for the duration of the project. | 0 | YES
IV A2 | Supervisor EEO Orientation |  |  |  |  | Affirmative Action Reqrmnts SSPs | Prior to the initiation of work at any job site. | 0 | YES
IV A3 | Written notification to the Director of the Office of Federal Contract Compliance Programs for any construction subcontract in excess of $10,000. |  |  |  |  | Affirmative Action Reqrmnts SSPs | Within 10 working days of award of any construction subcontract. | 0 | YES
IV A4 | Form 1419 - DBE Participation Report (based off Forms 1417 - Anticipated DBE Plan & 1415 DBE Commitment Confirmation) |  |  |  |  | DBE Requirements SSP & Goal | Quarterly (1/15, 4/15, 7/15. 10/15) & before final payment. | 0 | YES
IV A5 | Form 1420 - DBE Participation Plan Modification Request (Changing Form 1417) - must be approved in order to count toward the goal. |  |  |  |  | DBE Requirements SSP & Goal | Before modification to DBE Plan | 0 | YES
IV A6 | Form 1337 - Contractor Commitment to Meet OJT Requirements |  |  |  |  | On the Job Train. Goal SSP | Before training begins (PreCon) | 0 | YES
IV A7 | Form 838 - On-the-Job Trainee/Apprentice Record & OJT training program and copy of trainee acceptance/certification approved by Engr. |  |  |  |  | On the Job Train. Goal SSP | Before training begins (PreCon) | 0 | YES
IV A8 | Form 832 - Trainee Status and Evaluation Report |  |  |  |  | On the Job Train. Goal SSP | Monthly by the cutoff date for the progress pay estimate | 0 | YES
IV A9 | Form 205 - Sublet Permit Application |  |  |  |  | 108.01 | Prior to the initiation of sub work at any job site. | 0 | YES
IV A10 | List of Subcontractors with work sublet |  |  |  |  | 108.01 | Prior to the initiation of sub work at any job site. | 0 | YES
IV A12 | Form 1432 - Commercially Useful Function Questionnaire |  |  |  |  | DBE Requirements SSP & Goal | Prior to the release of retainage | 0 | YES
IV A13 | Prompt Payment (via B2GNow) (based off approved Form 205(s)). |  |  |  |  | DBE Requirements SSP & Goal | Monthly & after final payment. | Applies to all projects. State & Fed | YES
IV A14 | Form 1425 - Supplier List (list all materials/items the sum of which is $10,000) |  |  |  |  | DBE Requirements SSP & Goal | Prior to work on the project beginning | If no B2G then FM1418 | YES
V A1 | Colorado Discharge Permit System Stormwater Construction Permit (CDPS-SCP) |  |  |  |  | 107.25(d) SSP | PreCon | 0 | YES
V A2 | Temporary/Permanent Erosion Control Schedule |  |  |  |  | 208.03(b) | With Project Schedule | 0 | YES
V A3 | Clean Equipment Certification |  |  |  |  | 107.25(b)21 | Prior to equipment arrival to the site. | 0 | YES
V A4 | SWMP Notebook |  |  |  |  | 208.03(d)1 | Engineer provides Contractor. | 0 | YES
V A5 | Potential Pollution Source Report |  |  |  |  | 107.25(b)6 | Prior to Environ. PreCon | 0 | YES
V A6 | Proof of Erosion Control Supervisor satisfactory completion of CDOT authorized training program. |  |  |  |  | 208.03(c) | Prior to Environ. PreCon | 0 | YES
V A7 | Spill Prevention, Control, and Countermeasure Plan |  |  |  |  | 208.06(c) | Prior to construction and any time there are revisions to the SWMP | 0 | YES
V A8 | Concrete Washout Method Statement |  |  |  |  | 208.02(j) | With updated SWMP Notebook | 0 | YES
V A9 | Weed Free Certification |  |  |  |  | 208.02(a), 213.02 | With Submittal for particular item | 0 | YES
V D1 | List of Proposed Material Suppliers, Form 1425 |  |  |  |  | 106.01 | PreCon & updated two weeks prior to delivery or fabrication for each material. | 0 | YES
V D2 | Source of Undesignated Materials |  |  |  |  | 106.02(b) | Before used on the project for each particular item | 0 | YES
V D3 | Pipe Material to be used |  |  |  |  | 624.02 | PreCon | 0 | YES
V D4 | What Structural Plate Material will be used - Aluminum or Steel? |  |  |  |  | 510.02 | PreCon | 0 | YES
V D5 | Waterstops and Expansion Joints - manufacturer and model number of the designated devices. |  |  |  |  | 518.04, 518.05, 518.07 | PreCon | 0 | YES
V D6 | Lighting Materials & equipment |  |  |  |  | 613.02(i) | PreCon | 0 | YES
V D7 | Concrete Mix Design |  |  |  |  | 601.05 | For Approval Prior to Placement | 0 | YES
V D8 | Certified Cement Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Prior to use of Cement. | 0 | YES
V D9 | Certified Fly Ash Test Reports |  |  |  |  | 106.13, 601.05, 701.01 | Prior to use of Fly Ash. | 0 | YES
V D10 | Flow fill Mix Design |  |  |  |  | 206.02(a) | For Approval Prior to Placement | 0 | YES
V D11 | Concrete Quality Control Plan |  |  |  |  | 106.06(a)1 | PreCon | 0 | YES
V D12 | Form 46 - Concrete Truck Mixer Inspection Certification |  |  |  |  | 601.07(c)3 | When each concrete truck is delivering to the site. | 0 | YES
V D13 | Scale Certifications |  |  |  |  | 109.01 | When each truck is delivering to the site. | 0 | YES
V D14 | HMA Mix Design |  |  |  |  | 401.02(a)1 | For Approval Prior to Production of the Material | 0 | YES
V D15 | HMA Quality Control Plan |  |  |  |  | 106.05(a)1 | PreCon | 0 | YES
V D16 | HMA Segregation Quality Control Plan |  |  |  |  | 403.02 PSP | For Approval Prior to Paving | 0 | YES
V D17 | NCHRP 350 Certification for Work Zone Devices |  |  |  |  | 630.09 | Before used on the project for each particular item | 0 | YES
V D18 | COCs |  |  |  |  | 106.12 | Prior to the installation of the material. | 0 | YES
V D19 | CTRs |  |  |  |  | 106.13 | Prior to the installation of the material. | 0 | YES
V D20 | Paint Certification |  |  |  |  | 708 | Prior to use on the project. | 0 | YES
V D21 | Quality Control Plan for Embankment |  |  |  |  | 203.03(a) | For Approval Prior to Placement | 0 | YES
V D22 | Buy America Certification |  |  |  |  | 106.11 | Prior to the permanent incorporation into the project of steel or iron products. | 0 | YES
V F1 | The Erection Plan, Precast Bridge Girders and Falsework - Approval from CDOT Bridge Fabrication Unit |  |  |  |  | 509.27, 601.11, 618.14 | The earliest of either - One week prior to the Pre-Erection Conference or Two weeks prior to any fabrication. | 0 | YES
V F2 | Written documentation of daily inspections of the erected girders and other permanent and temporary bridge elements until the deck concrete has attained the Field Compressive Strength. |  |  |  |  | 509.27, 601.11 | Within 24 hours following each inspection. | 0 | YES
V F3 | Shop drawings for all prestressed components. |  |  |  |  | 618.04 | With the Erection Plan | 0 | YES
V F4 | Shop drawings, design calculations and load data for review of Type III bearing devices. |  |  |  |  | 512.17 | With the Erection Plan | 0 | YES
VI A1 | Health and Safety Plan (HASP) - including First Aid/Hospital/EMT Statement |  |  |  |  | 250.03(c) | For Approval Prior to construction | 0 | YES
VI A2 | Form 140 - Emergency Phone Number Cards to be posted at the job site. |  |  |  |  | included in this agenda | PreCon | 0 | YES
VI A3 | Project Safety Management Plan |  |  |  |  | 107.06(a) | Prior to construction. | 0 | YES
VI A4 | Safety "Toolbox" Meeting Schedule |  |  |  |  | 107.06(a)4 | Prior to construction. | 0 | YES
VI A5 | PPE Statement |  |  |  |  | 107.06(e), 250.03(d)2F | Prior to construction. | 0 | YES
VI B1 | Superintendent & TCS Traffic Control Certifications and CDOT or Alternate Training Certifications for all personnel handling traffic. |  |  |  |  | 630.11 | PreCon | 0 | YES
VI B2 | NCHRP, Test Level 3 Certification for all Traffic Control Devices (as required) to be used on the project. |  |  |  |  | 630.10(a) | PreCon with initial TMP | 0 | YES
VI C1 | Transportation Management Plan (TMP) - Initial Plan provided at PreCon |  |  |  |  | 630.1 | For Approval Prior to each phase of construction | 0 | YES
VI C1a | Traffic Control Plan (TCP) |  |  |  |  | 630.10(a) | with TMP | 0 | YES
VI C1b | Transportation Operations Plan (TO) |  |  |  |  | 630.10(b) | with TMP & weekly | 0 | YES
VI C1c | Public Information Manager (PIM) & Plan (PIP) |  |  |  |  | 630.10, PSP 626.01 | PreCon with initial TMP | 0 | YES
VI C1c(1) | Stakeholder list |  |  |  |  | PSP 626.01 | with PIP | 0 | YES
VI C1c(2) | Specific Stakeholders needing ongoing communication |  |  |  |  | PSP 626.01 | with PIP | 0 | YES
VI D1 | Method of Handling Traffic (MHT) to implement the TCP - Initial MHT with the TMP provided at PreCon |  |  |  |  | 630.10(a) | For Approval Prior to each phase of construction | N/A | YES
VI D2 | Construction Traffic Information Signs |  |  |  |  | Drawing S-630-1 note:6 | After Award | 0 | YES
VI F1 | Form 568 - Authorization and Declaration of Temporary Speed Limits |  |  |  |  | 630.13, Drawing S-630-1 note.3 | By Project Engineer with Project Schedule Review | 0 | YES