## Course Descriptions - TETP Cons
TETP Construction Training
Grouping | Class | What you'll learn | Format | Length
Engineering | Bridge Inspection Training | CDOT’s Bridge Inspection Training has been developed to increase knowledge and understanding of structural and bridge construction projects. The training will discuss commonly identified quality assurance and quality control challenges on CDOT structural projects including high-risk construction elements, critical points where additional documentation or inspection may be needed, and how to anticipate, mitigate, and best manage these elements. | Instructor-led | 2 days
Project Management | Buy America Requirements for Iron and Steel | This course introduces the requirements for the use of iron and steel products in federally-funded highway construction projects and explains how to document the processes performed on these iron and steel products. Failure to comply with both the use and the documentation requirements can result in the need to take corrective action, reduction in payment to the Contractor, loss of federal funding, and criminal and civil liability. | E-learning | 2 hours
Project Management | Construction Budget Mgmt for Project Managers & Engineers | In this online course, project managers and engineers will gain a basic understanding of project construction budgets, resource allocation and the budget management process during each phase of Preconstruction. The course introduces the software programs used to manage different parts of the financial and planning process as well as the STIP, key budget terms, overs and unders, and indirect costs. | E-learning | 4 hours
Engineering | Construction Change Orders | This course is for project and resident engineers involved with Change Orders for construction projects. The course explains the who, what, when, where, why and how of Change Orders, using examples from the simple to the complex. It explores how change orders and explanation letters need to be written and processed to effectively modify the contract between CDOT and the construction contractor. It also addresses federal and state regulations and requirements. There are no prerequisites, but construction project experience, familiarity with standards/specifications and familiarity with SiteManager software are strongly recommended. | E-learning | 2 hours
Engineering | Construction Force Accounts | This course is for project and resident engineers who work with the force account method of payment on construction projects. The course uses examples from simple to complex to explain the who, what, when, where, why and how of force account. | E-learning | 2 hours
Engineering | Construction Manual - Section 100 | This e-learning course for CDOT project managers, project engineers, construction engineers and inspectors introduce the key subsections in the Section 100 Standard Specification. It addresses the basic rules and regulations of project administration and issues where the majority of conflicts and disputes on a project arise. This is a prerequisite for the instructor-led Construction Project Administration course. | E-learning | 2 hours
Engineering | Construction Project Administration | This course introduces best practices in construction project administration for CDOT project managers, project engineers, construction engineers and inspectors. The course teaches about the contract and its implications, facilitating meetings, conducting field inspections, completing and reporting paperwork, and accessing and interpreting documentation. The Construction Manual: Section 100 E-learning courses are prerequisites. | Virtual Instructor-led | 2 days
Engineering | Construction Project Administration / Local Agencies | This course introduces Local Agency project managers to CDOT's best practices in project administration. Understanding the contract and its implications, meeting facilitation, field inspections, federally-required paperwork and reporting, and accessing and interpreting documentation will be presented. | Instructor-led | 2 days
Engineering | Construction Project Financials (Form 65) | This online course identifies and explores the Project Financials Statement, more commonly known as Form 65, and how you can identify, interpret and understand the financial status of your project, focusing on Post-Award. | E-learning | 2 hours
Engineering | Managing Contract Time | This course is an overview of how to manage contract time for project managers and project engineers. It covers using Critical Path Method (CPM) schedules to manage contract time and address delay issues on construction projects. There will be detailed discussions on issues that arise with an early completion date, how to handle a delay, what float ownership is, the benefit of using a baseline schedule, and the risks and benefits of certain actions. The Managing Contract Time E-learning course is a prerequisite course to familiarize learners with important information found in existing CDOT materials relating to managing contract time and addressing delays. | Virtual Instructor-led | 1 day
Engineering | Managing Contract Time E-learning | This course covers the basics of Managing Contract Time. It is a prerequisite to the instructor-led course. | E-learning | 2 hours
Engineering | Materials Technician Certification | This online course is designed for materials testers who are new to working with CDOT, including consultants and new CDOT hires. The course provides information and simulated situations, so students can learn about and practice the CDOT approach to administering testing, documentation and communication on construction projects. By the end of the course, materials testers will understand their role on a CDOT project and be able to find and use available resources, follow best practices, communicate with team members, enter and verify data in the Laboratory Information Management System (LIMS), and follow appropriate documentation procedures. Prerequisites include successful completion of CDOT’s SiteManager Materials (SMM)/LIMS for Samplers and Testers training and at least one current CDOT certification for asphalt, concrete and/or soil testing. | E-learning | 3 hours
Engineering | Municipal Separate Storm Sewer System (MS4) Permit Overview | This one-hour course covers the history of water quality in the United States, and the regulations and agencies that govern the Municipal Separate Storm Sewer System (MS4) permit. It describes CDOT’s role in managing the water quality within its MS4 boundary and covers the seven programs that make up the permit. | E-learning | 1 hour
Engineering | MS4 Overview for Engineering: Supplement | CDOT Engineers play a critical role in meeting CDOT’s MS4 Permit compliance. Throughout Design and Construction of projects, Engineers are critical in maintaining stormwater compliance. This 30-minute supplemental module provides additional information for the three MS4 programs that CDOT engineers interact the most with to maintain water quality, which include Industrial Facilities, Construction Sites, and Permanent Water Quality. | E-learning | 1/2 hour
Engineering | MS4 Overview for Maintenance: Supplement | CDOT Maintenance Staff play a critical role in meeting CDOT’s MS4 Permit compliance. This 30-minute supplemental module provides additional information for the five MS4 programs that CDOT maintenance interacts the most with to maintain water quality, which include Construction Sites, Permanent Water Quality, Illicit Discharges, Pollution Prevention and Good Housekeeping, and Wet Weather Monitoring programs. | E-learning | 1/2 hour
Project Management | Project First Program | This virtually taught course will prepare you to successfully use the Project First Program on your projects. Project First formalizes the partnering process to proactively identify and manage risks through collaboration. The goal is to create project wins while maintaining relationships. After you complete this course, you will understand: the requirements of the Project First standard special provision; how to facilitate Project First workshops; how to manage the Escalation Ladder; how to Manage the Project Risk Assessment Tool; how to differentiate when an issue should follow the Project First Escalation Ladder vs. the Disputes and Claims for Contract Adjustments process; and understand all the Project First resources. | Virtual Instructor-led | 5 hours
Project Management | Project Lifecycle Simulation | Project Lifecycle is a simulation that places participants in an environment where they can experience tradeoffs that are often part of complex projects. During the activity, participants learn about important project lifecycle levers and drivers, and gain a deeper appreciation for how each CDOT functional area contributes to managing the complexities of a large-scale project. | E-learning | 2 hours
Project Management | Reviewing Critical Path Method (CPM) Construction Schedules | This course addresses specific issues related to reviewing a Contractor’s Critical Path Method (CPM) schedule per the requirements of the CDOT Standard Specifications subsection 108.03 Project Schedule. Working in small groups, with CDOT Standard Specification 108.03 as guide, participants evaluate contractor schedules and reports to find potential issues within schedule submittals and take corrective action if necessary. When you have completed this course, you will have the skills to apply CDOT Standard Specifications subsection 108.03 Project Schedule to CPM Schedules submitted by the contractor. | Virtual Instructor-led | 1 day
Project Management | SAP Project Portal | The Systems, Applications and Products(SAP) Project Portal E-learning course provides a high-level overview of the new SAP Project Portal. It also describes key fields used for project management during the Preconstruction and Construction phases and explains how the Project Portal interacts with other software programs. | E-learning | 2 hours
Engineering | SiteManager | This hands-on construction project documentation and Pay Estimate system course for PEs and Inspectors will teach participants how to define terms and navigate in SiteManager, add subcontracts, create Daily Work Reports and Diaries, create Change Orders, and generate contractor payment estimates. Participants must be currently assigned to an active construction project and have basic Windows navigation knowledge. More information about SiteManager training can be found here. | Virtual Instructor-led | 1.5 days
Engineering | SiteManager Materials & LIMS | This is an online class for samplers/testers and those looking to learn about the materials workflow. Will teach participants how to create samples in SiteManager and complete the samples in Laboratory Information Management System (LIMS). Content also includes how to navigate and view project and materials information in CDOT Application for Reporting (CAR). Basic instruction on how to get access to SiteManager is also included. More information about SiteManager training can be found here. | Virtual Instructor-led | 1 day
Project Management | Utility Engineering Project Management E-learning | The Utility Engineering Project Management E-learning introduces CDOT’s process and methodology for managing sub-surface utility investigation and relocation. CDOT’s process emphasizes collaboration with utility owners and other stakeholders throughout a construction project. | E-learning | 4 hours
Project Management | Utility Engineering Project Management Workshop | The Utility Engineering Project Management Workshop is an immersive learning experience that challenges participants to analyze and assess the needs for utility coordination throughout the project life cycle from planning through design and construction. This course will utilize resources from past projects at CDOT to provide a learning experience that is grounded in the context of everyday practice in utility engineering. | Instructor-led | 1 day
Project Management | Work Zone Safety and Mobility - Development of Transportation Management Plan | The course focuses on the importance of the Work Zone Mobility Rule implementation (23 CFR Section 630 Subparts J & K) supporting required planning, design, positive protection for workers and reporting for creating safe work zones for roadway workers and the traveling public, by presenting in-depth information and providing practice in creating and utilizing effective Traffic Management Plans and Traffic Control Plans for various types of projects. | Instructor-led | 1 day
Project Management | Work Zone Safety and Mobility E-learning | The Work Zone Safety and Mobility E-learning course is a prerequisite to the one-day workshop. The course introduces the importance of the Work Zone Mobility Rule implementation (23 CFR Section 630 Subparts J & K) supporting required planning, design, positive protection for workers, and reporting for creating safe work zones for roadway workers and the traveling public. It will introduce basic work zone safety and mobility concepts, including: the rules and policies that govern work zone safety and mobility; the specific roles involved in developing and implementing a Traffic Management Plan; the components of a TMP, including the Traffic Control Plan, Traffic Operations, and Public; information, and the strategies available for each of these component; implementing the TMP; and reporting and communicating TMP requirements. | E-learning | 3 hours