

COLORADO

DEPARTMENT OF TRANSPORTATION

##### REGION 6

**REQUEST FOR QUALIFICATIONS**

US 6 Bridges Design Build Project

PROJECT NO. BR 0061-083

Subaccount Number

18838 (CN)

##### August 24, 2012

**STATEMENTS OF QUALIFICATIONS DUE: September 24, 2012**

**TABLE OF CONTENTS**

Page

**1.0 INTRODUCTION** 1

1.1 Procurement Process 1

1.2 Submitter Information 1

**2.0 BACKGROUND INFORMATION: RFQ PROCESS** 1

2.1 Project Description: Scope of Work/Purpose and Need 1

2.2 Project Goals 3

2.3 Estimated Cost: Maximum Time Allowed 3

2.4 Project Schedule 3

2.5 CDOT Project Management: Ex Parte Communications 4

2.6 Questions and Clarifications: Addenda 4

2.7 Major Participant 5

2.8 Ineligible Firms 5

2.9 Organizational Conflicts of Interest 5

2.10 Changes to Organizational Structure 7

2.11 Past Performance or Experience 8

2.12 Equal Employment Opportunity 8

2.13 Small and Disadvantaged Business Enterprises 8

2.14 CDOT on The Job Training (OJT) Program 9

3.**0 CONTENT OF SOQs AND CONFIDENTIALITY** 9

3.1 Introduction 9

3.2 Submitter Experience 9

*3.2.1 Submitter Experience* 10

*3.2.2 Contractor Safety Statistics* 10

3.3 Organization and Key Personnel 11

*3.3.1 Organizational Chart(s)* 11

*3.3.2 Resumes of Key Personnel* 11

*3.3.3 Minimum Requirements of Key Personnel* 12

3.4 Project and Management Approach 16

3.5 Legal 16

*3.5.1 Acknowledgment of Clarifications and Addenda* 16

*3.5.2 Organizational Conflicts of Interest* 16

*3.5.3 Legal Structure* 17

*3.5.4 Bonding Capability* 17

*3.5.5 Submitter Information* 17

*3.5.6 SOQ Forms* 18

**4.0 SOQ SUBMITTAL REQUIREMENTS** 18

4.1 Due Date, Time, and Location 18

4.2 Format/Quantities 18

4.3 Submittals 19

**5.0 EVALUATION PROCESS** 19

5.1 SOQ Evaluation 19

5.2 Interview 19

5.3 SOQ Evaluation and Scoring 19

5.4 Determining Short-Listed Submitters 21

5.5 Notification of Short-Listing 21

5.6 Debriefing Meetings 21

**6.0 PROCUREMENT PHASE 2** 21

6.1 Request for Proposals 21

6.2 RFP Content 22

*6.2.1 RFP Structure* 22

*6.2.2 RFP Information* 22

6.3 Alternative Configuration Concepts Meeting 22

6.4 Proposals Submitted in Response to the RFP 22

6.5 Proposal Evaluations 22

6.6 Stipends 23

**7.0 PROTEST PROCEDURES** 23

7.1 Protests Regarding RFQ 23

**FORMS**

FORM A – Submitter and Major Participant Information

FORM B – Contractor Safety Statistics

FORM C – Summary of Comparable Contracts in Past Ten (10) Years

FORM D – Receipt of Addenda/Clarifications

FORM E – Certificate of Prequalification

**1.0 INTRODUCTION**

The Colorado Department of Transportation (CDOT), Region 6 is requesting Statements of Qualifications (“SOQs”) from entities (“Submitters”) interested in submitting Proposals for the US 6 Bridges Design Build Project (the “Project”). The Project will be funded with Federal, State and Local dollars. Submitters must comply with all applicable Federal, State and Local requirements.

**1.1 Procurement Process**

CDOT will use a two-phase value based procurement process to select a Design Build contractor to deliver the Project. This Request for Qualifications (“RFQ”) is issued as part of the first phase to solicit information, in the form of SOQs. CDOT will evaluate received SOQs to determine which Submitters are the most highly qualified to successfully deliver the Project. CDOT will short-list not more than three most highly qualified Submitters that submit SOQs.

In the second phase, CDOT will issue a Request for Proposals (“RFP”) for the Project to the short-listed Submitters. Only the short-listed Submitters will be eligible to submit Proposals for the Project. Each short-listed Submitter that submits a Proposal in response to the RFP (if any) is referred to herein as a “Proposer.” CDOT will award a Design Build Contract for the Project (if any) to the Proposer offering the best value, as determined by CDOT at its sole discretion.

**1.2 Submitter Information**

To allow receipt of any addenda or other information regarding this RFQ, each Submitter is solely responsible for ensuring that CDOT’s Project Director as described in Section 2.5 has the contact person’s name and e-mail address. The contact person shall be the Submitter’s single point of contact. If an entity intends to submit a Proposal as part of a team, the entire team is required to submit a single SOQ as a single Submitter and shall have a single point of contact.

**2.0 Background Information: RFQ Process**

**2.1 Project Description, Scope of Work**

The Federal Highway Administration (FHWA) in cooperation with the Colorado Department of Transportation (CDOT) completed the I-25 Valley Highway Final Environmental Impact Study (FEIS) and issued a Phased Record of Decision (ROD) in June 2007.

FHWA in cooperation with CDOT is in the process of completing a reevaluation of the previous I-25 Valley Highway FEIS and Phased ROD issued in 2007. The reevaluation will result in a new Record of Decision (ROD) for this project and will encompass the first decision document’s project area along with the EIS preferred alternative for the US 6 mainline.

The new Record of Decision may not be issued at the time the Request for Proposals is released; however it is expected to be issued prior to issuance of the Final Addendum to the RFP. Proposers shall note that the Code of Federal Regulations (CFRs) prohibits any Final Design from being undertaken until the new Record of Decision is issued.

Transportation facilities identified in the Preferred Alternative for improvements include Interstate 25, from Logan St. on the south to US 6 on the north, and US 6, from I 25 on the east to Federal Blvd. on the west.

Improvements on these facilities, consistent with the FEIS Preferred Alternative and the ROD are intended to:

Provide lane continuity and balance.

* Optimize highway system operations.
* Improve connectivity and pedestrian and bicycle mobility.
* Increase safety for motorists, pedestrians and bicyclists.
* Correct roadway deficiencies to meet current design standards to provide a safer, more efficient and reliable transportation system.
* Increase safety and reduce congestion and delays.

The Project generally includes improvements at the I-25/US 6 interchange, partial closure of the Bryant Street interchange, a diamond interchange at US 6/Federal Boulevard with slip ramps to Bryant Street and a braided ramp from Federal Boulevard to eastbound US 6, improvements to Federal Boulevard between 5th and 7th Avenues, conversion of 5th Avenue to two-way operation east of Federal Boulevard, upgrading portions of the South Platte River Trail to current standards in areas impacted by construction, reconstruction of US 6 with collector-distributor roads/auxiliary lanes from Federal Boulevard to the BNSF Railroad Bridge Structure, in-kind replacement of impacted facilities for Barnum East Park, adding a bicycle/pedestrian Bridge Structure connecting Barnum Parks South and North over US6, replacement of existing bridge structures at Federal Blvd. over US 6 (F-16-EK**),** US 6 over Bryant Street (F-16-EN), US 6 over the South Platte River (F-16-EF), US 6 over I-25 (F-16-DU) and US 6 over the BNSF Railroad (F-16-EJ), and resurfacing US 6 westerly to Sheridan Boulevard.

This Project and Work is provided for under the National Environmental Policy Act (NEPA**)** and as such shall not preclude anything required as part of the I-25 Valley Highway FEIS/ROD to ensure future implementation of the FEIS Preferred Alternative in its entirety. The successful Proposer is responsible to ensure the completion of design and construction of the Work results in the ability for each phase of the FEIS/ROD to operate independently and within air quality conformity requirements. Mitigation measures needed in response to Project impacts shall be implemented with the Work, and shall be compatible with current phases of the FEIS/ROD. No Project mitigation measure resultant of the Work shall be deferred to a future project.

The Basic Configuration for this Project is based on the I-25 Valley Highway FEIS/ROD and will be included in the RFP. The successful Proposer will be responsible for design, construction and warranty of the Project generally including quality management, public information, environmental compliance, utility coordination/relocation, pavement, earthwork, drainage and water quality, final alignments, lighting, traffic operations, maintenance of traffic, and bridge/retaining wall structures. The design and construction by the successful Proposer shall be completed in accordance with applicable CDOT guidelines and standards as specifically modified in the RFP for this Project.

**2.2 Project Goals**

The following Goals have been established for the Project in priority order:

1. Manage impacts during construction.

* Project Duration
* Project Phasing

2. Maximize the use of available funds in the reconstruction of the US6 Corridor as described in the I25 Valley Highway F.E.I.S. Record of Decision.

* Include Additional Requested Elements (AREs)
* Price to complete

3. Demonstrate a commitment to enhance the established project values.

* Maximize safety of the Workers and traveling public
* Quality
* Environmental
* Project Communications Plan
* Equal Employment and Work Force Development

**2.3 Estimated Cost/Maximum Time Allowed**

The estimated Design Build Contract Guaranteed Maximum Price is $115 million. All Work required to reconstruct the bridge structures shall be completed as identified in the Request for Proposals.

**2.4 Project Schedule**

The deadline for submitting written RFQ inquiries and the SOQ due date are stated below. All inquiries must be submitted as identified in Section 2.5. RFQ inquiries, and all information submitted as part of the inquiry, shall be considered non-confidential and non-proprietary. Inquiries received which follow the prescribed process will be assigned a unique SOQ identification number, converted to PDF format, and posted on the Project web-site for viewing. Identification of the Submitter shall not be disclosed. Responses by CDOT to these inquiries shall be posted electronically on the Project web-site for viewing, CDOT will not respond verbally to any response. CDOT will not respond to inquiries which fail to follow this process. Verbal inquiries will not be accepted or responded to.

CDOT anticipates the following Project milestone dates. This schedule is subject to revision by addenda to this RFQ and subsequent Request for Proposals (RFP).

Industry Review Activities:

Issue Request for Qualifications: August 24, 2012

Deadline for Industry inquiries to RFQ: September 12, 2012

CDOT responses to Industry RFQ inquiries: September 14, 2012

Statements of Qualifications Due: September 24, 2012

Short-Listed Firms Notified: October 2, 2012

Debrief RFQ Submitters: By request and appointment

Issue Request for Proposals: October 15, 2012

**2.5 CDOT Project Management: Ex Parte Communications**

Kevin Sullivan is the CDOT Project Director. As the Project Director, Mr. Sullivan is CDOT’s sole contact person and addressee for receiving all communications regarding the Project. All inquiries and comments regarding the Project, and the procurement thereof, shall be sent by e-mail.

E-mail inquiries shall be sent to: [US6Bridges@dot.state.co.us](mailto:US6Bridges@dot.state.co.us) and shall include the wording “Inquiry Request” in the “subject” line.

During the Project procurement process, commencing with issuance of this RFQ and continuing until award of a Contract for the Project (or cancellation of the procurement), no employee, member, or agent of any Submitter shall have ex parte communications regarding this procurement with any member of CDOT, the Bridge Enterprise or their advisor, the Federal Highway Administration or their advisors, the City and County of Denver Departments of Public Works or Parks, or any of their contractors or consultants involved with the procurement, except for communications expressly permitted by this RFQ (or subsequent to issuance of the RFP, except for communications expressly permitted by the RFP). Any Submitter engaging in such prohibited communications may be disqualified at the sole discretion of CDOT’s Project Director.

**2.6 Questions and Clarifications: Addenda**

Questions and requests for clarification regarding this RFQ must be submitted to CDOT’s Project Director, as described in Section 2.5. To be considered, all questions and requests must be **received by** **4:00 pm, Mountain Time**, on the date indicated in Section 2.4.

CDOT reserves the right to revise this RFQ at any time before the SOQ due date. Such revisions, if any, will be announced by addenda to this RFQ and posted on CDOT’s Project website.

CDOT will use the following guidelines when responding to questions and requests for clarification and issuing addenda:

* All questions and requests for clarification received via e-mail will be converted to a PDF format and posted on the Project website. Identification of the Submitter shall not be disclosed.
* CDOT will prepare a written response for each question and request for clarification received via e-mail. The response will be posted on the Project web-site in PDF format. The Submitter’s name and contact information will not be disclosed.
* Inquiries not following the prescribed format will not be accepted or responded to.

**2.7 Major Participant**

As used herein, the term “Major Participant” means any of the following entities: all general partners or joint venture members of the Submitter; all individuals, persons, proprietorships, partnerships, limited liability partnerships, corporations, professional corporations, limited liability companies, business associations, or other legal entity, however organized, holding (directly or indirectly) a 25% or greater interest in the Submitter; any subcontractor(s) that will perform Work valued at 30% or more of the overall contract amount;the lead engineering/design firm(s); and each engineering/design sub-consultant that will perform 30% or more of the design Work.

CDOT may disqualify a Submitter if any of the Submitter’s Major Participants belong to more than one Submitter organization.

**2.8 Ineligible Firms**

CDOT has retained the consulting firms of Hartwig & Associates, Inc., Rocksol Consulting Group, Inc., PB Americas, Inc., Olsson Associates Consulting, Bachman PR Group, AECOM, and the Architerra Group to provide guidance in preparing and evaluating this RFQ and the RFP, and advice on related contractual and technical matters. As such, the consulting firms of Hartwig & Associates, Inc., Rocksol Consulting Group, Inc., PB Americas, Inc., Olsson Associates Consulting, Bachman PR Group, AECOM and the Architerra Group are not eligible to submit a SOQ or to act as a member of any Submitter’s team.

Requests for determination regarding this eligibility requirement may be submitted in writing to the CDOT Project Director identified in Section 2.5 of this RFQ.

**2.9 Organizational Conflicts of Interest**

The Submitter’s attention is directed to the following section of CDOT’s Design Build Rules:

2 CCR 601-15SECTION 7 - CONFLICT OF INTEREST

1. CDOT will award a Design BuildContractonly to a Firmthat does not have impaired objectivity or an unfair competitive advantage, due to any interest of the Firmthat creates an actual conflict or a significant potential conflict with the proposed contract.

2. Except as provided below, any consultant shall be disqualified from submitting a proposal on a Project, or from acting as a subconsultant or subcontractor on a Project, if CDOTdetermines that the consultant has such a conflict, including in the following situations:

a) it develops the Scope of Workfor a Design BuildProject; or,

b) it develops the RFQor RFPfor the Project; or,

c) it performs 20% or more of the Preliminary Engineering on the Project.

3. Any consultant that is so disqualified may still be part of any CDOT oversight team for the Project if CDOTdeems it appropriate.

23 CFR § 636.116 What organizational conflict of interest requirements apply to Design Build projects?

(a) State statutes or policies concerning organizational conflict of interest should be specified or referenced in the Design/Build RFQ or RFP document as well as any contract for engineering services, inspection or technical support in the administration of the Design Build contract. All Design Build solicitations should address the following situations as appropriate:

(1) Consultants and/or sub-consultants who assist the owner in the preparation of a RFP document will not be allowed to participate as an offeror or join a team submitting a proposal in response to the RFP. However, a contracting agency may determine there is not an organizational conflict of interest for a consultant or sub-consultant where:

(i) The role of the consultant or subconsultant was limited to providing preliminary design, reports, or similar ‘‘low-level’’ documents that will be incorporated into the RFP, and did not include assistance in development of instructions to offerors or evaluation criteria, or

(ii) Where all documents and reports delivered to the agency by the consultant or sub-consultant are made available to all offerors.

(2) All solicitations for Design Build contracts, including related contracts for inspection, administration or auditing services, must include a provision which:

(i) Directs offerors attention to this subpart;

(ii) States the nature of the potential conflict as seen by the owner;

(iii) States the nature of the proposed restraint or restrictions (and duration) upon future contracting activities, if appropriate;

(iv) Depending on the nature of the acquisition, states whether or not the

terms of any proposed clause and the application of this subpart to the contract are subject to negotiation; and

(v) Requires offerors to provide information concerning potential organizational conflicts of interest in their proposals. The apparent successful offerors must disclose all relevant facts concerning any past, present or currently planned interests which may present an organizational conflict of interest. Such firms must state how their interests, or those of their chief executives, directors, key project personnel, or any proposed consultant, contractor or subcontractor may result, or could be viewed as, an organizational conflict of interest. The information may be in the form of a disclosure statement or a certification.

(3) Based upon a review of the information submitted, the owner should make a written determination of whether the offeror’s interests create an actual or potential organizational conflict of interest and identify any actions that must be taken to avoid, neutralize, or mitigate such conflict. The owner should award the contract to the apparent successful offeror unless an organizational conflict of interest is determined to exist that cannot be avoided, neutralized, or mitigated.

(b) The organizational conflict of interest provisions in this subpart provide minimum standards for State Transportation Departments (STDs)to identify mitigate or eliminate apparent or actual organizational conflicts of interest. To the extent that State developed organizational conflict of interest standards are more stringent than that contained in this subpart, the State standards prevail

The Submitter is prohibited from receiving any advice or discussing any aspect relating to the Project or the procurement of the Project with any person or entity with an organizational conflict of interest, including, but not limited to those firms identified in Section 2.8; the consulting firms of Hartwig & Associates, Inc., Rocksol Consulting Group, Inc., PB Americas, Inc., Olsson Associates Consulting, Bachman PR, AECOM and the Architerra Group. Such persons and entities are prohibited from participating in any Submitter organization relating to the Project.

The Submitter agrees that if, after award, an organizational conflict of interest is discovered, the Submitter must make an immediate and full written disclosure to CDOT that includes a description of the action the Submitter has taken or proposes to take to avoid or mitigate such conflicts. If an organizational conflict of interest is determined to exist, CDOT may, at its discretion, cancel the Design Build Contract for the Project. If the Submitter was aware of an organizational conflict of interest prior to the award of the Contract and did not disclose the conflict to CDOT, CDOT may terminate the Contract for default.

**2.10 Changes to Organizational Structure**

Key Personnel or Major Participants identified in the SOQ shall not be removed, replaced, or added without the written Approval of CDOT. CDOT may revoke an awarded Contract if any Key Personnel or Major Participant identified in the SOQ is removed, replaced, or added to without CDOT’s written Approval. To qualify for CDOT’s Approval, the written request must document that the proposed removal, replacement, or addition will be equal to or better than the Key Personnel or Major Participant provided in the SOQ. CDOT will use the criteria specified in this RFQ, and the qualifications submitted in the SOQ, to evaluate all requests. Requests for removals, replacements, and additions must be submitted in writing to CDOT’s Project Director as described in Section 2.5.

**2.11 Past Performance or Experience**

Past performance or experience does not include the exercise or assertion of a person’s legal rights.

**2.12 Equal Employment Opportunity**

The Submitter will be required to follow Federal Equal Employment Opportunity (EEO) policies.

CDOT will affirmatively assure that for the Project constructed pursuant to this advertisement, equal employment opportunity will be offered to all persons without regard to race, color, creed, religion, national origin, sex, marital status, status with regard to public assistance, membership or activity in a local commission, disability, sexual orientation, or age. The Submitter will be required to follow Federal Equal Employment Opportunity (EEO) policies.

**2.13 SMALL AND DISADVANTAGED BUSINESS ENTERPRISES**

All proposers are required to provide Colorado Disadvantaged Business Enterprises (DBEs) the opportunity to compete fairly for contracting opportunities on this project. Proposers shall not discriminate on the basis of race, color, national origin, or sex and shall carry out applicable requirements of 49 CFR Part 26 in the award and administration of the contract.

In accordance with 49 CFR Part 26 and the CDOT DBE Program Plan, CDOT will establish a goal for DBE participation on the contract. The goal will be based upon subcontracting opportunities within the contract and ready, willing and able DBEs to perform such work. The goal will be set forth in the RFP. A proposer will not be eligible for contract award unless such proposer demonstrates good faith efforts to meet the goal. CDOT encourages the contractor to consider opportunities for DBEs at this preliminary stage. A list of current DBEs and their certified Work areas can be found on the Colorado UCP DBE Directory at http://coloradodbe.org/.

CDOT will monitor the efforts of the winning contractor throughout the duration of the contract. The contractor will be required to make ongoing good faith efforts to meet the goal throughout the performance of the contract and failure to do so will result in sanctions being assessed against the contractor.

The specific requirements of the DBE program will be provided in the RFP and contract.

**EMERGING SMALL BUSINESS PROGRAM**

CDOT’s Emerging Small Business (ESB) Program is an incentive based program. The details of the ESB incentives for this project will be provided in the RFP and contract.

CDOT encourages the contractor to consider opportunities for ESBs at this preliminary stage. A list of current ESBs and their certified work areas can be found on the CDOT website at http://www.coloradodot.info/business/equal-opportunity/emerging-small-business-program.

**2.14 CDOT ON THE JOB TRAINING (OJT) PROGRAM**

Construction contracts awarded by CDOT require prime contractors to offer on-the-job training (OJT) aimed at developing full journey workers in a trade or job classification on the awarded project. Though the program is open to all, trainees are to be recruited among women and minorities as available according to census data. OJT participation is mandatory under 23 Code of Federal Regulations 230. The specific requirements of the OJT program will be provided in the RFP.

**3.0 CONTENT OF SOQs AND CONFIDENTIALITY**

This section describes specific information that must be included in the SOQ. SOQs must follow the outline of this Section 3.0. Submitters shall provide brief, concise information that addresses the requirements of the Project consistent with the evaluation criteria described in this RFQ.

Documents submitted pursuant to this RFQ will be subject to the Colorado Open Records Act, C.R.S. §§ 24-72-201, et. seq. Information clearly marked as confidential and proprietary will be kept confidential by CDOT, unless otherwise provided by law. The Colorado Open Records Act provides that “Trade secrets, privileged information, and confidential commercial, and financial, data furnished by any person” to a state agency will not be produced in response to an open records request. CDOT will notify the Submitter if a request is made for such information, and the denial is challenged, so that the Submitter may take any action it deems necessary to defend the challenge. The Submitter, not CDOT, shall be the entity responsible for defending against Colorado Open Records Act disclosures for any records claimed by the Submitter to be confidential and proprietary.

**3.1 Introduction**

Provide a letter stating the business name, address, business type (e.g., corporation, partnership, joint venture, etc.), business information, and roles of the Submitter and each Major Participant listed in Form A (attached). Identify a single point of contact with his or her address, telephone number, a fax number, and e-mail address. CDOT will send all Project-related communications to this contact person during the procurement process . Authorized representatives of the Submitter organization must sign Form A. If the Submitter is a joint venture, all joint venture members must sign Form A. If the Submitter is not yet a legal entity, the Major Participants must sign Form A. Each joint venture member must certify the truth and correctness of the contents of the SOQ. The Introduction shall include a “Title Page” and “Table of Contents.” Information provided in response to Section 3.1 shall not count towards the overall page limitation defined in Section 4.2.

**3.2 Submitter Experience**

CDOT will evaluate the capabilities of the Submitter organization to effectively meet the Project Goals.

**3.2.1 Submitter Experience**

Information provided in response to Section 3.2.1, including submittal of Form C, shall not count towards the overall page limitation defined in Section 4.2. Describe the experience, up to a maximum of four highway projects of which one shall be a Design Build project that the Submitter and each Major Participant has managed, designed, and/or constructed by completing Form C (if the Submitter is not yet existing or is newly formed, please explain). For the projects in which several of the proposed Major Participants were involved, the Submitter may provide a single project description. Highlight experience relevant to the Project that the Submitter/Major Participants have gained in the last ten years. Cite and describe experiences that could apply to this Project demonstrating experiences in each of the following areas:

1. Interstate highway reconstruction and bridge structure replacement;
   1. under traffic in urban areas;
   2. within Railroad right-of-way;
      1. Successful experience in obtaining and fulfilling Construction and Maintenance (C&M) Agreements with Railroad Companies for Work within their right-of-way;
2. Construction/reconstruction using innovative designs, methods, and materials;
3. Design and construction activity integration under Design Build contracting;
4. Experience with design and construction of recreational parks;
5. Environmental compliance;
6. Public information; and
7. Full completion of the project on schedule.

Each project description must include the following information:

1. Name of the project and either the owner’s contract number or project number;
2. Owner’s name, Owner’s Project Manager’s name, address, and current e-mail, telephone and fax numbers;
3. Description of original and final project schedule milestones including milestones for design and construction;
4. Description of the Work or services provided and percentage of the Work actually performed; and
5. Description of original and final completed project contract amount.

**3.2.2 Contractor Safety Statistics**

Provide the general partners or joint venture members (contractors only) safety statistics for the last three years by completing Form B (attached). Information provided in response to Section 3.2.2 shall not count towards the overall page limitation defined in Section 4.2.

**3.3 Organization and Key Personnel**

**3.3.1 Organizational Chart(s)**

Provide organizational chart(s) showing the structure of the organization with lines identifying participants who are responsible for major functions to be performed and their reporting relationships in managing, designing, and building the Project. The chart(s) must show the functional structure of the organization down to the design discipline leader or and construction superintendent level and must identify Key Personnel by name. Indicate the anticipated percent of each Key Personnel’s time that would be committed to the Project. Identify the Submitter and all Major Participants in the chart(s). Identify the critical support elements and relationships of project management, project administration, construction management, quality control/quality assurance, safety, environmental compliance, and subcontractor administration. For each organizational chart(s), provide a brief, written description of significant functional relationships among participants and how the proposed organization will function as an integrated Design Build team. Information provided in response to Section 3.3.1 shall count towards the overall page limitation defined in Section 4.2.

**3.3.2 Resumes of Key Personnel**

Resumes of Key Personnel shall be submitted as “Appendix A” and titled “*Resumes of Key Personnel.”* Information provided in response to Section 3.3.2 shall not count towards the overall page limitation defined in Section 4.2. Resumes of Key Personnel shall be limited to one page each. If an individual fills more than one position, only one resume is required. The listing below describes the minimum qualifications for Key Personnel of the Project. Personnel who staff these key functions listed below shall be identified in the required organizational chart(s) (as described in Section 3.3.1).

1. Design Build Project Manager
2. Design Manager
3. Construction Manager
4. Design Build Quality Manager
5. Environmental Compliance Manager
6. Drainage Design Manager
7. Structural Design Manager
8. Traffic Operations Manager
9. Recreational Park Design Manager
10. Recreational Park Construction Manager

Include the following items on each resume:

* 1. Relevant licensing and registration, including registration as required in the State of Colorado.
  2. Years of experience performing similar Work.
  3. Title, roles, and responsibilities on any of the Projects listed in response to Section 3.2.1.
  4. List a minimum of three personal professional references for each key personnel.

**3.3.3 Minimum Requirements of Key Personnel**

The following provides a brief job description and minimum requirements of the Key Personnel assigned to the Project. Key Personnel will be evaluated, in part, based on the extent they meet and/or exceed such requirements. Any licenses or certifications that are required to meet the requirements of the RFQ shall be in place by the time the Proposal is submitted.

1. Design Build Project Manager
   * + The Design Build Project Manager shall be a licensed Professional Engineer in the State of Colorado and shall be in direct charge of the Work and is responsible for the administration and satisfactory completion of the project under the contract. This person shall be assigned to the Project full time and will be required to be on-site for the duration of the Project.
     + Shall have at least ten years of recent experience managing projects involving Interstate highway reconstruction and bridge structure replacement under traffic in urban areas.
     + Shall have Design Build experience.
     + Shall not be assigned any other duties or responsibilities on the Project.
     + Must Work under the direct supervision of the Design Builder’s Executive Management team (EMT). The Design Build Project Manager will report to the EMT.
2. Design Manager
   * The Design Manager will be responsible for ensuring that the overall Project design is completed and design criteria requirements are met.
   * The Design Manager shall Work under the direct supervision of the Design Build Project Manager.
   * The Design Manager shall be responsible for certifying on the monthly invoice that the construction has been completed in conformance to the stamped/sealed drawings, including stamped field revisions.

* Shall be a registered Professional Engineer in the State of Colorado.
* Shall have a minimum of ten years of recent experience in managing the design of projects involving Interstate highway reconstruction and bridge structure replacement under traffic in urban areas.
* Shall have the authority to stop construction Work if and when he/she knows or has reason to believe that any Work does not meet the standards, specification, or criteria established for the Project.
* Shall have Design Build experience.
* Shall not be assigned any other duties or responsibilities on the Project.

1. Construction Manager

* The Construction Manager shall be on site during all construction activities.
* Shall have a minimum of ten years of recent experience in managing the construction of projects involving Interstate highway reconstruction and bridge structure replacement under traffic in urban areas.
* The Construction Manager shall Work under the direct supervision of the Design Build Project Manager.
* Shall not be assigned any other duties or responsibilities on the Project.
* Should be a registered Professional Engineer in good standing in the State of Colorado.
* Shall have the authority to stop construction Work if and when he/she knows or has reason to believe that any Work does not meet the standards, specification, or criteria established for the Project.
* Shall have Design Build experience.
* Shall ensure all Work is constructed in compliance with Project standards, specifications, or criteria established for the Project.

1. Design Build Quality Manager

* Shall Work under the direct supervision of the Design Builder’s Executive Management team (to whom the Design Build Project Manager reports to).
* Responsible for the Design Builder’s quality program, quality personnel, quality planning, ensuring that quality assurance activities are independent of production, enforcement of quality system procedures, development of the quality program objectives, implementation of the quality program objectives, total system quality and management, quality records, quality documentation, review of the Quality Program Manual, and approval of the Quality Program Manual prior to submittal to CDOT.
* Shall have the authority to stop any and all Work that does not meet the standards, specifications, or criteria established for the Project.
* Shall have Design Build experience.
* Shall be a registered Professional Engineer in the State of Colorado.
* Shall have a minimum of ten years of recent experience developing, implementing, and overseeing quality programs.

E. Environmental Compliance Manager

* The Environmental Compliance Manager shall Work under the direct supervision of the Design Build Project Manager.
* Shall have at least ten years of recent experience in NPDES / MS4 regulatory requirements and recent experience in NPDES / MS4 compliance in an urban setting.
* Shall have experience with environmental documentation, including Environmental Impact Statements and implementation of resulting requirements.
* Responsible to ensure the Contractor complies with all mitigation requirements of the Project.
* Responsible to ensure the Contractor develops, implements, maintains, and documents best management practices for the Project and is in compliance with permit application requirements.

F. Drainage Design Manager

* + The Drainage Design Manager will be responsible for ensuring that the overall Project drainage and water quality design is completed and design criteria requirements are met.
  + The Drainage Design Manager shall Work under the direct supervision of the Design Manager.
  + Shall have experience associated with floodplains and coordination with Urban Drainage and Flood Control District.
* Shall be a registered Professional Engineer in the State of Colorado.
* Shall have a minimum of ten years of recent experience in managing the drainage/water quality design of projects involving Interstate highway reconstruction and bridge structure replacement under traffic in urban areas.

G. Structural Design Manager

* + The Structural Design Manager shall be responsible for ensuring that all Project structure designs, including major structures and minor structures, are completed and design criteria requirements are met.
  + The Structural Design Manager shall Work under the direct supervision of the Design Manager.
* Shall be a registered Professional Engineer in the State of Colorado.
* Shall have a minimum of ten years of recent experience in managing the bridge/retaining wall design of projects involving Interstate highway reconstruction and bridge structure replacement under traffic in urban areas.

H. Traffic Operations Manager

* + The Traffic Operations Manager shall be responsible for ensuring overall Project Traffic Management.
  + The Traffic Operations Manager shall Work under the direct supervision of the Design Build Project Manager
  + The Traffic Operations Manager shall ensure Traffic Control Plans (TCP) and Methods of Handling Traffic (MHT) are designed, implemented, evaluated, revised and maintained to ensure maximum safe and efficient flow of traffic through the Work.
  + The Traffic Operations Manager shall ensure all TCP’s and MHT’s are consistent with Construction Phasing.
  + The Traffic Operations Manager shall review and Approve all Traffic Control Plans (TCP) and Methods of Handling Traffic (MHT) implemented on the Project.
* Shall be a Certified Traffic Control Supervision in the State of Colorado.
* Shall have a minimum of ten years of recent experience in managing traffic operations.

I. Recreational Park Design Manager

* + The Recreational Park Design Manager will be responsible for ensuring that the overall Recreational Park design is completed and design criteria requirements are met.
  + The Recreational Park Design Manager shall Work under the direct supervision of the Design Manager.
  + The Recreational Park Design Manager shall be responsible for certifying that the construction has been completed in conformance to the stamped/sealed drawings, including stamped field revisions.
* Shall be a Licensed Landscape Architect in the State of Colorado.
* Shall have a minimum of five years of recent experience in the design of recreational parks, and experience working with City and County of Denver Parks and Recreations department.
* Shall not be assigned any other duties or responsibilities on the Project

J. Recreational Park Construction Manager

* The Recreational Park Construction Manager shall be on site during all park related construction activities.
* Shall have a minimum of five years of recent experience in managing the construction of recreational parks.
* The Recreational Park Construction Manager shall Work under the direct supervision of the Construction Manager.
* Should be a registered Professional Engineer in good standing in the State of Colorado.
* Shall have the authority to stop construction of the recreational park Work if and when he/she knows or has reason to believe that any Work does not meet the standards, specification, or criteria established for the Project.
* Shall ensure all recreational park Work is constructed in compliance with Project standards, specifications, or criteria established for the Project.
* Shall not be assigned any other duties or responsibilities on the Project.

K. Additional Key Personnel

The Submitter may, in its sole discretion, add additional Key Personnel in its SOQ. For any Key Personnel added by the Submitter, the Submitter must include the minimum qualifications of the individual and a resume. Additional Key Personnel are subject to the substitution Approval requirements in Section 2.10.

CDOT may add additional Key Personnel with minimum requirements in the RFP.

**3.4 Project Understanding and Approach**

* Identify and describe your understanding of Project critical issues and demonstrate your team’s approach to successful resolution of them.
* Provide your understanding of and approach to successfully delivering the Project for the following items:

* + - Meeting or exceeding the established Project goals (see section 2.2)
    - Budget Management
    - Quality Management
    - Schedule Management
    - Design and Construction Management
    - Stakeholder Involvement , including CDOT, the City and County of Denver, the City and County of Denver Parks and Recreation, and the BNSF
    - Public Involvement
    - Safety
    - Underutilized Disadvantaged Business Enterprise/Equal Employment Opportunity (UDBE/EEO)Plan

The information provided pursuant to Section 3.4 is considered proprietary and should be marked “CONFIDENTIAL” by the Submitters. Information provided in response to Section 3.4 shall count towards the overall page limitation defined in Section 4.2.

**3.5** **Legal**

The information required in response to Section 3.5 shall be submitted as “Appendix B” and titled “*Legal*.” Information provided in response to Section 3.5 shall not count towards the overall page limitation defined in Section 4.2.

**3.5.1 Acknowledgment of Clarifications and Addenda**

Identify all clarifications and addenda received by number and date by completing Form D (attached).

**3.5.2 Organizational Conflicts of Interest**

Identify all relevant facts relating to past, present, or planned interest(s) of the Submitter’s team (including the Submitter, Major Participants, proposed consultants, contractors and subcontractors, and their respective chief executives, directors, and key project personnel) which may result, or could be viewed as, an organizational conflict of interest in connection with this RFQ. See Section 2.8 and Section 2.9.

Disclose: (a) any current contractual relationships with CDOT (by identifying the CDOT contract number and the CDOT Project Engineer); (b) present or planned contractual or employment relationships with any current CDOT employee; and (c) any other circumstances that might be considered to create a financial interest in the Contract by any current CDOT employee, if the Submitter is awarded the Contract. The Submitter must also disclose any current contractual relationships with those firms listed in Section 2.8. The foregoing is provided by way of example, and shall not constitute a limitation on the disclosure obligations.

For any fact, relationship, or circumstance disclosed in response to this Section 3.5.2, identify steps that have been or will be taken to avoid, neutralize, or mitigate any organizational conflicts of interest.

In cases where Major Participants on different Submitter organizations belong to the same parent company, each Submitter must describe how the participants would avoid conflicts of interest through the qualification and Proposal phases of the Project.

**3.5.3 Legal Structure**

If the Submitter organization has already been formed, provide complete copies of the organizational documents that allow, or would allow by the time of Contract award, the Submitter and Major Participants to conduct business in the State of Colorado. If the Submitter organization has not yet been formed, provide a brief description of the proposed legal structure or draft copies of the underlying agreements if available.

**3.5.4 Bonding Capability**

Provide a letter from a surety or insurance company stating that the Submitter is capable of obtaining a Performance Bond and Payment Bond covering the Project in the amount of $115 million each. Letters indicating “unlimited” bonding capability are not acceptable. The surety or insurance company providing such letter must be licensed as surety and qualified to do business in the State of Colorado. This letter is not included in the page limit.

**3.5.5 Submitter Information**

For the Submitter (if the Submitter organization is not yet existing or newly formed, please explain), each Major Participant, and any affiliate of the Submitter or a Major Participant (including the company’s parent company, subsidiary companies, and any other subsidiary or affiliate of the company’s parent company), whose experience is cited as the basis for the company’s qualifications shall:

1. Describe the conditions surrounding any contract (or portion thereof) entered into by the company that has been terminated for cause, or which required completion by another party, within the last five years. Describe the reasons for termination and the amounts involved.
2. Describe any debarment or suspension from performing Work for the federal government, any state or local government, or any foreign governmental entity against the company.
3. For each description (1. and 2. above), identify the project owner’s representative and current phone number. Indicate “None” to any subsection above that does not apply.
4. Each Major Participant must be prequalified to perform Work in the State of Colorado. Each Major Participant must complete Form E (attached).

**3.5.6 SOQ Forms**

The information required in response to Section 3.5.6 shall be submitted as “Appendix C” and titled “*Forms A-C*.” Information provided in response to Section 3.5.6 shall not count towards the overall page limitation defined in Section 4.2.

**4.0 SOQ Submittal Requirements**

The following section describes requirements that all Submitters must satisfy in submitting SOQs. Failure of any Submitter to submit their SOQ as required in this RFQ, may result in rejection of its SOQ.

**4.1 Due Date, Time, and Location**

All SOQs must be sent by registered mail, Federal Express, UPS or a similar delivery method that furnishes proof of having been **received by CDOT no later than 4:00 p.m., Mountain Time**, on the SOQ due date indicated in Section 2.4, Faxed or e-mailed SOQs will not be accepted or considered for this project. SOQs must be **delivered** to:

Kevin Sullivan, Project Director

c/o Hartwig & Associates, Inc.

188 Inverness Drive West

Suite 675

Englewood, CO 80112

Any SOQ that fails to meet the deadline or delivery requirement will be rejected without opening, consideration, or evaluation.

**4.2 Format/Quantities**

The SOQ shall not exceed 20 single-sided pages, or 10 double-sided pages. The information submitted in pursuit to section 3.4 should be marked “confidential”, bound separately, and in a sealed envelope marked “confidential.” Except for charts, exhibits, and other illustrative and graphical information, all information must be printed on 8.5” by 11” paper. Charts, exhibits, and other illustrative and graphical information may be on 11” by 17” paper but must be folded to 8.5” by 11”, which will be counted as one sheet and must be limited to 4 sheets. All printing, except for the front cover of the SOQ and resumes, must be Times New Roman, 12-point font. All dimensional information must be shown in English units.

The front cover of each SOQ must be labeled with “US 6 Bridges Design Build Project” and “Statement of Qualifications” along with the date of submittal.

The following outline summarizes the submittal requirements and whether they are included or not included in the total submittal page limits as identified in Section 4.2:

* Introduction (is not included in page limit)
* Submitter Experience (is not included in page limit)
* Organizational Chart with description of relationships (is included in page limit)
* Project Understanding and Approach (is included in page limit)
* Appendix A - Resumes of Key Personnel (is not included in page limit)
* Appendix B – Legal, Forms D and E (is not included in page limit)
* Appendix C – Forms A, B and C (is not included in page limit)

**4.3 Submittals**

Each Submitter must provide CDOT with 7 bound copies of the SOQ confidential and non-confidential information. Each copy must be identified on its front cover, in the upper right-hand corner, as “Copy of 7 Copies”. In addition to the 7 bound copies, each Submitter shall provide 1 signed and dated “original” bound copy of the SOQ confidential and non-confidential information. The “original” designation with a signature and date shall be identified on the front cover, in the upper right-hand corner.

All binders must be packed together in one sealed package for delivery to CDOT. The outside of the sealed package must be clearly identified, labeled, and addressed as follows:

1. Return address: Submitter’s name, single point of contact person’s name, mailing address;
2. Date of submittal;
3. Contents labeled as “US 6 Bridges Design Build Project” and “Statement of Qualifications”;
4. Recipient (CDOT) as specified in Section 4.1.

**5.0 EVALUATION PROCESS**

**5.1 SOQ Evaluation**

CDOT will initially review the SOQs for responsiveness to the requirements of this RFQ. The information in the SOQ will then be measured against the evaluation criteria stated in Section 5.3.

**5.2 Interview**

CDOT reserves the right to conduct interviews with all potential Submitters prior to development of a short-list. CDOT may conduct these interviews during its evaluation of the overall SOQ submittal process and scoring. If elected by CDOT, CDOT will determine the schedule for interviews following receipt of the SOQs.

**5.3 SOQ Evaluation and Scoring**

CDOT will evaluate all responsive SOQs and measure each Submitter’s response against the criteria set forth in this RFQ, resulting in a numerical score for each SOQ. CDOT will use the following criteria and weightings:

Submitter Experience (35 Points):

* + - Experience on Interstate highway reconstruction and bridge structure replacement
      * under traffic in urban areas;
      * within Railroad right-of-way;
        + successful experience in obtaining and fulfilling Construction and Maintenance (C&M) Agreements with Railroad companies for Work within their right-of-way;
    - Experience with construction/reconstruction using innovative designs, methods, and materials;
    - Experience with design and construction activity integration under Design Build contracting;
    - Experience with design and construction of recreational parks;
    - Experience with Environmental compliance;
    - Experience with Public information;
    - Experience in fully completing projects on schedule;
    - Owner/client references; and,
    - Contractor Safety statistics.

Organization and Key Personnel (25 Points)

* Team member relevant experience and qualifications;
* Commitment and conformance to registration requirements.

Project Understanding and Approach (40 Points)

* Identification and description of understanding Project critical issues and demonstration of approach to successful resolution of them.
* Understanding of and approach to successfully delivering the Project for the following items:
* Meeting or exceeding the established Project goals (see section 2.2);
* Budget Management;
* Quality Management;
* Schedule Management;
* Design and Construction Management;
* Stakeholder involvement including CDOT, the City and County of Denver, the City and County of Denver Parks and Recreation, and the BNSF;
* Public Involvement;
* Safety Management;
* Partnering;
* Underutilized Disadvantaged Business Enterprise/Equal Employment Opportunity (UDBE/EEO).

**5.4 Determining Short-listed Submitters**

CDOT will total the scores for each responsive SOQ and prepare a ranked list of Submitters. **CDOT will short-list not more than three most highly qualified Submitters**. In the event two or more Submitters are tied for the ranking of three (3) oral interviews shall be held to distinguish between the tied Submitters and determine the third most highly qualified Submitter.

CDOT reserves the right, in its sole discretion, to cancel this RFQ, issue a new RFQ, reject any or all SOQs, seek or obtain data from any source that has the potential to improve the understanding and evaluation of the responses to this RFQ, seek and receive clarifications to a SOQ and waive any deficiencies, irregularities, or technicalities in considering and evaluating the SOQs.

This RFQ does not commit CDOT to enter into a Contract or proceed with the procurement of the Project. CDOT assumes no obligations, responsibilities and liabilities, fiscal or otherwise, to reimburse all or part of the costs incurred by the parties responding to this RFQ. All such costs shall be borne solely by each Submitter.

**5.5 Notification of Short-listing**

Upon completion of the evaluation, scoring, and short-listing process, CDOT will send the record of short-listed Submitters (if any) to all Submitters. CDOT will also publish the list on its project website at <http://www.coloradodot.info/projects/US6Bridges>

**5.6 Debriefing Meetings**

Once CDOT announces the short-list (if any), CDOT will to meet with any of the Submitter organizations requesting to be debriefed. These debriefing meetings would give Submitters and CDOT an informal setting to discuss this RFQ and the short-listing process.

**6.0 PROCUREMENT PHASE 2**

This Section 6.0 is provided for informational purposes only so that each Submitter has information that describes the second phase of the project procurement process, including a summary of certain anticipated RFP requirements. CDOT reserves the right to make changes to the following, and the short-listed Submitters must only rely on the actual RFP when and if it is issued. This Section 6.0 does not contain requirements related to the SOQ. CDOT expects to conduct an industry review of a draft RFP with the short-listed Submitters before it issues the RFP.

**6.1 Request for Proposals**

The Submitters remaining on the short-list following Phase 1 of the procurement process will be eligible to move to Phase 2 and receive an RFP. The RFP is available to the public for informational purposes however only short-listed submitters shall be allowed to submit a response to the RFP.

**6.2 RFP Content**

**6.2.1 RFP Structure**

The RFP will be structured as follows:

1. Instructions to Proposers.
2. Contract Documents.

* Book 1 (Contract Terms and Conditions)
* Book 2 (Technical Requirements)
* Book 3 (Applicable Standards)
* Book 4 (Contract Drawings)
* Reference Documents (For information only).

**6.2.2 RFP Information**

The RFP will include the following information:

1. Maximum time allowable for design and construction.
2. CDOT’s GMP for the Project.
3. Requirements for a proposed schedule of Work.
4. Requirements for submitting Alternative Configuration Concepts (ACCs) and Alternative Technical Concepts (ATCs).
5. A requirement that if the Proposer is a joint venture, each of the joint venture members will be, if awarded the Design Build Contract for the Project, be jointly and severally liable for performance of the Contractor’s obligations under the contract.
6. Additional Requested Elements (ARE’s) – To be determined

**6.3 Alternative Configuration Concepts and Alternative Technical Concept Meetings**

CDOT will offer each short-listed Proposer the opportunity to meet before the Proposal due date to discuss Alternative Configuration Concepts (ACCs) and Alternative Technical Concepts (ATCs). The meeting(s) will be held for Proposers to present ACCs that are outside the Basic Configuration, as defined in the RFP, but are determined to be “equal to or better than” the Basic Configuration by CDOT. ATCs will be covered in a similar fashion. Proposers will not be required to accept the meeting(s) offered.

**6.4 Proposals Submitted in Response to the RFP**

Short-listed Proposers that choose to continue in the procurement process must submit a two-part Proposal. One part is the technical proposal. The second part is the price proposal. The RFP will specifically define formats and page limits for the Proposal packaging and all Proposal contents.

**6.5 Proposal Evaluations**

CDOT has determined that award of the Project will be based on a “best value” determination under C.R.S. Sections 43-1-1401 through 43-1-1412.

**6.6 Stipends**

CDOT will award a stipend to each short-listed, responsible Proposers that provides a responsive but unsuccessful Proposal. The amount of such stipends, and their terms and conditions, will be stated in the RFP.

No stipends will be paid for submitting SOQs.

In consideration for paying the stipend, CDOT may use any ideas or information contained in the Proposals in connection with any Contract Awarded for the Project, or in connection with a subsequent procurement, without any obligation to pay any additional compensation to the unsuccessful short-listed Proposers.

CDOT will pay the stipend to each eligible Proposer within 90 days after the award of the Contract or the decision not to award a Contract.

**7.0 Protest Procedures**

**7.1 Protests Regarding RFQ**

Any protests regarding the SOQ shall be hand delivered to the Project Director identified in Section 2.5 of this RFQ within 7 Working days after the Submitter knows or should have known of the facts giving rise to the basis for the protest. The Submitter is responsible for obtaining proof of delivery.

No hearing will be held on the protest, but the CDOT Chief Engineer or his/her designee shall decide it on the basis of the written submissions. Any additional information regarding the protest should be submitted within the time period requested in order to expedite resolution of the protest. If any party fails to comply expeditiously with any request for information by the CDOT Chief Engineer or his/her designee, the protest may be resolved without such information.

The CDOT Chief Engineer or his/her designee will issue a written decision regarding the protest within 7 Working days after the protest is filed. The decision shall be based on and limited to a review of the issues raised by the aggrieved Submitter(s) and shall set forth each factor taken into account in reaching the decision. The CDOT Chief Engineer’s decision is final and protestor has no right of appeal. No stay of procurement will become effective.

Submitter [ ] or Major Participant [ ] (check appropriate box):

Company Name of Submitter / Major Participant (as indicated above):

Year Established: Federal Tax ID No.:

Name of Official Representative:

Contact Person:

Address:

Telephone No.: Fax No.:

E-mail address:

Business Organization (check one):

Corporation (If yes, indicate the State and Year of Incorporation):

Partnership

Joint Venture

Other (describe):

A. Business Name:

B. Business Address:

Headquarters:

Office Performing Work:

Contact Telephone Number:

C. Bonding Capacity:

Total: Available:

D. If the entity is a Joint Venture or Partnership, indicate the name and role of each member company in the space below. Complete a separate Submitter Information form for each member company and attach it to the SOQ. Also indicate the name and role of each other financially liable party and attach a separate form.

Name of Member Company Role Financial Liability

E. Submitter Bonding Capacity:

Total Bonding Capacity: Available Bonding Capacity:

Under penalty of perjury, I certify that I am the company’s Official Representative and that, to the best of my knowledge and belief, following reasonable inquiry; the foregoing is true and correct.

By\*: Print Name:

(Signature)

Title: Date:

\* Authorized representative of Submitter or Joint Venture members. If Submitter is not yet a legal authority, the Major Participants must sign Form A

[*Please make additional copies of this form as needed.*]

Contractor’s Name:

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Year | Incident Rate | Lost Work Day Index | Cost of Accident per Employee | Experience Modification Rating | No. of Fatalities | No. of Lost Work Days | No. of Recordable Injuries |
| 2010 |  |  |  |  |  |  |  |
| 2009 |  |  |  |  |  |  |  |
| 2008 |  |  |  |  |  |  |  |

Incident Rate = (Number of Injuries and Illnesses) x 200,000

Total Hours Worked

Lost Work Day Index = (Number of Lost Work Days) x 200,000

Total Hours Worked

Cost of Accident per Employee = Total Cost of Accidents

Average Number of Employees

Experience Modification Rating = Actual Claims per Year

Expected Claims Based on Past 3 Year Trending

Under penalty of perjury, I certify that I am the company’s Official Representative and that, to the best of my knowledge and belief, following reasonable inquiry; the foregoing is true and correct.

By: Print Name:

(Signature)

Title: Date:

*[Please make additional copies of this form and attach additional sheets as needed]*

|  |  |
| --- | --- |
| 1. Company Name:  Submitter [ ] or Major Participant [ ] (check appropriate box) | 2. Name of Project: |
| 3. Owner Contract No. or State Project No.: | 4. Type:  Construction  Design Build  Design |
| 5. Name of Prime Designer/Contractor: | 6. Company Role:  (joint venture partner, subcontractor, etc.) |
| 7. Owner (Name):  Project Manager (Name)  Provide the following information for the Project Manager listed above:  Address:  Phone:  Fax:  e-mail: | 8. Original Project Contract Amount: $  Final Project Contract Amount: $  Percent of Work Performed  by Own Forces (%): |
| 9. Original Project Schedule Milestones:  Final Project Schedule Milestones: | |
| 10. Project Description and Nature of Work Performed by Submitter / Major Participant: | |

[*Please make additional copies of this form as needed.*]

Submitter’s Name:

The undersigned acknowledges receipt of the addenda to the RFQ as indicated below.

**ADDENDA**

|  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Addendum/Clarification No. | |  | | Dated | |  | |
| Addendum/Clarification No. | |  | | Dated | |  | |
| Addendum/Clarification No. | |  | | Dated | |  | |
| Addendum/Clarification No. | |  | | Dated | |  | |
| Addendum/Clarification No. | |  | | Dated | |  | |

Failure to acknowledge receipt of all addenda may cause the SOQ to be considered non-responsive to the solicitation. Acknowledged receipt of each addendum must be clearly established and included with response to the RFQ.

\*By: Print Name:

(Signature)

Title: Date:

\* Authorized representative of Submitter or Joint Venture members. If Submitter is not yet a legal authority, the Major Participants must sign Form D

[*Please make additional copies of this form as needed].*

Under penalty of perjury, I certify that I am the Official Representative of

[Company Name], and that

[Company Name] is currently prequalified to perform Work for CDOT.

By: Print Name:

(Signature)

Title: Date: