## Sheet1
(CIMARRON/BIJOU) |  |  |  |  | 1-25 CORRIDOR COLORADO SPRINGS DESIGN-BUILD POTHOLE LOG | [7 empty] | CButilitylogPH Model
UTILITYOWNER- | SURFACE |  |  | TOP ELEV. | BOT. ELEV. |  | RFP | RFP | COSMIX | COSMIX
USE-POTHOLE# | ELEVATION | MATERIAL | DIAMETER | OF UTILITY | OF UTILITY | PAVEMENT | NORTHING | EASTING | NORTHING | EASTING | STATION | OFFSET | COMMENTS
ADP-F0P-3002 | 6044.31 | PVC | 1 " | 6042.39 | 6042.31 | DIRT | 66706.55 | 192570.4 | 166731.0747 | 92627.6886 | 24+05 | 45' L T | BIJOU
ADP-FOP-3002A | [10 empty] | 24+50 | 35' R T | ADELPHIA IN OVERHEAD
COS-TRA-3001 | 6006.23 | HDPE | (4) @ 1 1/4" | 6004.23 | 6003.9 | DIRT | 65609.1 | 191226.5 | 165633.605 | 91283.7645 | 561+20 | 80' L T | WEST 0 F 1-25
COS-TRA-3004 | [5 empty] | DIRT |  |  |  |  | 574+00 | 120' RT | Unable to PH (City states Util is 14' deep)
CSU-ELE-3006 | 6017.39 | STEEL | (2) @ 6" | 6014.39 | 6013.89 | DIRT | 66963.71 | 191656.01 | 166988.2393 | 91713.2822 | 579+20 | 200' L T | WEST 0 F 1-25
CSU-ELE-3008 | 6023.08 | PVC | 1 " | 6022.08 | 6022 | DIRT | 66451.55 | 191904.5 | 166476.0701 | 91961.7767 |  |  | N BON RAM P TO B IJ 0 U
CSU-GAS-3003 | 6005.64 | PLASTIC | 6" | 6001.06 | 6000.56 | DIRT | 65622.37 | 191219.5 | 165646.8752 | 91276.7644 | 561+15 | 80' L T | WEST 0 F 1-25
CSU-GAS-3006 | 6005.63 | PLASTIC | 2" | 6002.63 | 6002.46 | ASPHALT | 65622.1 | 191166.5 | 165646.6052 | 91223.7635 |  |  | SPRUCE
QST-FOP-3001 | [10 empty] | 580+85 | 80' R T | No Phole-Quest cleared Util in this loc.
QST-TEL-3004 | [10 empty] | 580+85 | 80' R T | No Phole-Quest cleared Util in this loc.
QST-TEL-3005 | [10 empty] | 581+55 | 80' R T | No Phole-Quest cleared Util in this loc.
QST-TEL-3009 | 6018.6 | NO LOC . |  |  |  |  | 67396.21 | 192024.2 | 167420.7471 | 92081.4788 | 583+90 | 90' R T | POT HOLED TO 9'4"
COS-TRA-3005 | 6017.5 | HDPE | (4) @ 1 1/4" | 6013.83 | 6013.58 | DIRT | 67111.78 | 192009.3 | 167136.312 | 92066.5786 |  |  | EAST OF 1-25
COS-TRA-3005A | 6017.79 | HDPE | 1 1'4" | 6015.62 | 6015.54 | DIRT | 67111.56 | 192028.8 | 167136.0919 | 92086.0789 |  |  | EAST OF 1-25
(FILLMORE/GARDENOFTHEGODS) |  |  |  |  | 1-25 CORRIDOR COLORADO SPRINGS DESIGN-BUILD POTHOLE LOG | [7 empty] | FGutilitylogPH Model
UTILITYOWNER- | SURFACE |  |  | TOP ELEV. | BOT. ELEV. |  | RFP | RFP | COSMIX | COSMIX
USE-POTHOLE# | ELEVATION | MATERIAL | DIAMETER | OF UTILITY | OF UTILITY | PAVEMENT | NORTHING | EASTING | NORTHING | EASTING | STATION | OFFSET | COMMENTS
ADP-F0P-2006 | [10 empty] | 749+75 | 175' L T | ADELPHIA IS OVER HEAD
ADP-F0P-2006 | [10 empty] | 750+70 | 175' L T | ADELPHIA IS OVER HEAD
COS-TRA-2001 | 6122.8 | PVC /PVC | 4"/2" | 6120.05 | 6119.72 | ASPHALT | 80129.86 | 90498.9 | 180136.759 | 90514.8486 | 715+45 | 45' L T | SB 1-25
COS-TRA-2004 | 6188.71 | HDPE | (4) @ 1 1/4" | 6183.21 | 6182.88 | ASPHALT | 83963.66 | 90074.36 | 183970.5781 | 90090.3065 |  |  | ELLSTON STREET
COS-TRA-2005 | 6208.66 | HDPE | (4) @ 1 1/4" | 6204.91 | 6204.74 | DIRT | 84766.57 | 90270.66 | 184773.4921 | 90286.6074 | 761+10 | 80' L T | WEST 0 F 1-25
COS-TRA-2006 | 6225.25 | HDPE | (4) @ 1 1/4" | 6222.33 | 6222.17 | DIRT | 87928.33 | 91421.29 | 187935.2679 | 91437.2432 | 792+90 | 140' L T | WEST 0 F 1-25
COS-TRA-2006 | 6209.86 | HDPE | (4) @ 1 1/4" | 6205.86 | 6204.53 | DIRT | 87934.57 | 91739.48 | 187941.508 | 91755.4348 | 793+00 | 100' R T | EAST 0 F 1-25
CSU-ELE-2009 | 6179.42 | CONC. |  | 6176.42 | 6175.25 | DIRT | 82312.19 | 90314.47 | 182319.0999 | 90330.4177 | 735+45 | 100' R T | ENCASED IN CONCRETE
CSU-ELE-2011 | 6188.46 | CONC. |  | 6185.46 | 6184.21 | DIRT | 83948.33 | 90060.01 | 183955.248 | 90075.9564 |  |  | ENCASED IN CONCRETE (ELLSTON ST.)
CSU-ELE-2019 | 6216.11 | CONC. |  | 6213.11 | 6212.11 | DIRT | 86629.55 | 91198.37 | 186636.4814 | 91214.3221 | 786+60 | 80' RT | ENCASED IN CONCRETE
CSU-GAS-2001 | 6179.35 | STEEL | 8" | 6174.18 | 6172.85 | DIRT | 82312.57 | 90313.5 | 182319.4799 | 90329.4477 | 737+00 | 110' R T | EAST 0 F 1-25
CSU-GAS-2002 | 6177.61 | STEEL | 10" | 6173.19 | 6172.36 | DIRT | 82424.96 | 90406.53 | 182431.8704 | 90422.4781 | 738+50 | 235' R T | EAST OF 1-25
CSU-GAS-2002A | 6177.58 | STEEL | 4" | 6173.16 | 6172.83 | DIRT | 82337.47 | 90357.63 | 182344.38 | 90373.5779 | 737+20 | 155' R T | EAST 0 F 1-25
CSU-GAS-2003 | 6188.44 | PVC | 4" | 6185.61 | 6185.19 | ASPHALT | 83991.72 | 90080.57 | 183998.6383 | 90096.5165 |  |  | ELLSTON STREET
CSU-WAT-2001 | 6160.57 | NO LOC. |  |  |  |  | 81854.85 | 90445.86 | 181861.7576 | 90461.8083 | 733+80 | 120' R T | POT HOLED TO 9'4"
CSU-WAT-2001B | 6178.53 | PLASTIC | 12" | 6172.11 | 6171.11 | ASPHALT | 82284.95 | 90332.6 | 182291.8597 | 90348.5477 | 739+20 | 240' R T | EAST 0 F 1-25
CSU-WAT-2002 | 6190.34 | NO LOC. |  |  |  |  | 83971.33 | 90046.93 | 183978.2482 | 90062.8763 |  |  | POT HOLED TO 9'0"
CSU-WAT-2003 | 6234.59 | STEEL | 21 " | 6230.92 | 6229.17 | DIRT | 85854.43 | 90629.2 | 185861.3576 | 90645.1492 | 775+10 | 165' L T | WEST 0 F 1-25
QST-FOP-2001 | 6172.85 | HDPE | (3)@ 11/4" | 6169.02 | 6168.68 | DIRT | 82198.45 | 90391.91 | 182205.3593 | 90407.858 | 736+20 | 200' R T | EAST 0 F 1-25
QST-TEL-2003 | 6188.71 | 300/400 C P | 2" | 6186.54 | 6186.38 | ASPHALT | 83963.66 | 90074.36 | 183970.5781 | 90090.3065 |  |  | ELLSTON STREET
QST-TEL-2004 | 6194.57 | 600/900 C P | 3" | 6192.74 | 6192.49 | DIRT | 84077.15 | 90069.27 | 184084.0687 | 90085.2164 | 755+20 | 175' L T | WEST 0 F 1-25
QST-TEL-2004 | 6236.6 | 200 C P | 2" | 6233.52 | 6233.35 | DIRT | 86313.22 | 90794.05 | 186320.1499 | 90810.0001 | 782+00 | 155' L T | WEST 0 F 1-25
ESP-F0P-2001 | 6191.62 | HDPE | (4) @ 1 1/4" | 6188.12 | 6187.79 | DIRT | 84029.41 | 90039.25 | 184036.3284 | 90055.1963 |  |  | ELLSTON STREET
ESP-F0P-2002 | 6175.32 | HDPE | (4) @ 1 1/4" | 6170.32 | 6169.82 | DIRT | 82301.83 | 90402.1 | 182308.7398 | 90418.0481 |  |  | SINTON ROAD
(NEVADA/ROCKRIMMON) |  |  |  |  | 1-25 CORRIDOR COLORADO SPRINGS DESIGN-BUILD POTHOLE LOG | [7 empty] | NR1utilitylogPH Model
UTILITYOWNER- | SURFACE |  |  | TOP ELEV. | BOT. ELEV. |  | RFP | RFP | COSMIX | COSMIX
USE-POTHOLE# | ELEVATION | MATERIAL | DIAMETER | OF UTILITY | OF UTILITY | PAVEMENT | NORTHING | EASTING | NORTHING | EASTING | STATION | OFFSET | COMMENTS
USE-POTHOLE# | E LEV AT 10 N |  |  | OF UTILITY | OF UTILITY
ADP-F0P-1003 | 6296.28 | CABLE | 1 " | 6294.28 | 6294.2 | DIRT | 97127.79 | 196314.2 | 197127.7593 | 96314.1297 | 297+50 | 200' R T | EAST OF 1-25
ADP-F0P-1004 | 6240.71 | HOPE | (2) @ 2" | 6233.29 | 6233.13 | DIRT | 90515.73 | 192373.4 | 190515.6994 | 92373.3297 | 221+00 | 80' RT | EAST OF 1-25
COS-TRA-1002 | 6231.37 | HOPE | (4) @ 1 1/4" | 6228.79 | 6228.2 | DIRT | 89084.4 | 191934.9 | 189084.3694 | 91934.8298 | 206+00 | 10' L T | M ED IA N
COS-TRA-1004 | 6253.88 | HOPE | (3) @ 1 1/4" | 6250.38 | 6249.88 | DIRT | 93933.09 | 195663.8 | 193933.0593 | 95663.7297 | 60+00 | 50' L T | NO. NEVADA AVENUE
CSU-ELE-1004A | 6235.8 | STEEL | (2) @ 6" | 6230.8 | 6229.8 | DIRT | 93950.09 | 193802.01 | 193950.0593 | 93801.9397 | 8+70 | 40' L T | MARK DABLING BLVD.
CSU-ELE-1004B | 6238.6 | CONC. |  | 6238.02 | 6235.1 | ASPHALT | 94996.96 | 194088.9 | 194996.9293 | 94088.8297 | 19+40 | 30' RT | ENCASED IN CONCRETE
CSU-ELE-1004C | 6230.72 | HOPE | 2" | 6226.72 | 6226.55 | DIRT | 94507.87 | 194124.01 | 194507.8393 | 94123.9397 | 18+45 | 60' L T | ROCKRIMMON BLVD.
CSU-ELE-1006A | 6237.8 | CONC. |  | 6234.3 | 6232.8 | ASPHALT | 94986.14 | 194030.1 | 194986.1093 | 94030.0297 | 19+00 | 21' L T | ENCASED IN CONCRETE
CSU-ELE-1006B | 6220.92 | NO LOC. |  |  |  | ASPHALT | 94760.57 | 193753.1 | 194760.5393 | 93753.0297 | 13+10 | 45' L T | WATER ENCOUNTERED AT 6'0"
CSU-ELE-1007 | 6222.35 | PVC | 8" | 6218.02 | 6217.35 | ASPHALT | 94800.01 | 193704.31 | 194799.9793 | 93704.2397 | 19+40 | 30' RT | MARK DABLING BLVD.
CSU-ELT-1001A | 6253.95 | CONC. |  | 6250.95 | 6250.12 | ASPHALT | 93999.88 | 195859.11 | 193999.8493 | 95859.0397 | 58+65 | 52' RT | ENCASED IN CONCRETE
CSU-ELT-1001C | 6259.46 | CONC. |  | 6256.46 | 6256.04 | ASPHALT | 96352.64 | 196127.4 | 196352.6093 | 96127.3297 | 32+55 | CL | ENCASED IN CONCRETE
CSU-GAS-1001A | 6250.14 | STEEL | 12" | 6243.39 | 6242.39 | ASPHALT | 96123.34 | 196079.2 | 196123.3093 | 96079.1297 | 29+25 | 40' L T | NO. NEVADA FRTG. ROAD
CSU-GAS-1003 | 6253.69 | STEEL | 8" | 6248.27 | 6247.61 | ASPHALT | 93988.41 | 195876.7 | 193988.3793 | 95876.6297 | 10+00 | 35' RT | NO. NEVADA FRTG. ROAD
CSU-GAS-1004 | 6225.92 | STEEL | 10" | 6219.59 | 6218.75 | ASPHALT | 94781.68 | 193569.1 | 194781.6493 | 93569.0297 | 11+80 | 28' RT | ROCKRIMMON BLVD.
CSU-GAS-1006A | 6235.5 | STEEL | 8" | 6231 | 6230.33 | ASPHALT | 93925.84 | 193829.2 | 193925.8093 | 93829.1297 | 5+70 | 28' RT | MARK DABLING BLVD.
CSU-GAS-1007 | 6228.48 | STEEL | 8" | 6223.73 | 6223.06 | ASPHALT | 94914.34 | 193569.1 | 194914.3093 | 93569.0297 | 11+18 | 90' L T | ROCKRIMMON BLVD.
CSU-WAT-1002B | 6247.2 | STEEL | 12" | 6239.7 | 6238.7 | DIRT | 96065.74 | 196072.9 | 196065.7093 | 96072.8297 | 28+70 | 45' L T | NO. NEVADA FRTG. ROAD
CSU-WAT-1003A | 6254.14 | STEEL | 8" | 6248.56 | 6247.89 | DIRT | 93972.76 | 195875.3 | 193972.7293 | 95875.2297 | 59+70 | 45' L T | NO. NEVADA AVENUE
CSU-WAT-1003B | 6243.54 | NO LOC. |  |  |  | ASPHALT | 95967.16 | 196108.6 | 195967.1293 | 96108.5297 | 26+00 | 30' RT | POTHOLED TO 10'0"
ESP-FOP-1001A | 6242.93 | HOPE | (4) @ 1 1/4" | 6238.85 | 6238.51 | DIRT | 95974.5 | 196103.1 | 195974.4693 | 96103.0297 | 27+50 | 25' RT | NO. NEVADA FRTG. ROAD
ESP-FOP-1001C | 6254.78 | HOPE | (3) @ 1 1/4" | 6249.78 | 6249.36 | DIRT | 93950.6 | 195873.7 | 193950.5693 | 95873.6297 | 11+80 | 15' RT | NO. NEVADA FRTG. ROAD
ESP-FOP-1002A | 6229.52 | HOPE | (4) @ 1 1/4" | 6226.1 | 6225.94 | DIRT | 94780.07 | 193979.6 | 194780.0393 | 93979.5297 | 15+80 | 23' L T | MARK DABLING BLVD.
ESP-FOP-1002B | 6221.85 | HOPE | (4) @ 1 1/4" | 6219.27 | 6218.85 | DIRT | 94648.69 | 193939.3 | 194648.6593 | 93939.2297 | 13+00 | 40' L T | ROCKRIMMON BLVD.
ICG-FOP-1002A | 6224.82 | CONC. |  | 6222.15 | 6221.15 | DIRT | 94482.67 | 193911.1 | 194482.6393 | 93911.0297 | 13+40 | 32' L T | ENCASED IN CONCRETE
ICG-F0P-1002C | 6221.78 | PLASTIC | 2" | 6217.78 | 6217.61 | DIRT | 94697.51 | 193703.7 | 194697.4793 | 93703.6297 | 15+10 | 39' RT | ROCKRIMMON BLVD.
ICG-F0P-1003A | 6227.8 | CONC. |  | 6225.13 | 6224.13 | DIRT | 93509.03 | 193698.9 | 193508.9993 | 93698.8297 | 3+80 | 35' L T | ENCASED IN CONCRETE
ICG-F0P-1003B | 6222.09 | NO LOC. |  |  |  | DIRT | 94649.86 | 193939.7 | 194649.8293 | 93939.6297 | 15+55 | 20' L T | POTHOLED TO 8'0"
QST-FOP-1001A | 6258.84 | CONC. |  | 6255.09 | 6254.67 | ASPHALT | 96357.18 | 196147.6 | 196357.1493 | 96147.5297 | 54+40 | 50' RT | ENCASED IN CONCRETE
QST-FOP-1001C | 6253.54 | CONC. |  | 6251.54 | 6249.96 | ASPHALT | 93998.31 | 195868.6 | 193998.2793 | 95868.5297 | 10+25 | 20' RT | ENCASED IN CONCRETE
QST-FOP-1001F | 6258.61 | CONC. |  | 6256.44 | 6254.86 | ASPHALT | 96340.83 | 196142.4 | 196340.7993 | 96142.3297 | 31+00 | 10' RT | ENCASED IN CONCRETE
QST-FOP-1003 | 6224.09 | HOPE | 6" | 6221.09 | 6220.59 | ASPHALT | 94441.08 | 193979.1 | 194441.0493 | 93979.0297 | 13+52 | 24' L T | MARK DABLING BLVD.
(NEVADA/ROCKRIMMON) |  |  |  |  | 1-25 CORRIDOR COLORADO SPRINGS DESIGN-BUILD POTHOLE LOG | [7 empty] | NR2utilitylogPH Model
UTILITYOWNER- | SURFACE |  |  | TOP ELEV. | BOT. ELEV. |  | RFP | RFP | COSMIX | COSMIX
USE-POTHOLE# | ELEVATION | MATERIAL | DIAMETER | OF UTILITY | OF UTILITY | PAVEMENT | NORTHING | EASTING | NORTHING | EASTING | STATION | OFFSET | COMMENTS
QST-FOP-1003 | 6224.09 | HOPE | 6" | 6221.01 | 6220.51 | ASPHALT | 94441.08 | 193979.1 | 194441.0493 | 93979.0297 | 13+52 | 50' R T | MARK DABLING BLVD.
QST-FOP-1007 | 6238.79 | STEEL | 6" | 6235.04 | 6234.54 | ASPHALT | 94992.55 | 194099.7 | 194992.5193 | 94099.6297 | 19+75 | 35' R T | MARK DAB LING BLVD.
QST-FOP-1009 | [10 empty] | 14+35 | 50' L T | NO PH DONE(UTILIQUEST UNSURE)
QST-FOP-1010 | 6220.2 | CONC. |  | 6217.37 | 6215.87 | ASPHALT | 94620.5 | 193863.3 | 194620.4693 | 93863.2297 | 12+90 | 48' R T | ENCASED IN CONCRETE
QST-FOP-1001A(LH) | 6220.15 | NO LOC. |  |  |  | DIRT | 94616.13 | 193862.8 | 194616.0993 | 93862.7297 | 15+20 | 80' R T | POTHOLED TO | 9'0"
QST-TEL-1004 | 6295.92 | CABLE | 1 " | 6293.67 | 6293.59 | DIRT | 97126.81 | 196308.4 | 197126.7793 | 96308.3297 | 295+80 | 212' R T | E A S T 0 F 1-25
QST-TEL-1006 | 6238.7 | PVC | 8" | 6234.2 | 6233.53 | DIRT | 94993.94 | 194095.2 | 194993.9093 | 94095.1297 |  |  | MARK DABLING BLVD.
CSU-WAT-1003A | 6252.63 | STEEL | 8" | 6245.63 | 6244.96 | ASPHALT | 93989.51 | 195716.3 | 193989.4793 | 95716.2297 |  |  | NO. NEVADA FRTG. ROAD
MCL-CBL-1001A | 6254.2 | HOPE | (3) @ 1 1/4" | 6250.2 | 6249.7 | ASPHALT | 93972.43 | 195874.7 | 193972.3993 | 95874.6297 |  |  | NO. NEVADA FRTG. ROAD
ESP-FOP-1002B | 6221.85 | HOPE | (4) @ 1 1/4" | 6218.85 | 6218.52 | DIRT | 94648.69 | 193939.3 | 194648.6593 | 93939.2297 |  |  | ROCKRIMMON BLVD.
CSU-ELE-1006B | 6220.92 | CONC. |  | 6220.5 | 6217.5 | ASPHALT | 94760.57 | 193753.1 | 194760.5393 | 93753.0297 |  |  | ENCASED IN CONCRETE
QST-FOP-1012 | 6248.66 | CONC. |  | 6247.16 | 6245.99 | DIRT | 96092.67 | 196076.4 | 196092.6393 | 96076.3297 |  |  | ENCASED IN CONCRETE