**REVISION OF SECTION 202**

**REMOVAL OF SIGN STRUCTURE**

**Section 202 of the Standard Specifications is hereby revised for this project as follows:**

**Subsection 202.01 shall include the following:**

This work includes complete removal overpass mounted sign structure and the overhead sign structure.

**Subsection 202.03 shall include the following:**

The Contractor shall safeguard salvable materials and shall be responsible for the expense of repairing or replacing damaged or missing material until it is delivered to a CDOT specific location. Please contact Albert Rodriguez @ (303) 757-9511 for designation of salvable material and location of delivery.

**Subsection 202.04 shall include the following:**

Removal of Overhead Sign Structure and Removal of Overpass Mounted Sign Bracket shall be performed as follows:

* The Contractor shall completely remove and dispose of all elements including the conduit, sign panels, and their associated footings. Removal operations shall be conducted so that there will be the least interference with public traffic using the adjacent roadway.
* At least 10 days before beginning removal of the sign structures the Contractor shall submit to the Engineer details of the removal operations showing the methods and sequence of removal and equipment to be used. These details shall include:

1. Equipment descriptions including size, number, type, capacity, and location of equipment during removal operations.
2. All temporary bracing and shoring.
3. Detailed methods for protection of the existing roadway facilities including measures to assure that people, property, utilities, and improvements will not be endangered.
4. Methods of Handling Traffic, including bicycles and pedestrians, in a safe and controlled manner.

All methods and equipment used to accomplish this item shall be subject to approval by the Engineer.

The Contractor shall have all necessary workers, materials, and equipment at the site prior to closing any lanes to traffic to accommodate removal operations. While the lanes are closed to public traffic work shall be pursued promptly and without interruption until the roadway is reopened to traffic.

Prior to reopening the roadway to public traffic, all debris, materials, and devices shall be removed and the roadways swept clean.

**Subsection of 202.11 shall include the following:**

Removal of Overhead Sign Structure and Removal of Overpass Mounted Sign Bracket will be measured by the actual number removed and disposed of in accordance with subsection 202.04.

**-2-**

**REVISION OF SECTION 202**

**REMOVAL OF SIGN STRUCTURE**

**Subsection 202.12 shall include the following:**

Pay Item Pay Unit

Removal of Overhead Sign Structure Each

Removal of Overpass Mounted Sign Bracket Each

Payment for Removal of Sign Structure and payment for Removal of Overpass Mounted Sign Bracket will be full compensation for all labor and materials required to complete the work, including equipment, debris handling, and disposal of materials.